Federated GraphQL Breakdown — BOM · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (co-located) |
| Total FE Stories | 7 |
| Impact | 🔴 4 High · 🟡 1 Medium · 🟢 2 Low |
| Estimated effort | 29–46 days (single-engineer) |
| Phase-1 surface | 21 operation-to-root-field rows · 4 client files · 7 components |
| Generated | 2026-07-17 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the BOM GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (co-located)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| BOM-FE-001 | Statically expand BOM fragment factories (pre-cutover) | Refactor | 🔴 High | 3–4 days | — | — |
| BOM-FE-002 | Migrate BOM core reads | Query migration | 🔴 High | 6–10 days | BOM-BE-B-01, BOM-BE-B-03, BOM-FE-001 | getBomByIds, getBomByParentId, getBomStatus, getBomComponentStatus |
| BOM-FE-003 | Migrate BOM search and elastic reads | Query migration | 🔴 High | 5–8 days | BOM-BE-C-01, BOM-BE-S-03 | getBomElastic, searchMaterialsBom |
| BOM-FE-004 | Migrate BOM master-data reads | Query migration | 🟢 Low | 2–3 days | BOM-BE-B-05, BOM-BE-B-03, BOM-BE-B-08 | getBomMaterialTypes, getBomPackagingMaterialTypes, getBomPackagingSubstrates, getBomPackagingUnitOfMeasure |
| BOM-FE-005 | Migrate BOM supplier reads | Query migration | 🟡 Medium | 3–5 days | BOM-BE-C-03, BOM-BE-C-01 | getComboSupplierForBom, getValidTrimSuppliersForBom, getValidRawMaterialSuppliersForBom |
| BOM-FE-006 | Migrate BOM mutations including updateBom saga handling | Mutation migration (complex) | 🔴 High | 8–12 days | BOM-BE-D-01, BOM-BE-D-02, BOM-BE-S-01 | addBom, lockBom, unlockBom, updateBom, updateBomComponentStatus |
| BOM-FE-007 | Adopt BOM supplier entity references (optional, PO-gated) | Query enhancement | 🟢 Low | 2–4 days | BOM-BE-G-17, BOM-FE-002 | getBomByIds, getBomByParentId, searchMaterialsBom |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🔴 BOM-FE-001, 🟢 BOM-FE-004 | BOM-FE-004 → BOM-BE-B-05, BOM-BE-B-03, BOM-BE-B-08 | Reads cutover — needs backend phase A/B reads live |
| 2 | 🔴 BOM-FE-002, 🟡 BOM-FE-005 | BOM-FE-002 → BOM-BE-B-01, BOM-BE-B-03<br>BOM-FE-005 → BOM-BE-C-03, BOM-BE-C-01 | Search & listing — needs backend phase C |
| 4 | 🟢 BOM-FE-007 | BOM-FE-007 → BOM-BE-G-17 | Complex writes / sagas — needs backend phase E + ADR ratification |
| 5 | 🔴 BOM-FE-003, 🔴 BOM-FE-006 | BOM-FE-003 → BOM-BE-C-01, BOM-BE-S-03<br>BOM-FE-006 → BOM-BE-D-01, BOM-BE-D-02, BOM-BE-S-01 | Externally gated — search/read-hub decision |

Cutover flow: BOM-FE-001 → BOM-FE-004 → BOM-FE-002 → BOM-FE-005 → BOM-FE-007 → BOM-FE-003 → BOM-FE-006.

Recommended Story Graph — 2 Frontend Engineers

The order map above packed onto two frontend engineers. Lanes re-sync at each step because the step's backend gate — not engineer availability — is the limiter; in a single-story step the second engineer pairs on parity checks/rollout or pre-pulls the next unblocked story. FE→FE chains stay with one engineer for context.

| Step | 👤 FE-1 | 👤 FE-2 | Backend gate (focus) |
| --- | --- | --- | --- |
| 1 | 🔴 BOM-FE-001 (3–4d) | 🟢 BOM-FE-004 (2–3d) | Reads cutover — needs backend phase A/B reads live |
| 2 | 🔴 BOM-FE-002 (6–10d) | 🟡 BOM-FE-005 (3–5d) | Search & listing — needs backend phase C |
| 4 | 🟢 BOM-FE-007 (2–4d) | — | Complex writes / sagas — needs backend phase E + ADR ratification |
| 5 | 🔴 BOM-FE-006 (8–12d) | 🔴 BOM-FE-003 (5–8d) | Externally gated — search/read-hub decision |

Elapsed (nominal midpoints): ~24 FE build days with 2 engineers vs ~38 single-engineer — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-BE-bom.md — the backend breakdown this cutover follows.