Federated GraphQL Breakdown — Attachment

Target DGS: plm-attachment (separate)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 24 | T-Shirt Size L | Complexity 🔴 0 🟠 2 🟡 14 🟢 8 | Phases B, D, F, G |
| --- | --- | --- | --- |

Target DGS: plm-attachment (separate)   |   Generated: 2026-07-07

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

- We are moving the Attachment domain — files/documents, their gallery renders, tags, ACL permissions and resource associations — off the spark-internal-graphql gateway into its own `plm-attachment` DGS subgraph. - Attachment is referenced by product (attachments, attachmentsWithMetaData, copy flows), productDetails, packaging, workspace, sample, and claims.

- It is mid-sized: 8 queries (+1 deprecated drift), 15 mutations, ~32 field resolvers on a 318-line resolver, with no polymorphism. - The defining wrinkle is the dual record shape — the backend serves attachments in both elastic snake_case and api camelCase, so ~18 field resolvers coalesce today; the DGS port should normalize that at the DTO boundary.

ACL note: read tokens are context-only, but updateAttachmentsACLPermissions and the permissions arm of bulkUpdateAttachments are *ACL writes*** (granting ADMIN/READ to partners) — that IS build work.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 8 (+1 deprecated drift) | V3 reads, by-resource (relationship+ACL), renders, from-related (🔴 search) |
| Mutations | 15 | archive/delete/copy/associate, tags, attributes/bulk, gallery publish, ACL writes, teams |
| Field-resolver type blocks | ~5 | Attachment (~25) + gallery/3d/packet sub-types |
| External dependencies | 6 keys | search 🔴; relationship/tag/user-profile 🟡; vmm/gallery 🔵 |
| Federation role | provides Attachment entity | product/productDetails/packaging/workspace/sample/claims |
| Total stories | 26 | green-field; separate subgraph |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPARK-SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

No spike-gated stories in this domain.

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 5 | 6–11d |
| D | Mutations | 14 | 20–33d |
| F | Federation & decisions | 2 | 4–7d |
| G | Field Resolvers & Tests | 3 | 12–20d |
| Total | — | 26 | 42–71d (buffered) |

ℹ️  One engineer ≈ 9–15 sprints. Parallelizable after B01.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~10–17 sprints | sequential |
| 2 engineers | ~6–10 sprints | reads + mutations parallel after B01 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1–2 | B01 (DGS module init + service wiring + first resolver) | schema (canonical DTO), service port, reads |
| 3 | D01–D07 | single-resource + tag/associate mutations |
| 4 | D08–D14 | bulk updates, ACL writes, gallery, teams |
| 5 | F01/F02 + G01 | entity fetcher + drift + core field resolvers |
| 6 | G02 + G03 | gallery/tags resolvers + tests |

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 SPARK-ATCH-B01 getAttachmentsV3(ids) | 🟢 Low [XS] | Query | — | Intent — Fetch full attachment records for a set of ids. Today — empty ids → []; token → GET … Done when: • returns attachments; empty ids → [] |
| 🔷 SPARK-ATCH-B02 getAttachmentsByResource(resourceId) | 🟡 Medium [M] | Query Calls: relationship | B01 | Intent — List the attachments hanging off a given resource (product, sample, etc.). Today — (relationship) searchByIds({id, includeNodeTypes:['attachments','attachments_v3'], maxDepth:0}) → ids → (accessControl) getUserAccessByPost → getAttachmentsByPostV3 Done when: • relationship→ids→attachments chain |
| 🔷 SPARK-ATCH-B03 getAttachmentsByResourceAndOwner(resourceId) | 🟡 Medium [M] | Query Calls: relationship | B01 | Intent — List a resource's attachments, filtered to a specific owner/author. Today — (relationship) ids → getAttachmentsByIdsAndAuthorByPostV3 Done when: • returns attachments incl. author |
| 🔷 SPARK-ATCH-B04 Renders queries (getRendersForAttachmentIds/V3Ids/byPost) | 🟡 Medium [M] | Query | B01 | Intent — Get the generated render/preview images for attachments. Today — map each id → renders loader (betaMode), compact; byPost uses an ACL token Done when: • each variant returns renders; betaMode honored |
| 🔷 SPARK-ATCH-B05 getAttachmentsfromRelatedResource(s) | 🟡 Medium [M] | Query Calls: search | B01 | Intent — Find attachments reachable through a resource's related resources. Today — (search) searchAttachmentsByParentAndRelatedResource / …ByRelatedResource(s) → content or [] Done when: • parent+related vs related-only branches |

ℹ️  SPARK-ATCH-B01: Note — DGS Module Init (this PR only): Creates attachment.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [03-schema.graphql](./03-schema.graphql).

✏️ Phase D — Mutations  (14 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 SPARK-ATCH-D01 archiveAttachmentV3 | 🟢 Low [XS] | Mutation | B01 | Intent — Archive (soft-remove) an attachment. Today — token → archiveAttachmentV3(id) Done when: • archives |
| 🔶 SPARK-ATCH-D02 deleteAttachmentV3 | 🟢 Low [XS] | Mutation | B01 | Intent — Permanently delete an attachment. Today — token → deleteAttachmentV3(humanId) → String Done when: • deletes; returns status |
| 🔶 SPARK-ATCH-D03 copyAttachmentsV3 | 🟡 Medium [M] | Mutation | B01 | Intent — Copy attachments onto another resource. Today — token for humanIds → copyAttachmentsV3 Done when: • copies; returns thumbnail + copies |
| 🔶 SPARK-ATCH-D04 associateResourcesV3 | 🟢 Low [XS] | Mutation | B01 | Intent — Link an attachment to additional resources. Today — token → associateResourcesV3 Done when: • associates resources |
| 🔶 SPARK-ATCH-D05 removeResourcesV3 | 🟢 Low [XS] | Mutation | B01 | Intent — Unlink an attachment from resources. Today — token → removeResourcesV3 Done when: • removes resources |
| 🔶 SPARK-ATCH-D06 updateAttachmentsACLPermissions | 🟡 Medium [M] | Mutation Calls: accessControl | B01 | Intent — Change who can view/administer an attachment (a permissions write). Today — build bulk {resourceId, dps:[{permissionLevel:ADMIN/READ, grantees:[partnerId]}]} for admin/read id lists → (accessControl) updateAccessControl. Note: this is an ACL… Done when: • ADMIN/READ DTOs built correctly per id list |
| 🔶 SPARK-ATCH-D07 updateAttachmentTags + updateAttachmentTagsV3 | 🟢 Low [XS] | Mutation | B01 | Intent — Update the tags on an attachment. Today — identical impl — token → updateTagsV3({attachmentId, tags}) Done when: • updates tags; both fields delegate |
| 🔶 SPARK-ATCH-D08 bulkUpdateAttachments | 🟡 Medium [M] | Mutation Calls: accessControl | B01 | Intent — Update many attachments at once (tags and/or permissions). Today — if tags → bulkUpdateTags; if permissions → (accessControl) bulkUpdateAttachmentPermissions. Latent: fire-and-forget; returns undefined (confirm contract) Done when: • tags + permissions applied • returns updated attachments (fix the undefined) |
| 🔶 SPARK-ATCH-D09 updateAttributes | 🟢 Low [XS] | Mutation | B01 | Intent — Update a single attachment's metadata attributes. Today — token for documentId → updateAttributes Done when: • updates attributes |
| 🔶 SPARK-ATCH-D10 bulkUpdateAttributes | 🟡 Medium [M] | Mutation | B01 | Intent — Update metadata attributes on many attachments at once. Today — token for documentId\¦\¦humanId → bulkUpdateAttributes Done when: • bulk-updates attributes |
| 🔶 SPARK-ATCH-D11 bulkUpdateAttachmentsV2 | 🟡 Medium [M] | Mutation | B01 | Intent — Bulk-update a batch of attachments. Today — token for documentId → bulkUpdateAttachmentsV2({attachments}) Done when: • bulk-updates (tags/packet/perms/related) |
| 🔶 SPARK-ATCH-D12 publishAttachmentToGallery | 🟡 Medium [M] | Mutation | B01 | Intent — Publish an attachment to the shared gallery. Today — branch on ATC- prefix → V3 (publishAttachmentToGalleryV3) or legacy (publishAttachmentToGallery); api returns void → return true Done when: • ATC- → V3, else legacy • returns true on no-error |
| 🔶 SPARK-ATCH-D13 unpublishAttachmentToGallery | 🟡 Medium [M] | Mutation | B01 | Intent — Remove an attachment from the shared gallery. Today — as D12, unpublish (V3/legacy by ATC-) Done when: • ATC- → V3, else legacy |
| 🔶 SPARK-ATCH-D14 associateAttachmentTeams | 🟡 Medium [M] | Mutation | B01 | Intent — Share attachments with teams (grant team access). Today — build {teamsToUpdateDto, parentId, humanIds:files, relatedResourceIds} → token for files → associateAttachmentTeams Done when: • associates teams to files |

🔗 Phase F — Federation & Stitching  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 SPARK-ATCH-F01 Attachment federated entity fetcher | 🟡 Medium [M] | Field Resolver | B01 | Intent — Let other subgraphs resolve an Attachment by its key (the federation entry point). Today — @DgsEntityFetcher(name="Attachment") resolving by id, so product (attachments Done when: • entity resolves by key • Product { attachments { id } } smoke test |
| 📄 SPARK-ATCH-F02 Deferred getAttachments drift query decision | 🟢 Low [XS] | Schema | B01 | Intent — Decide whether to keep or drop the deprecated getAttachments query. Today — getAttachments(resourceId, resourceType) is @deprecated("Use v3") with no resolver Done when: • decision + traffic survey |

🧪 Phase G — Field Resolvers & Tests  (3 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 SPARK-ATCH-G01 Attachment core field resolvers (snake/camel + access/users/businessPartnersFull) | 🟠 High [L] | Field Resolver Calls: accessControl, vmm, userAttributes | B01 | Intent — Resolve the everyday Attachment fields (names, dates, access, author, partners). Today — ~18 coalescing fields (snake/camel) + Date parse + id derivation; access (accessControl getPermissionsForResource), businessPartnersFull (vmm), createdBy/updatedBy (user) Done when: • coalescing correct (both shapes) • access/users/bps resolve | ☐ snake shape ☐ camel shape ☐ access ☐ users |
| 🔸 SPARK-ATCH-G02 tags + modelFile + gallery sub-types | 🟡 Medium [M] | Field Resolver Calls: tag, gallery, userAttributes | B01 | Intent — Resolve the tag, 3D-model-file and gallery sub-fields. Done when: • each resolves; gallery fileTypes via asset id | — |
| 📄 SPARK-ATCH-G03 Tests, parity harness | 🟠 High [L] | Tests | B01, D08, G01 | Intent — Prove the new attachment subgraph matches the old gateway (tests + parity). Today — ≥80% unit coverage; parity harness (incl Done when: • unit ≥80% • parity green (both shapes) • schema-diff intentional | ☐ Parity: DGS response matches spark-internal-graphql baseline ☐ contract |