Federated GraphQL Breakdown — Discussion

Target DGS: plm-discussion (separate)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 32 | T-Shirt Size XL | Complexity 🔴 0 🟠 4 🟡 15 🟢 13 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-discussion (separate)   |   Generated: 2026-07-07

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

- We are moving the Discussion domain — threaded discussions/replies on products, samples and workspaces, their participants, sample discussions, flags (critical/editable/tag), read-receipts and bulk operations — off the spark-internal-graphql gateway into its own `plm-discussion` DGS subgraph. - Discussion is referenced by product and workspace (it provides discussionsCount/discussionsV2 and the TechPack ResourcesCount.discussions count, SPARK-PROD-F02).

- It is large: it consolidates three API versions (v1/v2/V3) into one subgraph — 11 queries + 26 mutations (plus 3 schema-drift ops), ~12 field-resolver type blocks, and the `Resource` union (Product | SampleV2 | WorkspaceV2, resolved by id prefix). - The defining wrinkles are the *`core` twins (system-context versions of public ops — paired per story) and the participant-management** surface (V2 + V3 + core delete over users/teams/partners/design-partners).

ACL note: read/write tokens are context-only. The drop/undrop partner bookkeeping is driven by the workspace dispatcher (workspaceBusinessPartnerActionsV2), so it is a deferred drift decision, not build work here.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 11 | by-id/by-resource/by-thread, version history (V3), elastic (🔴 search), sample |
| Mutations | 26 (+3 drift) | add/update/delete, replies, sample, flags, files clone, read-receipts, participants V2/V3 + core twins |
| Field-resolver type blocks | ~12 | Discussion/FullDiscussion/DiscussionReply/participants/team + the Resource union + versioned |
| Polymorphism | 1 union | Resource → @DgsTypeResolver (+1 complexity tier) |
| External dependencies | 6 keys | search 🔴; attachment/user-profile/user-group 🟡; vmm/tag 🔵 |
| Federation role | provides Discussion entity + ResourcesCount.discussions | product / workspace |
| Total stories | 37 | green-field; separate subgraph |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPARK-SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 SPARK-DISC-E01 — Participants V2 (updateParticipantsV2 + deleteParticipantV2) | SPARK-SPIKE-01 | Non-Atomic Write Saga |
| 🔴🔬 SPARK-DISC-E02 — Participants V3 (updateParticipantsV3 + coreUpdate + coreDelete + deleteParticipantV3) | SPARK-SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 7 | 9–15d |
| C | Search & Listing | 2 | 4–7d |
| D | Mutations | 13 | 22–37d |
| E | Participant management | 2 | 6–10d |
| F | Federation & decisions | 3 | 4–7d |
| G | Field Resolvers & Tests | 5 | 13–22d |
| Total | — | 37 | 61–102d (buffered) |

ℹ️  One engineer ≈ 13–21 sprints. Parallelizable after B01.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~14–24 sprints | sequential |
| 2 engineers | ~8–14 sprints | reads + mutations + participants parallel after B01 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1–2 | B01 (DGS module init + service wiring + first resolver) | schema (~20 types + Resource resolver + ~12 inputs), service port (v1/v2/V3 consolidate) |
| 3 | B01–B07 + C01–C02 | reads + elastic + sample |
| 4 | D01–D08 | add/update/delete/reply/sample/flags |
| 5 | D09–D13 + E01 | clone/read-receipts, V3 add/bulk/update, participants V2 |
| 6 | E02 + F01–F03 | participants V3 + entity fetcher + TechPack count + drift |
| 7 | G01–G05 | field-resolver surface (incl. Resource union) + tests |

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (7 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 SPARK-DISC-B01 getDiscussionV2 (+ coreGetDiscussionV2) | 🟢 Low [XS] | Query | — | Intent — Fetch a single discussion (comment thread) by id. Today — GET discussions/v2?ids={id} → FullDiscussion; core* = system context Done when: • returns discussion; core uses system context |
| 🔷 SPARK-DISC-B02 getDiscussionByIdsV2 | 🟢 Low [XS] | Query | B01 | Intent — Fetch several discussions by ids. Today — GET … Done when: • returns by ids |
| 🔷 SPARK-DISC-B03 getDiscussionsCount | 🟢 Low [XS] | Query | B01 | Intent — Count discussions per resource. Today — count by resourceId/resourceType → [ResourceCount] Done when: • returns per-resource counts |
| 🔷 SPARK-DISC-B04 getDiscussionOnResource | 🟢 Low [XS] | Query | B01 | Intent — List the discussions on a given resource. Today — discussions for a resource Done when: • returns discussions |
| 🔷 SPARK-DISC-B05 getDiscussionsByThread | 🟢 Low [XS] | Query | B01 | Intent — List the discussions in a thread. Today — discussions in a thread Done when: • returns thread discussions |
| 🔷 SPARK-DISC-B06 getUnsentDiscussions | 🟢 Low [XS] | Query | B01 | Intent — List discussions queued but not yet sent (admin view). Today — GET … Done when: • returns unsent |
| 🔷 SPARK-DISC-B07 getVersionedDiscussions (+ threads) | 🟡 Medium [M] | Query | B01 | Intent — Return a discussion's version history. Today — (own V3) version history Done when: • both return version history |

ℹ️  SPARK-DISC-B01: Note — DGS Module Init (this PR only): Creates discussion.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [03-schema.graphql](./03-schema.graphql).

🔍 Phase C — Search & Listing  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 SPARK-DISC-C01 getDiscussionsV2 (elastic) | 🟡 Medium [M] | Query Calls: search | B01 | Intent — Search discussions for a resource via elastic (partner-filtered). Today — (search) elastic discussions by resourceId/resourceType (partner-filtered) → DiscussionElastic Done when: • elastic query + partner filter |
| 🔷 SPARK-DISC-C02 getSampleDiscussion | 🟡 Medium [M] | Query | B01 | Intent — List discussions scoped to a sample. Today — sample-scoped discussions Done when: • returns sample discussions |

✏️ Phase D — Mutations  (13 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔶 SPARK-DISC-D01 addDiscussionV2 | 🟡 Medium [M] | Mutation Calls: attachment | B01 | Intent — Post a new discussion, optionally with attachments. Today — create + (attachment) bulk attachment input Done when: • creates; attachments associated | — |
| 🔶 SPARK-DISC-D02 addDiscussionReplyV2 + updateDiscussionReplyV2 | 🟡 Medium [M] | Mutation Calls: attachment | B01 | Intent — Add or edit a reply on a discussion. Today — add/update reply + (attachment) input (isAttachmentsV3 flag) Done when: • add + update reply; v3-attachment flag honored | — |
| 🔶 SPARK-DISC-D03 updateDiscussionV2 | 🟢 Low [XS] | Mutation | B01 | Intent — Edit a discussion's body. Today — PUT discussion body Done when: • updates | — |
| 🔶 SPARK-DISC-D04 deleteDiscussionV2 | 🟢 Low [XS] | Mutation | B01 | Intent — Delete a discussion. Today — delete by id → ID Done when: • deletes | — |
| 🔶 SPARK-DISC-D05 deleteDiscussionReplyV2 | 🟢 Low [XS] | Mutation | B01 | Intent — Delete a reply. Today — delete reply → ID Done when: • deletes reply | — |
| 🔶 SPARK-DISC-D06 deleteDiscussionPartnersV2 | 🟢 Low [XS] | Mutation | B01 | Intent — Remove partners from a discussion. Today — delete partners from a discussion → ID Done when: • removes partners | — |
| 🔶 SPARK-DISC-D07 Sample discussions (V2/V3 + bulk) | 🟡 Medium [M] | Mutation | B01 | Intent — Create sample-scoped discussions. Today — sample-scoped create Done when: • each creates sample discussion(s) | — |
| 🔶 SPARK-DISC-D08 Flags (critical / editable / tag) | 🟢 Low [XS] | Mutation Calls: tag | B01 | Intent — Set discussion flags (critical / editable / tag). Today — @DgsMutation → DiscussionReply Done when: • each flag updates | — |
| 🔶 SPARK-DISC-D09 cloneFilesForBulkDiscussion | 🟡 Medium [M] | Mutation Calls: attachment | B01 | Intent — Copy attachments when bulk-creating discussions. Today — token → Promise.all(attachmentIds.map(id → (attachment) cloneAttachmentV3({cloneReferences}, id))) Done when: • clones each id | — |
| 🔶 SPARK-DISC-D10 discussionReadByUsers | 🟡 Medium [M] | Mutation | B01 | Intent — Mark discussions as read for a set of users. Today — mark read across discussionIds/discussionThreadIds for readByUserList Done when: • records read receipts | — |
| 🔶 SPARK-DISC-D11 addDiscussionV3 (+ coreAddDiscussionV3) | 🟡 Medium [M] | Mutation Calls: attachment | B01 | Intent — Post a new discussion (V3 model) with attachments. Today — (own V3) create + attachments; core* = system context Done when: • creates; core uses system context | — |
| 🔶 SPARK-DISC-D12 addBulkDiscussionV3 | 🟠 High [L] | Mutation Calls: attachment | B01 | Intent — Post discussions across many resources at once (V3). Today — (own V3) bulk create across resources + attachments → BulkDiscussionOutputV3. - Note: coreAddBulkDiscussionV3 is schema-drift (no resolver — see F03) Done when: • bulk creates | ☐ bulk ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔶 SPARK-DISC-D13 updateDiscussionV3 (+ coreUpdateDiscussionV3) | 🟡 Medium [M] | Mutation | B01 | Intent — Edit a discussion (V3 model). Today — (own V3) update; core* = system context Done when: • updates; core context | — |

⚙️ Phase E — Complex Operations  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 SPARK-DISC-E01 Participants V2 (updateParticipantsV2 + deleteParticipantV2) 🔴🔬 Spike-gated on SPARK-SPIKE-01 (Non-Atomic Write Saga) | 🟡 Medium [M] | Mutation Calls: userGroup | SPARK-SPIKE-01, B01 | Intent — Add or remove participants on a discussion (V2). Today — add participants (AddParticipantInput) / remove a participant (team/user/partner) Done when: • add + remove participants | — |
| 🔴🔬 🔶 SPARK-DISC-E02 Participants V3 (updateParticipantsV3 + coreUpdate + coreDelete + deleteParticipantV3) 🔴🔬 Spike-gated on SPARK-SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: userGroup | SPARK-SPIKE-01, B01 | Intent — Add / update / remove participants on a discussion with the richer V3 model. Today — richer participant model — updateParticipantsV3 / coreUpdateParticipantsV3 - (participants + relatedResources + resourceType), coreDeleteParticipantsV3… Done when: • each path updates/removes the right participants | ☐ update ☐ coreUpdate ☐ coreDelete ☐ delete |

🔗 Phase F — Federation & Stitching  (3 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 SPARK-DISC-F01 Discussion federated entity fetcher | 🟡 Medium [M] | Field Resolver | B01 | Intent — Let other subgraphs resolve a Discussion by key. Today — @DgsEntityFetcher(name="Discussion") by discussionId; provides discussionsCount/discussionsV2 Done when: • entity resolves by key • cross-subgraph smoke |
| 🔸 SPARK-DISC-F02 ResourcesCount.discussions (TechPack — SPARK-PROD-F02) | 🟢 Low [XS] | Field Resolver | B01 | Intent — Contribute the discussions count to the TechPack rollup. Today — extend type ResourcesCount @key(fields:"productId partnerId") { discussions: [ID] } with a @DgsEntityFetcher; fills the TechPack discussions count (the discussion side… Done when: • field resolves; parity vs facade |
| 📄 SPARK-DISC-F03 Deferred drift decision (drop/undrop + coreAddBulkDiscussionV3) | 🟢 Low [XS] | Schema | B01 | Intent — Decide the fate of drop/undrop + a drift bulk query that have no resolvers. Today — dropPartnerFromDiscussionIds/unDropPartnerFromDiscussionIds (no resolver — run inside workspaceBusinessPartnerActionsV2); coreAddBulkDiscussionV3 (no resolver) Done when: • decision + traffic survey |

🧪 Phase G — Field Resolvers & Tests  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 SPARK-DISC-G01 Discussion + FullDiscussion + DiscussionContent field resolvers | 🟠 High [L] | Field Resolver Calls: userAttributes, tag | B01 | Intent — Resolve the core discussion / content fields. Done when: • each field resolves | ☐ bodies ☐ users ☐ resource ☐ replies |
| 🔸 SPARK-DISC-G02 DiscussionReply + NotificationStatus field resolvers | 🟡 Medium [M] | Field Resolver Calls: attachment, userAttributes | B01 | Intent — Resolve reply and notification-status fields. Done when: • each resolves | — |
| 🔸 SPARK-DISC-G03 Participants + Team + Participant sub-types | 🟡 Medium [M] | Field Resolver Calls: userAttributes, vmm | B01 | Intent — Resolve participant / team sub-type fields. Done when: • teams/users/bp resolve | — |
| 🔸 SPARK-DISC-G04 Resource union members + Versioned + DiscussionReadByUsers | 🟡 Medium [M] | Field Resolver Calls: userAttributes | B01 | Intent — Resolve the resource-union, versioned and read-by fields. Done when: • each resolves | — |
| 📄 SPARK-DISC-G05 Tests, parity harness | 🟠 High [L] | Tests | B01, D12, E02, G01 | Intent — Prove the discussion subgraph matches the old gateway. Today — ≥80% unit coverage; parity harness (incl Done when: • unit ≥80% • parity green • schema-diff intentional | ☐ Parity: DGS response matches spark-internal-graphql baseline ☐ contract |