Federated GraphQL Breakdown — Packaging

Target DGS: plm-product (co-located)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 24 | T-Shirt Size L | Complexity 🔴 0 🟠 2 🟡 9 🟢 13 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-product (co-located)   |   Generated: 2026-07-07

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

- We are moving the Packaging domain — packaging records, their dielines (print artwork specs), printers, elements, and exports — off the spark-internal-graphql gateway into the `plm-product` DGS. - It is mid-sized with a wide schema (24 object types, 20 inputs): 7 queries, 10 mutations, 17 field resolvers on a 273-line resolver, but no polymorphism.

Two pieces carry the real work: `updatePackaging`, a multi-step write (body, then attachment remove via archive + relationship, then attachment add via relationship + attribute update) with no rollback; and `suggestedRetailPriceByDPCI`, a multi-hop pricing field (printers → dielines → DPCIs → pricing service).

ACL note: the current code obtains per-resource capability tokens via ACL; ACL is ignored in the DGS implementation (no ACL story) — noted for context only.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 7 | 2 cacheable master-data; 1 elastic (🔴 search) |
| Mutations | 10 | 9 simple + updatePackaging (multi-step) |
| Field-resolver type blocks | 4 | Packaging (12), Dieline (3), PrinterDieline (1), PackagingElement (1) |
| External dependencies | 7 keys (2 🔴 · 3 🟡 · 2 🔵) | search/attachment 🔴; relationship/user-profile/tag 🟡 |
| Federation contributions | 1 (Product) | internal (co-located) |
| Total stories | 26 | green-field |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPARK-SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 SPARK-PKG-E01 — updatePackaging (multi-step write) | SPARK-SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 6 | 6–11d |
| C | Search & Listing | 1 | 2–4d |
| D | Mutations (simple) | 9 | 13–22d |
| E | Complex (updatePackaging) | 1 | 5–8d |
| F | Federation (Product, internal) | 1 | 1–2d |
| G | Field Resolvers & Tests | 6 | 15–25d |
| Total | — | 26 | 42–72d (buffered) |

ℹ️  One engineer ≈ 9–15 sprints.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~10–17 sprints | sequential |
| 2 engineers | ~6–10 sprints | reads + mutations parallel after B01 |
| 3 engineers | ~4–7 sprints | critical path A → E01 → G04 → G06 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1 | B01 (DGS module init + service wiring + first resolver) | schema, service port, core reads |
| 2 | B04–B06 + C01 + D02/D05–D07 | master-data + search + simple mutations |
| 3 | D01/D03/D04/D08/D09 | create/bulk/clone/component-status |
| 4 | E01 + F01 | multi-step update + Product links |
| 5 | G01–G03 | ACL/users/refs field resolvers |
| 6 | G04/G05 + G06 | pricing + dieline resolvers + tests |

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (6 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 SPARK-PKG-B01 getPackagings(...) | 🟢 Low [XS] | Query | — | Intent — List packagings with paging and filters. Today — getPackagings() → paged Done when: • all 7 filter args forwarded; defaults page=0/size=10000 |
| 🔷 SPARK-PKG-B02 getPackagingById(packagingId) | 🟢 Low [XS] | Query | B01 | Intent — Fetch one packaging by id. Today — token → getPackagingById Done when: • returns packaging; miss→null |
| 🔷 SPARK-PKG-B03 getDielines(...) | 🟢 Low [XS] | Query | B01 | Intent — List dielines (print layouts) for a packaging. Today — getDielines → .dielines Done when: • filters forwarded; returns the dielines array |
| 🔷 SPARK-PKG-B04 getPackagingFieldValuesByType(type, ids) | 🟢 Low [XS] | Query | B01 | Intent — Return packaging field-value lookups by type. Today — getPackagingFieldValuesByType(type, ids) Done when: • by type (+optional ids) |
| 🔷 SPARK-PKG-B05 getDielineEvaluationStatuses (cacheable) | 🟢 Low [XS] | Query | B01 | Intent — Return the dieline evaluation-status lookup (cached). Today — getDielineEvaluationStatuses() Done when: • returns statuses; cached |
| 🔷 SPARK-PKG-B06 getCountries(codes) (cacheable) | 🟢 Low [XS] | Query | B01 | Intent — Return the country lookup (cached). Today — getCountries(codes) Done when: • returns countries (optionally filtered by codes) |

ℹ️  SPARK-PKG-B01: Note — DGS Module Init (this PR only): Creates packaging.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [03-schema.graphql](./03-schema.graphql).

🔍 Phase C — Search & Listing  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 SPARK-PKG-C01 getPackagingElastic(parentHumanId) | 🟡 Medium [M] | Query Calls: search | B01 | Intent — Search a product's packagings via elastic. Today — (search) search.getPackagingElastic → .content. EXT: search Done when: • parentId: elastic query built; returns content |

✏️ Phase D — Mutations  (9 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 SPARK-PKG-D01 addPackaging | 🟡 Medium [M] | Mutation | B01 | Intent — Create a packaging. Today — POST packaging/v1. Throw on validationErrors/message Done when: • creates • validation error → exception |
| 🔶 SPARK-PKG-D02 evaluateDieline | 🟢 Low [XS] | Mutation | B01 | Intent — Trigger evaluation of a dieline. Today — PUT packaging/v1/dielines/{dielineId}/evaluate Done when: • evaluates the dieline |
| 🔶 SPARK-PKG-D03 bulkAddPackagings | 🟡 Medium [M] | Mutation | B01 | Intent — Create many packagings at once. Today — bulkAddPackagings. Throw on validationErrors/message Done when: • bulk creates • error → throw |
| 🔶 SPARK-PKG-D04 bulkUpdatePackagings | 🟡 Medium [M] | Mutation | B01 | Intent — Update many packagings at once. Today — token for packaging[].humanId → bulkUpdatePackagings. Throw on error Done when: • bulk updates • error → throw |
| 🔶 SPARK-PKG-D05 exportPackaging | 🟢 Low [XS] | Mutation | B01 | Intent — Kick off a packaging export. Today — token → requestPackagingExport({workspace_id, workspace_description, product_ids}) → request id Done when: • returns the export request id |
| 🔶 SPARK-PKG-D06 lockPackaging | 🟢 Low [XS] | Mutation | B01 | Intent — Lock a packaging from edits. Today — token → PUT packaging/v1/{id}/lock Done when: • locks |
| 🔶 SPARK-PKG-D07 unlockPackaging | 🟢 Low [XS] | Mutation | B01 | Intent — Unlock a packaging. Today — token → PUT packaging/v1/{id}/unlock Done when: • unlocks |
| 🔶 SPARK-PKG-D08 cloneFilesForDielines | 🟡 Medium [M] | Mutation Calls: attachment | B01 | Intent — Copy attachment files for dielines. Today — token → Promise.all(attachmentIds.map(id => (attachment) cloneAttachmentV3({cloneReferences}, id))), flatten. EXT: attachment Done when: • clones each id with the shared cloneReferences |
| 🔶 SPARK-PKG-D09 updatePackagingComponentStatus | 🟢 Low [XS] | Mutation | B01 | Intent — Update component status on packagings. Today — updatePackagingComponentStatus({productId, ids, status}). No JWT — confirm backend-enforced Done when: • updates statuses • no-token behaviour documented |

⚙️ Phase E — Complex Operations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 SPARK-PKG-E01 updatePackaging (multi-step write) 🔴🔬 Spike-gated on SPARK-SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: attachment, relationship | SPARK-SPIKE-01, B01 | Intent — Edit a packaging — a multi-step write (body + attachments + relationships) with no rollback today. Today — token; set humanId=packagingId; PUT packaging/v1 (body); 2) if attachmentsToRemove → (attachment) archiveAttachmentBulkV2 + (relationship) removeRelationship; 3) if… Done when: • all branches in order • add rejects on status≥400; remove error handling decided • partial-failure strategy | ☐ body-only ☐ remove ☐ add ☐ status≥400 ☐ partial-failure ☐ Parity: DGS response matches spark-internal-graphql baseline |

🔗 Phase F — Federation & Stitching  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 SPARK-PKG-F01 Product packaging links (internal, same subgraph) | 🟢 Low [XS] | Field Resolver | B01 | Intent — Expose a product's packagings on the Product type (same subgraph). Today — Product references packaging (e.g. components(...packaging), packaging attributes) from the co-located packaging service Done when: • resolves in-process; no gateway hop |

🧪 Phase G — Field Resolvers & Tests  (6 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 SPARK-PKG-G01 access + businessPartner + participantDetails | 🟡 Medium [M] | Field Resolver Calls: vmm, userGroup | B01 | Intent — Resolve a packaging's access / partner / participant fields. Done when: • each resolves; null-safe | — |
| 🔸 SPARK-PKG-G02 createdBy + updatedBy + dielineEvaluators | 🟢 Low [XS] | Field Resolver Calls: userAttributes | B01 | Intent — Resolve the people fields on a packaging. Done when: • each resolves; null id → null | — |
| 🔸 SPARK-PKG-G03 product + workspaces + attachments | 🟡 Medium [M] | Field Resolver Calls: search | B01 | Intent — Resolve a packaging's product, workspaces and attachments. Done when: • product null when not PID* • workspaces/attachments via elastic | — |
| 🔸 SPARK-PKG-G04 suggestedRetailPriceByDPCI + waveDescription + retailPrice | 🟠 High [L] | Field Resolver Calls: tag, apex | B01 | Intent — Resolve pricing fields (the dieline→DPCI→price chain). Today — suggestedRetailPriceByDPCI — gated on requiresSuggestedRetailPrice + a BP id: - collect printer ids from packagingElements → getDielines(printerIds) → unique dpcis →… Done when: • price chain matches source; gate honored • wave tag fallback • retailPrice→0 | ☐ price chain ☐ gate ☐ wave ☐ retailPrice |
| 🔸 SPARK-PKG-G05 Dieline + PrinterDieline + PackagingElement field resolvers | 🟡 Medium [M] | Field Resolver Calls: attachment, search, userAttributes | B01 | Intent — Resolve the dieline / printer-dieline / element sub-type fields. Done when: • each field resolves to the right source | — |
| 📄 SPARK-PKG-G06 Tests, parity harness | 🟡 Medium [M] | Tests | B01, E01, G03, G04 | Intent — Prove the packaging subgraph matches the old gateway. Today — ≥80% unit coverage; parity fixtures (incl Done when: • unit ≥80% • parity green • schema-diff intentional | — |