Federated GraphQL Breakdown — Sample

Target DGS: plm-sample (separate)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 28 | T-Shirt Size XL | Complexity 🔴 0 🟠 5 🟡 11 🟢 12 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-sample (separate)   |   Generated: 2026-07-07

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

- We are moving the Sample domain — physical/virtual samples, their rounds, evaluations, RFID locations and master-data — off the spark-internal-graphql gateway into its own `plm-sample` DGS subgraph. - Sample is referenced by product (Product.samples/sampleIds), measurement (SampleV2.sampleMeasurement) and workspace (sample report + drop/undrop).

- It is large and mid-high risk: 23 queries, 9 mutations (+3 schema-drift), ~45 field resolvers on a 430-line resolver. - The cost concentrates in the wide `SampleV2` entity with prefix-gated polymorphic parent hydration (product / trim / color / fabric / artwork / asset), the `SampleAsset` union, and two evaluation writes (updateSamplesV2, bulkEvaluateSamples). - A long master-data tail (~13 cacheable lookups) is cheap.

ACL note: reads/writes curry capability tokens; drop/undrop bookkeeping lives in the workspace dispatcher. ACL is ignored in the DGS implementation (no ACL story) — context only.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 23 | ~13 cacheable master-data + by-id/parent + 2 RFID |
| Mutations | 9 (+3 deferred) | create/round/update/workspace-assoc/export/retry/clone + 2 evaluation writes |
| Field-resolver type blocks | ~7 | SampleV2 (~35) + 6 sub-types |
| Polymorphism | 1 union (SampleAsset) | B01 |
| External dependencies | ~20 keys (all cross-subgraph) | search 🔴; product/workspace/measurement/material/… 🟡 |
| Federation role | provides SampleV2 entity | product/measurement/workspace reference it |
| Total stories | 33 | green-field; separate subgraph |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPARK-SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 SPARK-SMPL-B01 — getSampleById(id) | SPARK-SPIKE-05 | Polymorphic Type Resolution |
| 🔴🔬 SPARK-SMPL-E01 — updateSamplesV2 | SPARK-SPIKE-01 | Non-Atomic Write Saga |
| 🔴🔬 SPARK-SMPL-E02 — bulkEvaluateSamples | SPARK-SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 8 | 8–14d |
| C | RFID Reads | 2 | 4–7d |
| D | Mutations (simple) | 7 | 11–18d |
| E | Complex (evaluation writes) | 2 | 9–15d |
| F | Federation & decisions | 2 | 4–7d |
| G | Field Resolvers & Tests | 7 | 31–51d |
| Total | — | 33 | 70–116d (buffered) |

ℹ️  One engineer ≈ 14–24 sprints. Parallelizable after B01; 2–3 engineers recommended.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~16–27 sprints | sequential |
| 2 engineers | ~10–16 sprints | reads + mutations parallel after B01 |
| 3 engineers | ~6–11 sprints | critical path A → G02 → G07; E in parallel |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1–2 | B01 (DGS module init + service wiring + first resolver) | schema, union resolver, service port, reads + master-data |
| 3 | C01/C02 + D02–D06 | RFID + simple mutations |
| 4 | D01/D07 + E01/E02 | create(+files), clone, evaluation writes |
| 5 | G01/G02 | users + the prefix-gated parents/union (X-Large) |
| 6 | G03–G06 | partners/assoc/attachments/participants |
| 7 | F01/F02 + G07 | entity fetcher + drift decision + tests |

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (8 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔴🔬 🔷 SPARK-SMPL-B01 getSampleById(id) 🔴🔬 Spike-gated on SPARK-SPIKE-05 (Polymorphic Type Resolution) | 🟢 Low [XS] | Query | SPARK-SPIKE-05 | Intent — Fetch one sample by id. Today — getSampleById Done when: • returns sample; miss→null |
| 🔷 SPARK-SMPL-B02 getSamplesByIdsV2(ids) (batched) | 🟡 Medium [M] | Query Calls: recentlyViewed | B01 | Intent — Fetch several samples by ids (batched); records 'recently viewed'. Today — batchParallelOperation(chunk) → token per batch → getSamplesByIdsV2ByPost. Side-effect: exactly-one → (recentlyViewed) addRecentlyViewed Done when: • batched by chunk size • single → recentlyViewed |
| 🔷 SPARK-SMPL-B03 getSamplesByParentId(humanId) | 🟡 Medium [M] | Query Calls: relationship | B01 | Intent — List a product's samples. Today — (relationship) getByID({id, type:'sample', maxDepth:0}) → ids → token → getSamplesByIdsV2; empty → [] Done when: • relationship→ids→samples chain |
| 🔷 SPARK-SMPL-B04 getColorSamplesByParentId(id) | 🟢 Low [XS] | Query | B01 | Intent — List a product's colour samples. Today — getColorSamplesByParentId Done when: • returns color samples |
| 🔷 SPARK-SMPL-B05 getSampleRounds(humanId) | 🟢 Low [XS] | Query | B01 | Intent — List the evaluation rounds on a sample. Today — token → getSampleRounds Done when: • returns rounds |
| 🔷 SPARK-SMPL-B06 getSampleExports | 🟢 Low [XS] | Query | B01 | Intent — List sample export jobs. Today — getSampleExports Done when: • returns exports |
| 🔷 SPARK-SMPL-B07 getSampleNotificationErrors | 🟢 Low [XS] | Query Calls: notification | B01 | Intent — List failed sample notifications. Today — (notification) getSampleNotificationErrors Done when: • returns errors |
| 🔷 SPARK-SMPL-B08 Master-data type/format/purpose queries (cacheable bundle) | 🟢 Low [XS] | Query | B01 | Intent — Return the sample type / format / purpose lookups (cached). Today — thin master-data loads Done when: • each returns its list; cached |

ℹ️  SPARK-SMPL-B01: Note — DGS Module Init (this PR only): Creates sample.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [03-schema.graphql](./03-schema.graphql).

🔍 Phase C — Search & Listing  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔷 SPARK-SMPL-C01 getSampleLocationByIds(ids) | 🟠 High [L] | Query Calls: search | B01 | Intent — Find each sample's latest physical location via its RFID tags. Today — batched samples → for each with rfidTagIds → (search) searchLatestRfidLocations({q: tagIds OR-joined}) → reduce to latest lastSeen → {id, locationDescription… Done when: • latest-location reduce correct • no tags → [] | ☐ latest reduce ☐ no-tags ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔷 SPARK-SMPL-C02 getSamplesByRfidTagIds(ids) | 🟡 Medium [M] | Query | B01 | Intent — Find samples by their RFID tag ids. Today — token → getSamplesByRfidTagIds Done when: • returns tag→sample pairs | — |

✏️ Phase D — Mutations  (7 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 SPARK-SMPL-D01 createSamplesV2 | 🟡 Medium [M] | Mutation Calls: relationship, attachment | B01 | Intent — Create samples (and link any attachment files). Today — createSamplesV2; if first new sample has files → (relationship) createSampleAttachmentRelationship + token + (attachment) bulkUpdateAttributes (stamp… Done when: • creates • file-relationship + attribute side-effects when files present |
| 🔶 SPARK-SMPL-D02 createSampleRoundV2 | 🟢 Low [XS] | Mutation | B01 | Intent — Create a new evaluation round on a sample. Today — token [sampleId, SAMPLE_EVALUTION] → createSampleRoundV2 Done when: • creates a round |
| 🔶 SPARK-SMPL-D03 updateSampleWorkspaceAssociation | 🟢 Low [XS] | Mutation | B01 | Intent — Add / remove a sample's workspace links. Today — token [sampleId, workspaceId] → updateSampleWorkspaceAssociation Done when: • associates sample to workspace |
| 🔶 SPARK-SMPL-D04 requestSampleExport | 🟢 Low [XS] | Mutation | B01 | Intent — Kick off a sample export. Today — requestSampleExport Done when: • returns request id |
| 🔶 SPARK-SMPL-D05 retrySampleNotificationError | 🟢 Low [XS] | Mutation Calls: notification | B01 | Intent — Retry one failed sample notification. Today — (notification) retrySampleNotificationError(failedMessageId) Done when: • retries one |
| 🔶 SPARK-SMPL-D06 retryAllSampleNotificationErrors | 🟢 Low [XS] | Mutation Calls: notification | B01 | Intent — Retry all failed sample notifications. Today — (notification) retryAllSampleNotificationErrors Done when: • retries all |
| 🔶 SPARK-SMPL-D07 bulkCloneFilesForEvaluate | 🟡 Medium [M] | Mutation Calls: attachment | B01 | Intent — Copy attachment files for sample evaluation. Today — token → Promise.all(attachmentIds.map(id => (attachment) cloneAttachmentV3({cloneReferences}, id))), flatten Done when: • clones each id |

⚙️ Phase E — Complex Operations  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 SPARK-SMPL-E01 updateSamplesV2 🔴🔬 Spike-gated on SPARK-SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation | SPARK-SPIKE-01, B01 | Intent — Update samples (the evaluation write). Today — token for all updateSamples[].id + SAMPLE_EVALUTION → updateSamplesV2 Done when: • bulk-updates samples (eval-scoped token) | ☐ update ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔴🔬 🔶 SPARK-SMPL-E02 bulkEvaluateSamples 🔴🔬 Spike-gated on SPARK-SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: attachment | SPARK-SPIKE-01, B01 | Intent — Apply evaluations to many samples and create new rounds. Today — delegates to bulkEvaluateSampleUtil(ctx, updateSamples, newSampleRounds) — applies evaluations and creates new sample rounds Done when: • evaluations + new rounds applied • partial-failure handling decided | ☐ evaluate ☐ new rounds ☐ partial ☐ Parity: DGS response matches spark-internal-graphql baseline |

🔗 Phase F — Federation & Stitching  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 SPARK-SMPL-F01 SampleV2 federated entity fetcher | 🟡 Medium [M] | Field Resolver | B01 | Intent — Let other subgraphs resolve a Sample by key. Today — @DgsEntityFetcher(name="SampleV2") resolving by id, so product (`Product Done when: • entity resolves by key • Product { samples { id } } cross-subgraph smoke test |
| 📄 SPARK-SMPL-F02 Deferred drift mutation decision | 🟢 Low [XS] | Schema | E02 | Intent — Decide the fate of superseded / drift sample mutations. Today — updateSampleEvaluations (no resolver — superseded by bulkEvaluateSamples), dropSamples/undropSamples (no resolver — run inside workspaceBusinessPartnerActionsV2) Done when: • decision + traffic survey |

🧪 Phase G — Field Resolvers & Tests  (7 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 SPARK-SMPL-G01 Users (created/updated/evaluated + evaluators + primary roles) | 🟡 Medium [M] | Field Resolver Calls: userAttributes, role | B01 | Intent — Resolve the created / updated / evaluated-by people and evaluator roles. Done when: • each resolves; system-user branch preserved | — |
| 🔸 SPARK-SMPL-G02 Prefix-gated parents + SampleAsset union | 🟠 High [L] | Field Resolver Calls: product, trim, colorArchroma, combination, fabric, artwork, material | B01 | Intent — Resolve a sample's parent (product / colour / fabric…) by id-prefix into the right type. Today — prefix-gated hydration — product (PID, product), colorArchroma (ARCCLR/TARARCCLR/REFARCCLR, colorArchroma), fabricSpecCombo (FSC, combination), fabricSpec (FAS… Done when: • each prefix routes to the right loader • asset union resolves • non-matching → null | ☐ each prefix ☐ union ☐ null |
| 🔸 SPARK-SMPL-G03 Partners (businessPartner/fabricSupplier/merchandiseVendors/brand/designPartnerId) | 🟡 Medium [M] | Field Resolver Calls: vmm, brand | B01 | Intent — Resolve the business / fabric / vendor / brand partner fields. Done when: • each resolves; empty → [] | — |
| 🔸 SPARK-SMPL-G04 workspace + sampleMeasurementSet + designCycle + clmPackage | 🟡 Medium [M] | Field Resolver Calls: workspaceV2, measurement, tag, tgtColorEvaluator | B01 | Intent — Resolve workspace, measurement, design-cycle and package fields. Done when: • each resolves; gates preserved | — |
| 🔸 SPARK-SMPL-G05 attachments + rfidLocationInfo + currentLocations | 🟡 Medium [M] | Field Resolver Calls: search | B01 | Intent — Resolve attachment and RFID-location fields. Done when: • attachments via elastic • rfid latest-location preserved | — |
| 🔸 SPARK-SMPL-G06 participants + sub-types (+ library color + department) | 🟡 Medium [M] | Field Resolver Calls: userGroup, vmm, color, ig | B01 | Intent — Resolve participant and related sub-type fields (library colour, department). Done when: • each resolves; Target-0 + system-user preserved | — |
| 📄 SPARK-SMPL-G07 Tests, parity harness, load test | 🟠 High [L] | Tests | B02, E02, G02 | Intent — Prove the sample subgraph matches the old gateway (incl. load test). Today — ≥80% unit coverage; parity harness (incl Done when: • unit ≥80% • parity green • load p95 parity • schema-diff intentional | ☐ Parity: DGS response matches spark-internal-graphql baseline ☐ Load: p95 latency is within spark-internal-graphql baseline ☐ contract |