Federated GraphQL Breakdown — Search

Target DGS: plm-elastic-search (separate)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 25 | T-Shirt Size L | Complexity 🔴 0 🟠 7 🟡 11 🟢 7 | Phases A, B, C, D, F, G |
| --- | --- | --- | --- |

Target DGS: plm-elastic-search (separate)   |   Generated: 2026-07-07

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

- We are moving the Search domain — the elastic-backed read layer that powers every search box, listing, suggestion, count and report across the PLM app — off the spark-internal-graphql gateway into its own `plm-elastic-search` DGS subgraph. - Search is the read hub: nearly every other domain calls it (the 🔴 search dependency you see throughout product/bom/measurement/packaging/productDetails/claims/watchlist/ workspace).

- It is breadth-dominated: ~48 mostly-thin elastic-wrapper queries + 1 mutation, but a large result-type surface (~50 types) and heavy enrichment field resolvers that re-hydrate hits from product, vmm, ig, tag, brand, workspace, user, attachment, fabric and color. - Low orchestration risk; the cost is surface area.

ACL note: a few proxy reads curry capability tokens; ACL is ignored in the DGS implementation — context only.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | ~48 | grouped into 10 search-family stories (Phase C) |
| Mutations | 1 | sendBulkCombinationUpdates |
| Result/value types | ~50 | the biggest single task (A02) |
| Field-resolver type blocks | ~12 | SearchAttachment, Material, combination/palette/watchlist/component, access/report/paging |
| External dependencies | ~14 keys | all cross-subgraph enrichment |
| Federation role | the program read hub | every domain calls it |
| Total stories | 25 | green-field; separate subgraph |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPARK-SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 SPARK-SRCH-A02 — Owned result types + inputs (the big surface) | SPARK-SPIKE-05 | Polymorphic Type Resolution |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| A | Foundation & Schema | 4 | 14–24d |
| B | Core Reads | 3 | 3–6d |
| C | Search & Listing (by family) | 10 | 24–40d |
| D | Mutations | 1 | 1–2d |
| F | Federation & ownership | 1 | 3–5d |
| G | Field Resolvers & Tests | 6 | 28–46d |
| Total | — | 25 | 73–123d (buffered) |

ℹ️  One engineer ≈ 15–25 sprints. Parallelizable by family after A.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~15–25 sprints | sequential |
| 2 engineers | ~9–15 sprints | families parallel after A |
| 3 engineers | ~6–10 sprints | A02/A04 → families → enrichment in parallel |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1–2 | A01–A04 | schema (type surface) + service port |
| 3 | B01–B03 + C01 | by-id/counts + attachments |
| 4 | C02/C03 | material + sample families |
| 5 | C04–C06 | team/template/product families |
| 6 | C07–C10 + D01 | combination/palette/misc/suggestions/reports + mutation |
| 7 | G01/G02 | the two heavy enrichment blocks |
| 8 | G03–G05 + F01 | remaining enrichment + gateway/ownership |
| 9 | G06 | tests, parity, conformance CI |

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

🧱 Phase A — Foundation & Type Resolvers  (4 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 📄 SPARK-SRCH-A01 Schema skeleton + DateTime/JSON scalars | 🟢 Low [XS] | Story | — | Intent — Stand up the search subgraph's schema shell and custom scalars. Today — green-field; schema translated from schemas/SPARK_Search.graphqls | — |
| 🔴🔬 📄 SPARK-SRCH-A02 Owned result types + inputs (the big surface) 🔴🔬 Spike-gated on SPARK-SPIKE-05 (Polymorphic Type Resolution) | 🟠 High [L] | Story | SPARK-SPIKE-05 | Intent — Define all the search result types and input shapes (the big surface). Today — all ~50 owned result/value types (SearchAttachment, Material, SearchCombination | — |
| 📄 SPARK-SRCH-A03 External stubs (platform + other DGS) | 🟡 Medium [M] | Story | — | Intent — Declare the external (other-DGS / platform) types search references. Today — @extends @external stubs for Product(sPaged), WorkspaceV2, Bom, SampleV2, Attachment | — |
| 🔷 SPARK-SRCH-A04 SearchService Kotlin port (plm-elastic-search) | 🟠 High [L] | Query | — | Intent — Port the ~80 elastic query-builder methods to Kotlin. Today — ~80 elastic query-builder methods on the plm-elastic-search base | — |

📖 Phase B — Core Reads  (3 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 SPARK-SRCH-B01 searchMaterialsById(id) | 🟢 Low [XS] | Query | — | Intent — Fetch materials by id. Today — getMaterialByIds |
| 🔷 SPARK-SRCH-B02 getElasticSamplesByIds(ids) | 🟢 Low [XS] | Query | — | Intent — Fetch elastic sample docs by ids. Today — getElasticSamplesByIds |
| 🔷 SPARK-SRCH-B03 getAttachmentsCounts + getSampleCount | 🟢 Low [XS] | Query | — | Intent — Count attachments / samples per resource. Today — getAttachmentsCounts(resourceIds); getSampleCount(resourceId) → [ResourceCount] |

🔍 Phase C — Search & Listing  (10 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔷 SPARK-SRCH-C01 searchAttachments | 🟡 Medium [M] | Query | — | Intent — Search attachments by query and filters. Today — (own elastic) searchAttachments({q,parentIds,relatedIds,partnerId,asset3D,proxyIds,page,size,sort}) | — |
| 🔷 SPARK-SRCH-C02 Material search family | 🟠 High [L] | Query | — | Intent — Search materials (incl. RGB colour and nested filters). Today — build elastic bodies (V2 = query+sort+options+searchArguments incl. - RGB color criteria + nested filters) → post → MaterialsPaged | — |
| 🔷 SPARK-SRCH-C03 Sample search family | 🟠 High [L] | Query | — | Intent — Search samples. Today — elastic sample queries + group-by aggregates | — |
| 🔷 SPARK-SRCH-C04 Team search family | 🟡 Medium [M] | Query | — | Intent — Search teams. | — |
| 🔷 SPARK-SRCH-C05 Template search family | 🟡 Medium [M] | Query | — | Intent — Search templates. | — |
| 🔷 SPARK-SRCH-C06 Product search family | 🟡 Medium [M] | Query | — | Intent — Search products. | — |
| 🔷 SPARK-SRCH-C07 searchCombinations + searchPalettes | 🟢 Low [XS] | Query | — | Intent — Search combinations and colour palettes. | — |
| 🔷 SPARK-SRCH-C08 searchWatchlist + searchClaimsByProxyIds + searchRfidLocations | 🟢 Low [XS] | Query | — | Intent — Search watchlists, proxied claims and RFID locations. | — |
| 🔷 SPARK-SRCH-C09 Suggestions family | 🟡 Medium [M] | Query | — | Intent — Provide type-ahead suggestions. | — |
| 🔷 SPARK-SRCH-C10 Reports | 🟡 Medium [M] | Query | — | Intent — Run the search-backed reports. | — |

✏️ Phase D — Mutations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 SPARK-SRCH-D01 sendBulkCombinationUpdates | 🟢 Low [XS] | Mutation | — | Intent — Queue bulk combination updates for indexing. Today — sendBulkCombinationUpdates(combinationUpdates) → {requestId} |

🔗 Phase F — Federation & Stitching  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 SPARK-SRCH-F01 Gateway composition + ownership reconciliation | 🟡 Medium [M] | Field Resolver | — | Intent — Wire search into the federated graph and settle who owns which fields. Today — add plm-elastic-search to the supergraph; reconcile drift/ownership: searchProducts |

🧪 Phase G — Field Resolvers & Tests  (6 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔷 SPARK-SRCH-G01 SearchAttachment enrichment | 🟠 High [L] | Query | — | Intent — Enrich search-attachment results with related data. | — |
| 🔸 SPARK-SRCH-G02 Material enrichment (incl. colorLinks) | 🟠 High [L] | Field Resolver | — | Intent — Enrich material results (incl. colour links). | — |
| 🔷 SPARK-SRCH-G03 SearchCombination + SearchPalette field resolvers | 🟡 Medium [M] | Query | — | Intent — Resolve combination / palette result fields. | — |
| 🔷 SPARK-SRCH-G04 SearchWatchlist + SearchComponent field resolvers | 🟡 Medium [M] | Query | — | Intent — Resolve watchlist / component result fields. | — |
| 🔸 SPARK-SRCH-G05 Access + report-group + paging field resolvers | 🟡 Medium [M] | Field Resolver | — | Intent — Resolve access, report-group and paging fields. | — |
| 🔸 SPARK-SRCH-G06 Tests, parity harness, schema-conformance CI | 🟠 High [L] | Field Resolver | — | Intent — Prove the search subgraph matches the old gateway. Today — ≥80% unit coverage; parity harness across the search families + enriched result types; **schema- | — |