Federated GraphQL Breakdown — Workspace

Target DGS: plm-workspace (separate)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 28 | T-Shirt Size XL | Complexity 🔴 3 🟠 3 🟡 13 🟢 9 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-workspace (separate)   |   Generated: 2026-07-07

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

- We are moving the Workspace domain — the seasonal/working containers that group products, samples, teams, partners, attachments and discussions — off the spark-internal-graphql gateway into its own `plm-workspace` DGS subgraph. - Workspace is a hub: nearly every product-family domain references a WorkspaceV2, and workspace itself reaches into product, search, discussion, sample, combination, attachment, relationship and access-control.

- It is large and high-risk: 8 queries, 10 mutations (+2 schema-drift wrappers), ~25 field resolvers on a 1,060-line resolver. - The cost and risk concentrate in three places: the `workspaceBusinessPartnerActionsV2` drop/undrop dispatcher (5 cases, manual compensation, and un-awaited promise chains to fix), and the two heavy field resolvers `attachmentsWithMetaData` and `counts` (the workspace product dashboard).

ACL note: ACL authorization is ignored in the DGS implementation; but the drop/undrop resource bookkeeping (which resources get dropped/undropped) IS real build work — it is data maintenance, not auth.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 8 | 2 paged elastic; product/search-backed lookups |
| Mutations | 10 (+2 deferred) | incl. the partner-action dispatcher + 3 exports |
| Field-resolver type blocks | ~3 | WorkspaceV2 (~22), WorkspaceDepartmentV2, paged |
| External dependencies | 14 keys (all cross-subgraph) | search/product/attachment 🔴 |
| Federation role | provides WorkspaceV2 entity | every product-family domain references it |
| Total stories | 32 | green-field; separate subgraph |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPARK-SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 SPARK-WS-D04 — addResourcesToWorkspaceV2 | SPARK-SPIKE-06 | Cross-Domain Association / Hydration |
| 🔴🔬 SPARK-WS-E01 — workspaceBusinessPartnerActionsV2 (5-case drop/undrop dispatcher) | SPARK-SPIKE-03 | Partner Drop/Undrop + Ownership |
| 🔴🔬 SPARK-WS-G04 — products + productsCount + combinations + sampleReport (cross-subgraph) | SPARK-SPIKE-06 | Cross-Domain Association / Hydration |
| 🔴🔬 SPARK-WS-G05 — partners (businessPartners/droppedPartners/notRemovablePartnerIds/unDroppablePartners) | SPARK-SPIKE-04 | Not-Removable / Undroppable Partners |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 6 | 8–14d |
| C | Search & Listing | 2 | 5–9d |
| D | Mutations (simple) | 9 | 16–27d |
| E | Complex (partner-action dispatcher) | 1 | 8–13d |
| F | Federation & decisions | 2 | 4–7d |
| G | Field Resolvers & Tests | 8 | 34–56d |
| Total | — | 32 | 75–126d (buffered) |

ℹ️  One engineer ≈ 15–26 sprints. Heavily parallelizable after B01; 2–3 engineers recommended.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~17–29 sprints | sequential — not recommended |
| 2 engineers | ~10–17 sprints | B/C/D parallel after B01 |
| 3 engineers | ~7–11 sprints | critical path A → E01 → G01/G02 → G08 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1–2 | B01 (DGS module init + service wiring + first resolver) | schema, service port, reads |
| 3 | C01/C02 + D06–D09 | paged search + teams + exports |
| 4 | D01–D05 | create/update/change + resource add/remove |
| 5–6 | E01 | partner-action dispatcher (focused) |
| 7–8 | G01–G04 | the heavy field resolvers (X-Large) |
| 9 | G05–G07 | partners/hierarchy/users/computed |
| 10 | F01/F02 + G08 | entity fetcher + drift decision + tests |

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (6 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 SPARK-WS-B01 getWorkspaceV2(id, metric) | 🟢 Low [XS] | Query | — | Intent — Fetch one workspace by id. Today — getWorkspaceByIdV2 GET … Done when: • returns workspace; miss→null |
| 🔷 SPARK-WS-B02 getWorkspacesByIdsV2(ids) | 🟢 Low [XS] | Query | B01 | Intent — Fetch several workspaces by ids. Today — token → getWorkspacesByIdsV2(jwt) Done when: • returns list for ids |
| 🔷 SPARK-WS-B03 getWorkspaceTypeCount | 🟢 Low [XS] | Query Calls: search | B01 | Intent — Count workspaces by type. Today — (search) getWorkspaceTypeCount({}) Done when: • returns products/combinations/research counts |
| 🔷 SPARK-WS-B04 findWorkspaceProductAndSampleIds(workspaceId, q, filter) | 🟡 Medium [M] | Query Calls: product | B01 | Intent — List the product and sample ids in a workspace. Today — (product) getWorkspaceProducts({workspaceId, filter, q, page:0, size:10000}) → map {id:humanId, sampleIds:[sample.humanId]} Done when: • maps products + their sample human ids |
| 🔷 SPARK-WS-B05 findWorkspaceClaims(workspaceId, q, filter) | 🟢 Low [XS] | Query Calls: search | B01 | Intent — List a workspace's claims (via elastic). Today — (search) getClaimsElastic({ q:"workspaceContext:{workspaceId}", page:0, size:10000 }) → .content Done when: • elastic query exact |
| 🔷 SPARK-WS-B06 getWorkspacePackagingAttachments(workspaceId, bpId) | 🟡 Medium [M] | Query Calls: search | B01 | Intent — Find a workspace's packaging attachments by tag. Today — env WORKSPACE_PACKAGING_TAG_ID (throws if unset) → (search) searchAttachments({ q:"tags:{tag}[ AND security.bps:{bpId}]", relatedIds:[workspaceId], size:500… Done when: • throws if tag config missing • bp filter appended when present |

ℹ️  SPARK-WS-B01: Note — DGS Module Init (this PR only): Creates workspace.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [03-schema.graphql](./03-schema.graphql).

🔍 Phase C — Search & Listing  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 SPARK-WS-C01 getWorkspacesPagedV2(...) | 🟡 Medium [M] | Query Calls: search | B01 | Intent — List workspaces with paging / filters (V2). Today — (search) getWorkspacesPagedV2 — array params CSV-joined (except page/size); omitBy drops empties Done when: • array→CSV; empties omitted |
| 🔷 SPARK-WS-C02 getWorkspacesPagedV3(...) | 🟡 Medium [M] | Query Calls: search | B01 | Intent — List workspaces with paging / filters (V3). Today — (search) getWorkspacesPagedV3 — CSV-join except q/designPartnerIds; omitBy Done when: • CSV-join rules preserved (q/designPartnerIds passthrough) |

✏️ Phase D — Mutations  (9 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 SPARK-WS-D01 createWorkspaceV2 | 🟡 Medium [M] | Mutation | B01 | Intent — Create a workspace (rejects duplicates). Today — default workspaceType=103; POST … (validateUnique). Throw GraphQLError('Workspace already exists') if the response message starts with the dup text Done when: • creates; default type • 2. dup → GraphQLError |
| 🔶 SPARK-WS-D02 updateWorkspaceV2 | 🟡 Medium [M] | Mutation | B01 | Intent — Edit a workspace (rejects duplicates). Today — token for workspace.id; default type 103; PUT … → same dup-check throw Done when: • updates; dup→throw |
| 🔶 SPARK-WS-D03 changeWorkspace | 🟡 Medium [M] | Mutation | B01 | Intent — Move resources from one workspace to another. Today — token for Attr-{newWs}-resources → PUT … with {newWorkspaceId, oldWorkspaceId, productHumanId, teams, removeWorkspaceOnly}. Throw on validationErrors/message Done when: • moves product between workspaces • error→throw |
| 🔴🔬 🔶 SPARK-WS-D04 addResourcesToWorkspaceV2 🔴🔬 Spike-gated on SPARK-SPIKE-06 (Cross-Domain Association / Hydration) | 🟡 Medium [M] | Mutation Calls: product | SPARK-SPIKE-06, B01 | Intent — Add products / samples to a workspace. Today — token; if single product → (product) read Product.workspaces + updateViewToggle (init workspace attrs; firstWorkspace adds designCycle/setDates); POST … Done when: • adds resources • single-product init side-effect preserved |
| 🔶 SPARK-WS-D05 removeWorkspaceResourcesV2 | 🟡 Medium [M] | Mutation Calls: product | B01 | Intent — Remove resources from a workspace. Today — token; if single product → (product) deletePartnerWorkspaceStatuses cleanup; DELETE … Done when: • removes resources • single-product status cleanup |
| 🔶 SPARK-WS-D06 addTeamsToWorkspaceV3 | 🟢 Low [XS] | Mutation | B01 | Intent — Add teams to a workspace. Today — token → POST … Done when: • adds teams |
| 🔶 SPARK-WS-D07 exportWorkspace | 🟢 Low [XS] | Mutation Calls: search | B01 | Intent — Kick off a workspace export. Today — (search) requestBulkAttachmentExport({parentResourceId, exportType, includedAttachmentIds, includeOnlyPrimaryThumbnails}, {q, filter}) Done when: • returns receipt |
| 🔶 SPARK-WS-D08 exportWorkspaceExcel | 🟢 Low [XS] | Mutation Calls: exportHub | B01 | Intent — Export a workspace to Excel. Today — (exportHub) exportWorkspaceExcel(workspaceExportOptions) Done when: • returns receipt |
| 🔶 SPARK-WS-D09 exportPackagingFiles | 🟢 Low [XS] | Mutation Calls: search | B01 | Intent — Export a workspace's packaging files. Today — (search) requestPackagingExport({workspaceId, workspaceDescription, exportContext, exportType}, {q, filter}) Done when: • returns receipt |

⚙️ Phase E — Complex Operations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 SPARK-WS-E01 workspaceBusinessPartnerActionsV2 (5-case drop/undrop dispatcher) 🔴🔬 Spike-gated on SPARK-SPIKE-03 (Partner Drop/Undrop + Ownership) | 🔴 Very High [XL] | Mutation Calls: relationship, discussion, sampleV2, favorite | SPARK-SPIKE-03, B01 | Intent — Drop / undrop a partner (or remove team/partner) across a workspace — a 5-case orchestrated write. Today — ~310-line switch — REMOVE_TEAM, REMOVE_PARTNER, DROP_PARTNER, - UNDO_DROP_PARTNER, DROP_UNDROP_PARTNER. - Builds a relationship tree (relationship), ACL-filters… Done when: • chains awaited; compensation on ACL failure • design-partner skips samples | ☐ REMOVE_TEAM ☐ REMOVE_PARTNER ☐ DROP ☐ UNDO_DROP ☐ DROP_UNDROP ☐ partial-failure ☐ Parity: DGS response matches spark-internal-graphql baseline |

🔗 Phase F — Federation & Stitching  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 SPARK-WS-F01 WorkspaceV2 federated entity fetcher | 🟡 Medium [M] | Field Resolver | B01 | Intent — Let other subgraphs resolve a Workspace by key. Today — @DgsEntityFetcher(name="WorkspaceV2") resolving by id, so the product-family subgraphs Done when: • entity resolves by key from _entities • a cross-subgraph Product { workspaces { id description } } smoke test passes |
| 📄 SPARK-WS-F02 Deferred drop/undrop wrapper decision (drift mutations) | 🟢 Low [XS] | Schema | E01 | Intent — Decide the fate of the drop/undrop drift wrappers. Today — dropWorkspaceBusinessPartnerV2/unDropWorkspaceBusinessPartnerV2 are schema-drift wrappers; traffic routes through workspaceBusinessPartnerActionsV2 Done when: • traffic survey complete • decision implemented |

🧪 Phase G — Field Resolvers & Tests  (8 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 SPARK-WS-G01 WorkspaceV2.attachmentsWithMetaData | 🔴 Very High [XL] | Field Resolver Calls: relationship, attachment, discussion | B01 | Intent — Resolve a workspace's attachments, enriched with discussion metadata. Today — (relationship) tree (attachments_v3/discussions/discussionThreads) → - (attachment) getAttachmentsV3 → (discussion) batch discussions/threads → merge → order by… Done when: • parity for mixed attachment/discussion/thread • ordering + draft filter preserved | ☐ merge ☐ ordering ☐ draft filter ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔸 SPARK-WS-G02 WorkspaceV2.counts (product dashboard rollup) | 🔴 Very High [XL] | Field Resolver Calls: search, product, discussion | B01 | Intent — Roll up a workspace's product / sample / discussion counts for the dashboard. Today — (search) getFilteredProductsWithSummary → (product) getPage → - (discussion) product discussion counts + (search) sample counts + sample-discussion roll-up into… Done when: • parity for the full rollup incl. sample-discussion increment • empty → zeros | ☐ rollup ☐ sample-discussion ☐ empty ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔸 SPARK-WS-G03 WorkspaceV2.attachmentsV3 | 🟠 High [L] | Field Resolver Calls: relationship, attachment | B01 | Intent — Resolve a workspace's attachments (with / without per-partner counts). Today — with args → getProductOrWorkSpaceAttachments (per-BP counts via initialCountsByBp); without args → relationship tree → resolveRelationIds → filter Done when: • both arg/no-arg paths • per-BP counts | ☐ with args ☐ no args ☐ counts |
| 🔴🔬 🔸 SPARK-WS-G04 products + productsCount + combinations + sampleReport (cross-subgraph) 🔴🔬 Spike-gated on SPARK-SPIKE-06 (Cross-Domain Association / Hydration) | 🟠 High [L] | Field Resolver Calls: product, search, combination, sampleV2 | SPARK-SPIKE-06, B01 | Intent — Resolve a workspace's cross-subgraph product / combination fields. Today — products → (product) getProducts(resourceType:'workspaces', resourceId, include*: true); productsCount → (product) getPage totalElements; combinations → (search)… Done when: • each resolves; include flags forwarded • sampleReport round counts correct | ☐ products ☐ count ☐ combinations ☐ sampleReport |
| 🔴🔬 🔸 SPARK-WS-G05 partners (businessPartners/droppedPartners/notRemovablePartnerIds/unDroppablePartners) 🔴🔬 Spike-gated on SPARK-SPIKE-04 (Not-Removable / Undroppable Partners) | 🟡 Medium [M] | Field Resolver Calls: vmm | SPARK-SPIKE-04, B01 | Intent — Resolve a workspace's business / dropped / not-removable partner lists. Done when: • each resolves; unDroppable gated on isDesignPartner | — |
| 🔸 SPARK-WS-G06 hierarchy/tags (divisions/brands/clazzes/designCycles/tags + WorkspaceDepartmentV2) | 🟡 Medium [M] | Field Resolver Calls: ig, brand, tag | B01 | Intent — Resolve a workspace's division / brand / class / design-cycle / tag fields. Done when: • each resolves; empty → [] | — |
| 🔸 SPARK-WS-G07 users/computed (createdBy/updatedBy/status/id + discussionsV2/teams + paged) | 🟡 Medium [M] | Field Resolver Calls: userAttributes, search | B01 | Intent — Resolve a workspace's people, status and discussion / team fields. Done when: • computed mappings correct • users/discussions/teams resolve | — |
| 📄 SPARK-WS-G08 Tests, parity harness, load test | 🟠 High [L] | Tests | B01, E01, G01, G02 | Intent — Prove the workspace subgraph matches the old gateway (incl. load test). Today — ≥80% unit coverage; parity harness (incl Done when: • unit ≥80% • parity green • load p95 parity • schema-diff intentional | ☐ Parity: DGS response matches spark-internal-graphql baseline ☐ Load: p95 latency is within spark-internal-graphql baseline ☐ contract |