Federated GraphQL Breakdown — Claims

Target DGS: spark-claims (separate)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 20 | T-Shirt Size L | Complexity 🔴 0 🟠 2 🟡 9 🟢 9 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: spark-claims (separate)   |   Generated: 2026-07-16

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

We are moving the Claims domain — a product's marketing/technical claims (claim details, guest-facing copy, substantiation, per-partner access, exports) — off the spark-internal-graphql gateway into its own `claims` DGS subgraph. Unlike BOM/Measurement/ProductDetails, claims is not part of the plm-product monorepo, so its links to Product, search, workspace, user-profile and VMM are all cross-subgraph (federation / gateway stitch), and it contributes the Product.claims field and the TechPack ResourcesCount.claims count back to plm-product.

It is mid-sized and mid-risk: 7 queries, 6 mutations, 17 field resolvers on a 164-line resolver, with no polymorphism. The one genuinely harder piece is `updateClaim`, a multi-step write that uses the proxy/external ACL path plus workspace association, with no rollback today.

ACL note: the current code obtains capability tokens via ACL (including the proxy variant for update); Per the program-level working decision, the DGS layer carries no ACL plumbing story — each domain service performs its own access control; scenario ADRs (complexStories/*/02-adr-noacl-*.md) record the assumption's impact and ratify with the global decision. ACL is noted in stories for context only.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 7 | 2 cacheable master-data; 1 elastic (🔴 search) |
| Mutations | 6 | 5 simple + updateClaim (proxy-ACL multi-step) |
| Field-resolver type blocks | 4 | Claims (11), ParentDetails (3), substantiate (1), claimDetails (1) |
| External dependencies | 6 keys (1 🔴 · 3 🟡 · 2 🔵) | search 🔴; product/user-profile/workspace 🟡 |
| Federation contributions | 2 (Product.claims, ResourcesCount.claims) | BLOCKED-BY product |
| Total stories | 20 | green-field; separate subgraph |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 CLAIM-BE-E-01 — updateClaim (proxy ACL + multi-step write) | SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 5 | 5–9d |
| C | Search & Listing | 2 | 4–7d |
| D | Mutations (simple) | 5 | 7–12d |
| E | Complex (updateClaim) | 1 | 4–7d |
| F | Federation Contributions | 2 | 4–7d (BLOCKED-BY product) |
| G | Field Resolvers & Tests | 5 | 12–20d |
| Total | — | 20 | 36–62d (buffered) |

ℹ️  One engineer ≈ 8–13 sprints.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~9–15 sprints | sequential |
| 2 engineers | ~5–8 sprints | reads + mutations parallel after B-01 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1 | B-01 (DGS module init + service wiring + first resolver) | schema, service port, reads |
| 2 | C-01/C-02 + D-01–D-05 | search + simple mutations |
| 3 | E-01 + G-01/G-02 | updateClaim + ACL/partner field resolvers |
| 4 | G-03/G-04 + G-05 | parent/elastic + misc fields + tests |
| post-launch | F-01, F-02 | federation contributions (unblocked by product) |

Recommended Implementation Order

Derived from each story's Depends On edges (plus the module-init scaffold as the implicit first step). A story appears in the earliest step where everything it depends on is already done; stories in the same step are independent of each other and parallelize across engineers.

🔬 spike gates and ⛔ cross-subgraph blocks are entry criteria, not ordering edges — a gated story slides later without reshuffling the map.

| Step | Stories (parallel set) | Entry gates in this step |
| --- | --- | --- |
| 1 | 🟢 B-01 | — |
| 2 | 🟢 B-02, 🟢 B-03, 🟢 B-04, 🟢 B-05, 🟡 C-01, 🟡 C-02, 🟡 D-01, 🟡 D-02, 🟢 D-03, 🟢 D-04, 🟢 D-05, 🟠 E-01, 🟡 F-01, 🟢 F-02, 🟡 G-01, 🟡 G-02, 🟠 G-03, 🟡 G-04 | E-01 → 🔬 SPIKE-01<br>F-01 → ⛔ BLOCKED-BY product<br>F-02 → ⛔ BLOCKED-BY product |
| 3 | 🟡 G-05 | — |

Critical path: B-01 → G-03 → G-05 — 3 sequential stories; everything else hangs off this chain in parallel.

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 CLAIM-BE-B-01 getClaims(parentHumanId, claimHumanIds, partnerIds) | 🟢 Low [XS] | Query | — | Intent — List claims for a product / set of partners. Today — claim.getClaims GET … (filtered) → camelCase. No ACL token Done when: • filters by the 3 args |
| 🔷 CLAIM-BE-B-02 getClaimByIds(claimHumanIds) | 🟢 Low [XS] | Query | B-01 | Intent — Fetch specific claims by their ids. Today — token → GET … Done when: • returns claims for ids |
| 🔷 CLAIM-BE-B-03 getCommunicationChannels (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the communication-channel lookup list (cached). Today — GET … Done when: • returns channels; cached |
| 🔷 CLAIM-BE-B-04 getAllClaimsAbout (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the 'claims about' lookup list (cached). Today — GET … Done when: • returns list; cached |
| 🔷 CLAIM-BE-B-05 getClaimExports | 🟢 Low [XS] | Query | B-01 | Intent — List the claim export jobs. Today — GET … Done when: • returns export records |

ℹ️  CLAIM-BE-B-01: Note — DGS Module Init (this PR only): Creates claims.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [be-03-schema.graphql](./be-03-schema.graphql).

🔍 Phase C — Search & Listing  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 CLAIM-BE-C-01 searchGuestFacing(queryParam) | 🟡 Medium [M] | Query | B-01 | Intent — Search the guest-facing (external-partner) claims view. Today — GET … → camelCase Done when: • query-string built from queryParam |
| 🔷 CLAIM-BE-C-02 getClaimsElastic(parentHumanId) | 🟡 Medium [M] | Query Calls: search | B-01 | Intent — Search a product's claims via elastic. Today — (search) search.getClaimsElastic. EXT: search Done when: • parentId: elastic query built |

✏️ Phase D — Mutations  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 CLAIM-BE-D-01 createClaim | 🟡 Medium [M] | Mutation | B-01 | Intent — Create a new claim. Today — POST … (snake_case). If validationErrors/message → throw Done when: • creates claim(s) • validation error → exception |
| 🔶 CLAIM-BE-D-02 bulkUpdateClaim | 🟡 Medium [M] | Mutation | B-01 | Intent — Update many claims in one call. Today — PUT … Error contract: result is array → return; status_code>400 → throw; else throw "unhandled". Latent: source snake-cases the response — fix to camelCase Done when: • array result returned (camelCase) • error status → exception |
| 🔶 CLAIM-BE-D-03 requestClaimExport | 🟢 Low [XS] | Mutation | B-01 | Intent — Kick off a claim export job. Today — POST … → response.request_id Done when: • returns the request id |
| 🔶 CLAIM-BE-D-04 lockClaim | 🟢 Low [XS] | Mutation | B-01 | Intent — Lock a claim from edits. Today — token → PUT … Done when: • locks the claim |
| 🔶 CLAIM-BE-D-05 unlockClaim | 🟢 Low [XS] | Mutation | B-01 | Intent — Unlock a claim for edits. Today — token → PUT … Done when: • unlocks the claim |

⚙️ Phase E — Complex Operations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 CLAIM-BE-E-01 updateClaim (proxy ACL + multi-step write) 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: workspaceV2 | SPIKE-01, B-01 | Intent — Edit a claim — a multi-step write (permissions + workspace + body) that has no rollback today. Today — getUserPermissionsJWTByProxy({id:humanId, proxyIds:[parentId], basePermissions:true}) (proxy/external ACL path — context only); 2) if workspaceContext.{add,remove}… Done when: • workspace assoc runs when present • body update + throw-on-error • partial-failure strategy | ☐ body-only ☐ +workspace ☐ validation-error→throw ☐ partial-failure ☐ Parity: DGS response matches spark-internal-graphql baseline |

🔗 Phase F — Federation & Stitching  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 CLAIM-BE-F-01 Product.claims (federation contribution) | 🟡 Medium [M] | Field Resolver | B-01 | Intent — Expose a product's claims on the Product type (federation contribution). Today — extend type Product @key(fields:"id") { claims(partnerIds:[String], includeClaims:Boolean): [Claims] } with a @DgsEntityFetcher; the claims subgraph fills `Product Done when: • Product.claims resolves via federation • parity vs the current in-gateway resolver |
| 🔸 CLAIM-BE-F-02 ResourcesCount.claims (TechPack — claims side of PRODUCT-BE-F-05) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Contribute the claims count to the product TechPack rollup. Today — extend type ResourcesCount @key(fields:"productId partnerId") { claims: [ID] } with a Done when: • field resolves on the federated ResourcesCount; parity vs facade |

🧪 Phase G — Field Resolvers & Tests  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 CLAIM-BE-G-01 access + currentUserPermissions + participantDetails | 🟡 Medium [M] | Field Resolver Calls: userGroup | B-01 | Intent — Resolve a claim's access / permission / participant fields. Done when: • each resolves; null-safe | — |
| 🔸 CLAIM-BE-G-02 createdBy + updatedBy + businessPartner + designPartner | 🟡 Medium [M] | Field Resolver Calls: userAttributes, vmm | B-01 | Intent — Resolve the people and partner fields on a claim. Today — users via user-profile; businessPartner 3-way fallback (partnerId \¦\¦ {bpId:0,bpName:'Target'} when no dpPartnerId \¦\¦ dpPartnerId); designPartner dpPartnerId or… Done when: • all 3 BP branches correct (incl. bpId:0 Target) • null id → null user | — |
| 🔸 CLAIM-BE-G-03 product + parentDetails (otherClaimBps / systemTeams / droppedPartnerIds) | 🟠 High [L] | Field Resolver Calls: product, search | B-01 | Intent — Resolve the parent product and its related-partner context on a claim. Today — product (product, only if parentId starts 'PID'); parentDetails → - product.getByID(parentId) (the product feeds ParentDetails): otherClaimBps (search getClaimsElastic… Done when: • product null when not PID* • otherClaimBps/systemTeams elastic queries match source; empty-BP → {content:[]} | ☐ product branch ☐ otherClaimBps ☐ systemTeams ☐ empty BPs |
| 🔸 CLAIM-BE-G-04 workspaces + ClaimSubstantiate.substantiatedBy + ClaimDetails.claimName | 🟡 Medium [M] | Field Resolver Calls: workspaceV2, userAttributes | B-01 | Intent — Resolve workspace links and a few computed claim fields. Done when: • each resolves; workspaces null when empty • claimName mirrors guestFacingClaim | — |
| 📄 CLAIM-BE-G-05 Tests, parity harness | 🟡 Medium [M] | Tests | B-01, E-01, G-02, G-03 | Intent — Prove the claims subgraph matches the old gateway. Today — ≥80% unit coverage; parity fixtures (incl Done when: • unit ≥80% • parity green • schema-diff intentional | — |