Federated GraphQL Breakdown — Product Details

Target DGS: plm-product (co-located)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 13 | T-Shirt Size M | Complexity 🔴 0 🟠 1 🟡 7 🟢 5 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-product (co-located)   |   Generated: 2026-07-16

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

We are moving the ProductDetails domain — the product's "construction" sets (build/assembly detail rows, their attachments, and per-partner access) — off the spark-internal-graphql gateway into the `plm-product` DGS. It is mid-sized and mid-low risk: 2 queries, 6 mutations, 12 field resolvers on a 129-line resolver, with no polymorphism. (In the backend this domain is called construction — construction/v1; the GraphQL names stay productDetails.)

The one genuinely harder piece is `updateProductDetailsSet`, a multi-step write — workspace associations, then bulk-archive removed attachments, then the body — with no rollback today.

ACL note: the current code obtains per-resource capability tokens via ACL; Per the program-level working decision, the DGS layer carries no ACL plumbing story — each domain service performs its own access control; scenario ADRs (complexStories/*/02-adr-noacl-*.md) record the assumption's impact and ratify with the global decision. ACL is noted in stories for context only.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 2 | one by-ids (internal), one elastic (🔴 search) |
| Mutations | 6 | 5 simple + updateProductDetailsSet (multi-step) |
| Field-resolver type blocks | 3 | ProductDetails (10), item (2), category (1) |
| External dependencies | 6 keys (2 🔴 · 2 🟡 · 2 🔵) | search/attachment 🔴 |
| Federation contributions | 1 (Product) | internal (co-located) |
| Total stories | 13 | green-field |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 PDTL-BE-E-01 — updateProductDetailsSet (multi-step write) | SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 1 | 1–2d |
| C | Search & Listing | 1 | 2–4d |
| D | Mutations (simple) | 5 | 7–12d |
| E | Complex (updateProductDetailsSet) | 1 | 4–7d |
| F | Federation (Product, internal) | 1 | 1–2d |
| G | Field Resolvers & Tests | 4 | 9–15d |
| Total | — | 13 | 24–42d (buffered) |

ℹ️  One engineer ≈ 5–9 sprints.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~6–11 sprints | sequential |
| 2 engineers | ~4–6 sprints | reads + mutations parallel after B-01 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1 | B-01 (DGS module init + service wiring + first resolver) | schema, service port, reads |
| 2 | D-01–D-05 | simple mutations |
| 3 | E-01 + F-01 | multi-step write + Product field |
| 4 | G-01–G-03 | field resolvers |
| 5 | G-04 | tests & parity |

Recommended Implementation Order

Derived from each story's Depends On edges (plus the module-init scaffold as the implicit first step). A story appears in the earliest step where everything it depends on is already done; stories in the same step are independent of each other and parallelize across engineers.

🔬 spike gates and ⛔ cross-subgraph blocks are entry criteria, not ordering edges — a gated story slides later without reshuffling the map.

| Step | Stories (parallel set) | Entry gates in this step |
| --- | --- | --- |
| 1 | 🟢 B-01 | — |
| 2 | 🟡 C-01, 🟡 D-01, 🟢 D-02, 🟢 D-03, 🟡 D-04, 🟢 D-05, 🟠 E-01, 🟢 F-01, 🟡 G-01, 🟡 G-02, 🟡 G-03 | E-01 → 🔬 SPIKE-01 |
| 3 | 🟡 G-04 | — |

Critical path: B-01 → E-01 → G-04 — 3 sequential stories; everything else hangs off this chain in parallel.

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 PDTL-BE-B-01 getProductDetailsById(ids) | 🟢 Low [XS] | Query | — | Intent — Fetch product-detail (construction) sets by id. Today — token for ids → GET construction/v1?ids={csv} → camelCase Done when: • returns list for ids; empty → [] |

ℹ️  PDTL-BE-B-01: Note — DGS Module Init (this PR only): Creates productDetails.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [be-03-schema.graphql](./be-03-schema.graphql).

🔍 Phase C — Search & Listing  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 PDTL-BE-C-01 getProductDetailsElastic(resourceId) | 🟡 Medium [M] | Query Calls: search | B-01 | Intent — Search a product's product-detail sets via elastic. Today — (search) search.getProductDetailsElastic → paged. - EXT: search Done when: • parentId: elastic query built • paged shape returned |

✏️ Phase D — Mutations  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 PDTL-BE-D-01 createProductDetailsSet | 🟡 Medium [M] | Mutation | B-01 | Intent — Create a product-detail set. Today — token for literal capability → POST construction/v1 (snake_case). If response has validationErrors or message → throw Done when: • creates set • validation error → exception (not a partial object) |
| 🔶 PDTL-BE-D-02 updateProductDetailAccess | 🟢 Low [XS] | Mutation | B-01 | Intent — Change who can access a product-detail set. Today — map managePermissionsRequest[].resourceId → token → PUT construction/v1/manage-permissions (primeKey=humanId) Done when: • updates partner access for each resource |
| 🔶 PDTL-BE-D-03 productDetailLockUnlock | 🟢 Low [XS] | Mutation | B-01 | Intent — Lock or unlock a product-detail set. Today — token for [constructionSetId] → PUT construction/v1/{id}/{lock\¦unlock} Done when: • isLock=true→lock path, false→unlock path |
| 🔶 PDTL-BE-D-04 cloneFilesForProductDetails | 🟡 Medium [M] | Mutation Calls: attachment | B-01 | Intent — Copy attachment files for product details. Today — token → Promise.all(attachmentIds.map((id,i) => (attachment) cloneAttachmentV3({cloneReferences:[cloneReference[i]]}, id))), stamp parentResource=id, flatten. No… Done when: • clones each id with its paired cloneReference • parentResource stamped |
| 🔶 PDTL-BE-D-05 updateProductDetailComponentStatus | 🟢 Low [XS] | Mutation | B-01 | Intent — Update component status on product-detail sets. Today — PUT construction/v1/component_status_update; wraps result as {content}. No JWT — confirm backend-enforced Done when: • updates statuses; result wrapped as {content} • no-token behaviour documented |

⚙️ Phase E — Complex Operations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 PDTL-BE-E-01 updateProductDetailsSet (multi-step write) 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: attachment, workspaceV2 | SPIKE-01, B-01 | Intent — Edit a product-detail set — a multi-step write (workspace + body) with no rollback today. Today — if workspaceContext.{add,remove}Workspaces non-empty → workspaceAssociationHelper(PRODUCT_DETAIL, id, add, remove) (throws on error); 2) null workspaceContext; 3) if… Done when: • all 4 steps in order • partial-failure strategy implemented • workspace assoc throws propagate | ☐ full path ☐ workspace-only ☐ attachment-archive ☐ partial-failure ☐ Parity: DGS response matches spark-internal-graphql baseline |

🔗 Phase F — Federation & Stitching  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 PDTL-BE-F-01 Product.productDetails (internal, same subgraph) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Expose a product's product-details on the Product type (same subgraph). Today — Product exposes productDetails resolved from the co-located ProductDetails service Done when: • Product.productDetails resolves in-process; no gateway hop |

🧪 Phase G — Field Resolvers & Tests  (4 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 PDTL-BE-G-01 access + currentUserPermissions + participantDetails | 🟡 Medium [M] | Field Resolver Calls: userGroup | B-01 | Intent — Resolve access / permission / participant fields. Today — access → accessControl.getPermissions([humanId\¦\¦id])[0]; currentUserPermissions → getUserAccessUnencoded(humanId\¦\¦id)[0]; participantDetails → getUserGroup(humanId) Done when: • each field resolves; null-safe on empty |
| 🔸 PDTL-BE-G-02 product + createdBy + updatedBy + businessPartners + workspaces | 🟡 Medium [M] | Field Resolver Calls: userAttributes, workspaceV2, vmm | B-01 | Intent — Resolve the product, people, partner and workspace fields. Today — product (internal, only if parentId starts 'PID'), createdBy/updatedBy (user-profile), businessPartners (vmm loadBpsWithType), workspaces (workspaceV2 by ids) Done when: • each resolves; product null when parentId not PID* • null id → null user |
| 🔸 PDTL-BE-G-03 attachment + item attachment/constructionSetAttachments + category subCategories | 🟡 Medium [M] | Field Resolver Calls: search | B-01 | Intent — Resolve attachment and category fields on product details. Today — ProductDetails.attachment → (search) searchAttachments([humanId\¦\¦id]), find - relatedResources.length<=2; ProductDetailsItem.attachment →… Done when: • each field resolves to the right source • attachment length-≤2 filter preserved |
| 📄 PDTL-BE-G-04 Tests, parity harness | 🟡 Medium [M] | Tests | B-01, E-01, G-01 | Intent — Prove the product-details subgraph matches the old gateway. Today — ≥80% unit coverage; parity fixtures (incl Done when: • unit ≥80% • parity fixtures green • schema-diff intentional-only |