Federated GraphQL Breakdown — Packaging · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (co-located) |
| Total FE Stories | 5 |
| Impact | 🔴 1 High · 🟡 3 Medium · 🟢 1 Low |
| Estimated effort | 21–33 days (single-engineer) |
| Phase-1 surface | 21 operation-to-root-field rows · 5 client files · 8 components |
| Generated | 2026-07-16 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Packaging GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (co-located)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| PKG-FE-001 | Migrate packaging reads | Query migration | 🟡 Medium | 5–8 days | PKG-BE-B-01, PKG-BE-B-02 | getPackagings, getPackagingById, getPackagingComponentStatus |
| PKG-FE-002 | Migrate packaging master-data reads and retire deprecated fields | Query migration | 🟢 Low | 2–3 days | PKG-BE-B-04, PKG-BE-B-06 | getCountries, getPackagingFieldValuesByType |
| PKG-FE-003 | Migrate dieline flows | Query + mutation migration | 🟡 Medium | 4–6 days | PKG-BE-B-03, PKG-BE-B-05, PKG-BE-D-02 | getDielines, getDielineEvaluationStatuses, evaluateDieline |
| PKG-FE-004 | Migrate packaging simple mutations and export | Mutation migration | 🟡 Medium | 5–8 days | PKG-BE-D-01, PKG-BE-D-03, PKG-BE-D-04, PKG-BE-D-05, PKG-BE-D-06, PKG-BE-D-07, PKG-BE-D-09 | addPackaging, bulkAddPackagings, bulkUpdatePackagings, exportPackaging, lockPackaging, unlockPackaging, updatePackagingComponentStatus |
| PKG-FE-005 | Migrate updatePackaging saga handling and packet information | Mutation migration (complex) | 🔴 High | 5–8 days | PKG-BE-E-01 | updatePackaging, getPackagingPacketsInformation, getPackagingPacketInformation |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🟡 PKG-FE-001, 🟢 PKG-FE-002 | PKG-FE-001 → PKG-BE-B-01, PKG-BE-B-02<br>PKG-FE-002 → PKG-BE-B-04, PKG-BE-B-06 | Reads cutover — needs backend phase A/B reads live |
| 3 | 🟡 PKG-FE-003, 🟡 PKG-FE-004 | PKG-FE-003 → PKG-BE-B-03, PKG-BE-B-05, PKG-BE-D-02<br>PKG-FE-004 → PKG-BE-D-01, PKG-BE-D-03, PKG-BE-D-04, PKG-BE-D-05 (+3) | Writes — needs backend phase D mutations |
| 4 | 🔴 PKG-FE-005 | PKG-FE-005 → PKG-BE-E-01 | Complex writes / sagas — needs backend phase E + ADR ratification |

Cutover flow: PKG-FE-001 → PKG-FE-002 → PKG-FE-003 → PKG-FE-004 → PKG-FE-005.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBrakDown-BE-packaging.md — the backend breakdown this cutover follows.