Federated GraphQL — Migration Overview (All Domains)

Generated: 2026-07-21  ·  8 domains  ·  spark-internal-graphql → Netflix DGS via Hive Schema Registry

| Program | spark-internal-graphql → Netflix DGS Federation (Hive Registry) |
| --- | --- |
| Domains | 8 |
| Target DGS services | 2 |
| Total Backend Stories | 211 |
| Total Frontend Stories | 41 · 165–256d single-engineer (Frontend section of each per-domain FederatedGqlBreakDown-<domain> page) |
| Complexity (backend) | 🔴 6 Very High · 🟠 13 High · 🟡 74 Medium · 🟢 118 Low |
| Generated | 2026-07-21 |

Overview

We are migrating the entire Product Lifecycle Management (PLM) GraphQL API surface off the monolithic spark-internal-graphql Node.js gateway onto a set of independently owned Netflix DGS (Domain Graph Service) subgraphs, federated via the Hive Schema Registry.

Each DGS is a Kotlin/Spring Boot service that exposes its domain's schema as a federated subgraph. The supergraph stitches them together transparently for clients.

Why?

•  The monolith is a ~15,000-line Node.js resolver with no clear ownership boundaries

•  Federation gives each team autonomous schema ownership, independent deployability, and fine-grained caching

•  Netflix DGS provides production-proven tooling (DataLoaders, code generation, Hive integration)

•  Hive Schema Registry enforces schema contracts and enables safe rollout with schema checks

Engineering model: every story is self-contained in one PR — schema additions, DGS data fetcher, Kotlin REST service method, and Hive registry push. There are no separate service-layer stories.

ACL note: the current gateway obtains per-resource ACL capability tokens. Per ADR-019 (complexStories/acl/01-adr-acl-mid-request-update.md), permission-check and own-domain-token call sites stay resolver-local (context-only, as before); the 31 downstream-token call sites — where a resolver hands its token to a different domain's loader — use Mid-Request ACL Update (SparkSecurityService.updateCurrentUserPermissions(capabilityToken)) before the downstream call. Each complex case's own ADR carries an ACL note applying this classification to its specific call sites.

Glossary

| Term | Meaning |
| --- | --- |
| DGS | Netflix Domain Graph Service — a Spring/Kotlin GraphQL subgraph |
| Hive Gateway / plm-gateway | the federation gateway that composes the subgraphs into one supergraph |
| subgraph | one DGS (e.g. plm-product, plm-sample) |
| co-located | a domain compiling into plm-product (in-process call, not a gateway hop) |
| CAT-1…5 | story categories: 1 schema · 2 resolver · 3 service · 4 federation · 5 tests |
| Phase A–H | the migration order within a domain (see the phases table below) |
| EXT severity | 🔴 critical/sequential · 🟡 single enrichment call · 🔵 optional/gateway |

The migration phases (A→H) — the order of replacement

Stories are grouped into phases that encode the replacement order within a domain:

| Phase | Replaces / builds | Category |
| --- | --- | --- |
| A | schema skeleton, owned types, external stubs, @DgsTypeResolver, service port, ACL/JWT plumbing | CAT-1/CAT-3 |
| B / C | query resolvers (reads) | CAT-2 |
| D | mutation resolvers (writes) | CAT-2 |
| E | complex operations (multi-step writes, aggregations) — often a stub + facade pointing at a complex case | CAT-2 |
| F | federation platform work — gateway composition, facade retirement, stub verification, contract alignment (not entity resolution itself) | CAT-4 |
| G | field resolvers (incl. the heavy ones) + the domain parity harness | CAT-2/CAT-5 |
| H | cross-subgraph entity resolution — real @DgsEntityFetcher/@key fields resolved by a separate subgraph (split out from Phase F) | CAT-4 |

Phase 0 = Spikes — time-boxed research producing a recorded decision before the phase it blocks.

How to read the spikes & related stories

The SPIKE-0x id is the join key between a program spike (here) and the domain stories it gates. Read global → domain to plan decisions, or domain → global to implement.

👔 Product Owner:

1. Phase 0 — Program Spikes table — what each spike blocks and its status. Nothing dependent starts until the spike's decision is recorded.

2. Spike Detail (per bucket) — the brief, the Decision to make, the intended steps, and the resolver table (blast radius).

3. Sequencing — SPIKE-01/02/03 are critical path (Sprint 0); 04/05/06a/06b run in parallel. Assign an owner + timebox each.

4. In a domain page, the Spikes & Complex Cases map lists which of that domain's stories are 🔴🔬-blocked — plan the domain around them.

🔧 Engineer:

1. In the domain A–H table, find your story. If it's 🔴🔬 with `SPIKE-0x` in Depends On, the complex part is blocked until that spike concludes — check its status first.

2. Follow the `SPIKE-0x` id → Spike Detail: the intended cross-domain steps (your target flow) + the resolver table (external services you'll call + what each resolver does today = your parity target).

3. Research so far — the Phase 0 — Program Spikes table links each spike to its complexStories/<case>/ brief.

4. Non-gated stories (no 🔴🔬) — build straight from the story's Acceptance Criteria; no spike needed.

5. In Jira/CSV — the spike is a Spike issue (SPIKE-0x) with the brief + steps in its description; your gated story lists it in Depends On.

One-line model — Product Owner: "which decisions block work, who owns them, when?" → the spike table. Engineer: "is my story blocked, and once unblocked what's the flow + who do I call?" → follow the id to Spike Detail.

🔬 Phase 0 — Program Spikes (cross-domain research buckets)

Why this table lives here and not in the domain pages. The same handful of hard problems recur across many domains under different operation names (e.g. every domain's multi-step update* write hits the same "no rollback" question). Rather than repeat a decision list on every domain page, each recurring problem is generalized into one program spike bucket below. A spike is time-boxed research that produces a recorded decision — not shipped code — and every domain story gated on one is marked 🔴🔬 in its domain page with the spike id in Depends On.

🔬 A spike is only for a genuinely complex problem that needs a solve/migrate approach. Simple, intuitive, one-off decisions (delete-vs-@deprecate drift ops, dead service-method audits, auth-token parity, sort pushdown, DTO request-shape) are not spikes — they are resolved inline in the owning story's acceptance criteria and no longer appear anywhere as a decision table.

| Spike ID | Bucket / Generic Problem | Domains affected (home story) | Blocks | Research so far | Status |
| --- | --- | --- | --- | --- | --- |
| SPIKE-01 | 🔬 Non-Atomic Write Saga — a mutation fans out across ≥2 REST services (workspace-assoc · body · permissions · component-status) with no transaction; on partial failure state is left inconsistent. Choose the failure strategy: (a) compensating saga · (b) compensation-log + best-effort · (c) best-effort. | bom E-01 · claims E-01 · measurement E-01 · packaging E-01 · productDetails E-01 · watchlist E-01 · product E-02 | all E-phase writes | complexStories/non-atomic-write-saga/ (brief + draft ADR-013 + [story breakdown](../../output/complexStories/non-atomic-write-saga/01-stories.md)) | 🟠 Draft ADR-013 proposed — shared WriteSaga module built (PRODUCT-BE-E-00, Sprint 0); consumers wired — ratification pending |
| SPIKE-02 | 🔬 TechPack Aggregate — build a ProductTechPack entity where every field is computed from a different microservice REST API; ratify the assembly pattern under federation. | product E-03/E-04 | product techpack | complexStories/techpack/ (brief + draft ADR-015 + [story breakdown](../../output/complexStories/techpack/01-stories.md)) | 🟠 Draft ADR-015 proposed (facade-then-federate, ADR-015 Option B = catalogue "Option D (hybrid)") — full phase 1–3 story chain built (E-03/E-04, H-01–H-06, F-09) — ratification pending |
| SPIKE-03 | 🔬 Partner Drop/Undrop + Ownership — orchestrated drop/undrop of a business partner across every referencing child domain; decide ownership (domain subgraph vs workspace) and the write saga. | product E-01 · workspace E-01 (later phase) | partner-write E/F | complexStories/partner-drop-undrop-write/ (brief + draft ADR-012 + [story breakdown](../../output/complexStories/partner-drop-undrop-write/01-stories.md)) | 🟠 Draft ADR-012 proposed (owner-orchestrated saga + participant contract, via PRODUCT-BE-E-00) — ratification pending |
| SPIKE-04 | 🔬 Not-Removable / Undroppable Partners — read aggregation computing which partners cannot be removed/dropped because still referenced (cross-domain @requires union). | product G-07 · G-11-1 · workspace G-05 (later phase) | partner-read fields | complexStories/notRemovable-undroppable-partners/ (brief + draft ADR-016 + [story breakdown](../../output/complexStories/notRemovable-undroppable-partners/01-stories.md)) | 🟠 Draft ADR-016 proposed (owner-@requires lane aggregation) — ratification pending |
| SPIKE-05 | 🔬 Polymorphic Type Resolution — interfaces/unions resolved by a category dispatcher; confirm the full code → type table + union membership, then @DgsTypeResolver + per-variant + CI schema-conformance. | bom A-04/G-08 (+ sample A-04/G-02, search B-01/C-02 — later phase) | type-resolver + variant fields | complexStories/polymorphic-type-resolution/ (brief + draft ADR-017 + [story breakdown](../../output/complexStories/polymorphic-type-resolution/01-stories.md)) | 🟠 Draft ADR-017 proposed (per-site ports + CI conformance gate, BOM-BE-A-05 built) — code→type table to confirm at ratification |
| SPIKE-06a | 🔬 Hydration — how a domain reads another's entity (federated @key ref vs REST client); two-stage hydration; federation/read-hub rollout ordering across sibling DGS. | product S-02 (gates C-01) · bom B-05 | hydration + rollout (reads) | complexStories/cross-domain-association/ | 🔴 Open — per-edge rule to decide (concludes via PRODUCT-BE-S-02, no draft ADR of its own — distinct from 06b/ADR-011 below) |
| SPIKE-06b | 🔬 Cross-Domain Association — one pattern for a mutation that also links its record into a sibling domain (workspace/attachment), incl. sync-vs-async and partial-failure handling. D-03 is a pure passthrough (no cross-domain call); D-06/D-07/D-11 are single-backend writes — the product backend owns all endpoints, no sibling service called (draft ADR-011 §1). | product S-01 (gates D-01/D-02/D-04 only — see scope note) | association-side writes (D-01/D-02/D-04) | complexStories/cross-domain-association/ (brief + draft ADR-011 + [story breakdown](../../output/complexStories/cross-domain-association/01-stories.md)) | 🟠 Draft ADR-011 proposed (sync orchestration + shared association component) — D-01/D-02/D-04 ACs updated — ratification pending |

Sequencing: SPIKE-01/02/03 are on the critical path (they block E-phase writes and TechPack); run them in Sprint 0 alongside each domain's B-01 module scaffold. 04/05/06a/06b block specific reads/writes and can run in parallel. Each spike concludes with the decision recorded back into the affected domain stories.

>

Note on `06a`/`06b`: these were originally tracked as one SPIKE-06 id. They're split because they answer different questions — 06a is "how do I read another domain's data," 06b is "how does my write also link into another domain" — and a story should only cite the one it actually needs.

Non-spike complex cases (read pattern applied at cutover — no research decision needed)

These recur across domains too, but the shape of the fix is already known (per-domain contribution + fan-out merge) — there's nothing to research, just build. They still get one complexStories/ brief each so the pattern is documented once instead of per-domain.

| Bucket | Generic Problem | Domains affected (home story) | Research so far |
| --- | --- | --- | --- |
| attachmentsWithMetaData enrichment | 📎 One attachments tab, three sources — files, discussion files, and sample files must merge into one ordered, ACL-filtered feed without a Relationship-Service walk. | product G-01/G-03 · workspace G-01/G-03 (later phase) | complexStories/attachments-enrichment/ (brief + draft ADR-018 + [story breakdown](../../output/complexStories/attachments-enrichment/01-stories.md)) |
| components + counts rollups | 🧮 Five domains, one dashboard number — a product's component list and a workspace's counts strip both roll up parallel per-domain fan-outs plus a batched ACL call into a single screen's worth of data. | product G-02 · workspace G-02/G-04 (later phase) | complexStories/components-and-counts-rollups/ (brief + draft ADR-014 + [story breakdown](../../output/complexStories/components-and-counts-rollups/01-stories.md)) |

T-Shirt Size Classification

| T-Shirt | Story count | Effort (high est., eng-days) | Rule | Typical scope |
| --- | --- | --- | --- | --- |
| 🔴 XXL | ≥ 60 | ≥ 200 | stories ≥ 60 OR effort_hi ≥ 200 | Very large, cross-domain initiative |
| 🔴 XL | 35–59 | 100–199 | stories ≥ 35 OR effort_hi ≥ 100 | Large feature or domain |
| 🟠 L | 25–34 | 60–99 | stories ≥ 25 OR effort_hi ≥ 60 | Medium-large project |
| 🟡 M | 15–24 | 40–59 | stories ≥ 15 OR effort_hi ≥ 40 | Medium-sized project |
| 🟢 S | 8–14 | 20–39 | stories ≥ 8 OR effort_hi ≥ 20 | Small project |
| 🟢 XS | < 8 | < 20 | otherwise | Minor enhancement or maintenance |

Domain Index

| # | Domain | Target DGS | T-Shirt | BE Stories | 🔴 VH | 🟠 H | 🟡 M | 🟢 L | FE Stories | FE effort | Breakdown pages |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Bill of Materials (BOM) | plm-product (co-located) | XL | 37 | 1 | 2 | 13 | 21 | 7 | 29–46d | FederatedGqlBreakDown-bom |
| 2 | Claims | spark-claims (separate) | L | 20 | 0 | 2 | 8 | 10 | 4 | 17–27d | FederatedGqlBreakDown-claims |
| 3 | Impression | plm-product (co-located) | XS | 7 | 0 | 0 | 2 | 5 | 2 | 3–5d | FederatedGqlBreakDown-impression |
| 4 | Measurement | plm-product (co-located) | M | 30 | 0 | 1 | 5 | 24 | 4 | 12–19d | FederatedGqlBreakDown-measurement |
| 5 | Packaging | plm-product (co-located) | L | 23 | 0 | 2 | 8 | 13 | 5 | 21–33d | FederatedGqlBreakDown-packaging |
| 6 | Product | plm-product (host) | XXL | 69 | 5 | 4 | 27 | 33 | 13 | 68–104d | FederatedGqlBreakDown-product |
| 7 | Product Details | plm-product (co-located) | M | 12 | 0 | 1 | 6 | 5 | 3 | 8–12d | FederatedGqlBreakDown-productDetails |
| 8 | Watchlist | plm-product (co-located) | M | 13 | 0 | 1 | 5 | 7 | 3 | 7–10d | FederatedGqlBreakDown-watchlist |
| — | TOTAL | — | — | 211 | 6 | 13 | 74 | 118 | 41 | 165–256d | — |

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

🔬 Spike Detail — the brief + the resolvers each spike touches

For each spike: what it means, the decision to make, and the exact queries/mutations/field-resolvers it covers — with the external services each one calls today and a one-line summary of its current logic, so an engineer knows what to look at before starting.

🔬 `SPIKE-01` · Non-Atomic Write Saga

•  Some “save” buttons actually fire two or three separate backend calls in a row (e.g. first update which workspaces a record belongs to, then save the record body, then save its permissions).

•  There is no database transaction across them, so if call 2 or 3 fails, call 1 is already committed and nothing undoes it — the record is left half-saved.

•  This spike picks one consistent way to detect and recover from that partial failure for every write of this shape.

Decision to make: Pick (a) compensating saga, (b) compensation-log + best-effort, or (c) best-effort — and write down how to undo each step.

Intended cross-domain steps:

1. Open a write-saga and record each step so it can be undone

2. PUT workspace-association first (compensatable — remembers add/remove to reverse)

3. PUT the record body (typed validation exception on error)

4. PUT permissions/partners only if the input carries them

5. On any step failure → run the chosen strategy: compensate (saga) or log + best-effort

| Resolver (home story) | Domain | Kind | Calls (external services) | What it does today (minimal) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 🔴🔬 BOM-BE-E-01 updateBom — 3-step orchestrated write | bom | Mutation | workspaceV2 | editing a bom today is really three separate backend calls made one - after another, with no undo button: (1) if the caller changed which workspaces the bom belongs… |  |  |
| 🔴🔬 CLAIM-BE-E-01 updateClaim (proxy ACL + multi-step write) | claims | Mutation | workspaceV2 | getUserPermissionsJWTByProxy({id:humanId, proxyIds:[parentId], basePermissions:true}) (proxy/external ACL path — context only); 2) if workspaceContext.{add,remove}… |  |  |
| 🔴🔬 MST-BE-E-01 updateMeasurement — 2-step orchestrated write | measurement | Mutation | workspaceV2 | workspaceAssociations = sparkMeasurement.updateWorkspaceAssociations \ | \ | {}. token for [humanId]. 2. If add/remove workspaces → workspaceAssociationHelper(MEASUREMENT… |
| 🔴🔬 PKG-BE-E-01 updatePackaging (multi-step write) | packaging | Mutation | attachment, relationship | token; set humanId=packagingId; PUT packaging/v1 (body); 2) if attachmentsToRemove → (attachment) archiveAttachmentBulkV2 + (relationship) removeRelationship; 3) if… |  |  |
| 🔴🔬 PRODUCT-BE-E-00 WriteSaga shared module (Sprint 0, critical path) | product | Service | — (internal only) | — |  |  |
| 🔴🔬 PRODUCT-BE-E-02 updateComponentStatuses (5-loader fan-out) | product | Mutation | claim | updating component statuses fans out to 5 places in parallel (bom, - measurement, productDetail, packaging — all internal — plus claim, external). - The bug: a loop… |  |  |
| 🔴🔬 PDTL-BE-E-01 updateProductDetailsSet (multi-step write) | productDetails | Mutation | attachment, workspaceV2 | if workspaceContext.{add,remove}Workspaces non-empty → workspaceAssociationHelper(PRODUCT_DETAIL, id, add, remove) (throws on error); 2) null workspaceContext; 3) if… |  |  |
| 🔴🔬 WATCHLIST-BE-E-01 updateWatchlistEntries (multi-step write) | watchlist | Mutation | attachment, userGroup | per-entry (currently NOT awaited — bug): getUserGroups([humanId]); if existing participants → updateUserGroup, else (user-group) addUserGroup (throw on error); 2)… |  |  |

🔬 `SPIKE-02` · TechPack Aggregate

•  A “TechPack” is one screen that shows counts and lists pulled from ~8 different backend services (attachments, discussions, samples, claims, BOMs, measurements, constructions, watchlists).

•  Today a single gateway helper calls all of them and adds up the numbers.

•  This spike decides how to assemble that one entity under federation so each service owns and contributes its own slice.

Decision to make: Ratify the assembly pattern and each domain’s contribution. Draft ADR-015 proposes facade-then-federate (ADR-015 Option B; the catalogue label is "Option D (hybrid)"): a frozen aggregation facade serves all 11 fields day 1 (E-03/E-04); each domain re-homes its slice as its subgraph ships (H-01–H-05 + the co-located F-04/F-06/F-08, extend type ResourcesCount); the facade retires last (F-09).

Intended cross-domain steps:

1. Phase 1 (`E-03`/`E-04`) — thin @DgsQuery stub in plm-product → frozen aggregation facade answers all 11 ResourcesCount fields (works day 1, before any sibling federates)

2. Phase 2 (`H-01`–`H-05` + co-located `F-04`/`F-06`/`F-08`) — as each owning subgraph ships, it contributes its slice via extend type ResourcesCount @key(fields: "productId partnerId"); the facade stops serving that field (per-slice parity fixture gates the flip)

3. Each subgraph returns only its own slice (its count/list) — it owns that field; co-located domains (bom/measurement/construction/watchlist) contribute in-process

4. Phase 3 (`F-09`) — facade retired; the gateway resolves the @key shell and fans out _entities to the contributors

| Resolver (home story) | Domain | Kind | Calls (external services) | What it does today (minimal) |
| --- | --- | --- | --- | --- |
| 🔴🔬 PRODUCT-BE-E-03 getProductTechPackCountV1 stub + aggregation facade (facade-then-federate, Phase 1) | product | Query | attachment, search | the TechPack panel shows badge counts (attachments, discussions, - samples, boms, claims, etc.) for a product. - Getting those counts today means walking the entire… |
| 🔴🔬 PRODUCT-BE-E-04 getProductTechPackBulkCountV1 (bulk wrapper, ordering fix) | product | Query | attachment, search | the bulk version runs all N single-product lookups concurrently and - returns them in whatever order they happen to finish — not the order the caller asked for. - If a… |

🔬 `SPIKE-03` · Partner Drop/Undrop + Ownership

•  When a business partner is dropped or undropped from a product or workspace, every child domain that references that partner has to be updated too.

•  This spike decides who orchestrates that fan-out write and how it recovers if one of the child updates fails midway.

Decision to make: Decide ownership (domain subgraph vs workspace) and the write-saga/rollback for the drop/undrop fan-out.

Intended cross-domain steps:

1. Owner (product/workspace) receives the drop/undrop request and starts the orchestration

2. Fans out the write to every child domain that references the partner

3. Each child applies its change with per-target failure isolation (one failure is visible, doesn't swallow the rest)

4. On partial failure → compensate/log per the SPIKE-01 saga

| Resolver (home story) | Domain | Kind | Calls (external services) | What it does today (minimal) |
| --- | --- | --- | --- | --- |
| 🔴🔬 PRODUCT-BE-E-01 productBusinessPartnerActions (REMOVE/DROP/UNDROP) | product | Mutation | sampleV2, recentlyViewed, todo, favorite | removing, dropping, or un-dropping a business partner from a product - isn't one write — it's a ~220-line dispatcher that updates the partner's status and then fans… |

🔬 `SPIKE-04` · Not-Removable / Undroppable Partners

•  The UI needs to know which partners can’t be removed yet because something still references them.

•  Answering that means asking several domains “do you still use this partner?” and combining the answers.

•  This spike designs that cross-domain read.

Decision to make: Agree the @requires contribution each domain exposes and where the union is computed.

Intended cross-domain steps:

1. Owner exposes the public field (notRemovablePartnerIds / unDroppablePartners)

2. Each contributing domain declares its refs as `@external`; owner `@requires` them

3. Gateway fetches every domain's contribution and batches them

4. Owner resolver unions + dedupes into the final answer

| Resolver (home story) | Domain | Kind | Calls (external services) | What it does today (minimal) |
| --- | --- | --- | --- | --- |
| 🔴🔬 PRODUCT-BE-G-07 Product.vendorAttributes + businessPartners + droppedPartners + unDroppablePartners + status | product | Field resolver | vmm | business-partner ids sometimes arrive as strings that need to be - parsed to ints before VMM will accept them (vmmUtils's int-parse normalization) — an easy detail to… |
| 🔴🔬 PRODUCT-BE-G-11-1 Product.notRemovablePartnerIds + notRemovableWorkspaceIds | product | Field resolver | vmm, workspaceV2 | to figure out which partners/workspaces can't be removed from a product (e.g. because they're the last remaining owner), today's code calls into 4-5 other field… |

🔬 `SPIKE-05` · Polymorphic Type Resolution

•  Some GraphQL types are interfaces or unions — one field can return one of several concrete shapes, chosen by a category code.

•  This spike confirms the full code→type mapping and how the resolver dispatches each row to the right variant.

Decision to make: Confirm the code → type table + union membership, then wire @DgsTypeResolver + CI conformance.

Intended cross-domain steps:

1. Read the row's category code (or union discriminator)

2. @DgsTypeResolver maps code → concrete type (unknown → base type)

3. Resolve the per-variant field set for that concrete type

4. CI schema-conformance check fails the build if a variant misses an interface field

| Resolver (home story) | Domain | Kind | Calls (external services) | What it does today (minimal) |
| --- | --- | --- | --- | --- |
| 🔴🔬 BOM-BE-A-04 @DgsTypeResolver for the 2 BOM interfaces | bom | Field resolver | — (internal only) | - Material: switch on material.materialCategory.code → 4→Trim, 6→Wash, 2→Fabric, 15→Combination, 16→FabricSpec, {10,11,12,13,14,17–24}→Packaging, default… |

🔬 `SPIKE-06a` · Hydration

•  One domain often needs to read another domain’s object (e.g. a product on a bom).

•  This spike decides whether to stitch it as a federated @key reference or call the other service directly, plus the order the services must ship so nothing launches half-wired.

Decision to make: Choose federated @key reference vs REST client per edge, and the cross-DGS rollout order.

Intended cross-domain steps:

1. Decide the edge shape: federated `@key` reference vs a direct REST client call

2. If @key: emit the key and let the owning subgraph hydrate it (gateway hop)

3. If REST: call the other service in-process/directly and map the result

4. Sequence the rollout order so no consumer launches before its provider is federated

| Resolver (home story) | Domain | Kind | Calls (external services) | What it does today (minimal) |
| --- | --- | --- | --- | --- |
| 🔴🔬 BOM-BE-B-05 getBomMaterialTypes (merge with Material Hub) | bom | Query | materialHub | load bom material types (GET …/master_data/bom_material_types[?ids]) and materialHub.getHubMaterialTypes (today sequential), concat; map each hub type → {code:9… |
| 🔴🔬 PRODUCT-BE-C-01 getProducts(...) two-stage hydration | product | Query | search | listing products needs data from two places — the search index (which - knows flags like "has boms", "has claims", workspace membership) and the canonical product… |

🔬 `SPIKE-06b` · Cross-Domain Association

•  A mutation on one domain’s record often also has to link that record into a sibling domain — attach files, put it in a workspace, add teams, add partners.

•  This spike decides the one pattern every such mutation should follow (sync direct call / event-driven / shared AssociationService), instead of each mutation inventing its own “write, then also link” logic.

•  Unlike 06a, there is no read-hydration or federated-reference question here — this is purely about how a write fans out to a sibling domain. Scope (per draft ADR-011 §1): D-03 (bulkUpdateProducts) is a pure passthrough — no cross-domain call.

•  D-06/D-07/D-11 ("Collab Canvas") are cross-domain in concept but all their endpoints are on the product backend; no external workspace/partner service is called.

•  Only D-01, D-02, D-04 are in scope.

Decision to make: Pick the association pattern (see PRODUCT-BE-S-01's three candidates) and how a mid-flight association failure is handled.

Intended cross-domain steps:

1. Primary mutation writes its own record (product create/update)

2. If the input carries a cross-domain link (workspaceId, copyProduct, template attachments) → build the association per the chosen S-01 pattern (draft ADR-011: shared association component, sync, service-to-service REST)

3. Apply the link to the target domain (workspace, attachment)

4. Record what happens if the link step fails after the primary write succeeded (today: mostly silent/undocumented; per-mutation failure policy is declared explicitly under ADR-011)

| Resolver (home story) | Domain | Kind | Calls (external services) | What it does today (minimal) |
| --- | --- | --- | --- | --- |
| 🔴🔬 PRODUCT-BE-D-01 addProduct | product | Mutation | workspaceV2, attachment | POST ${v1} + optional copyProductToProduct(copyProduct) + workspace association |
| 🔴🔬 PRODUCT-BE-D-02 addProducts (bulk) | product | Mutation | attachment | bulk POST ${v1}/bulk + attachment-link side-effects (no rollback — preserve, flag) |
| 🔴🔬 PRODUCT-BE-D-04 updateProduct | product | Mutation | attachment | PUT ${v1}/{id} + optional copy + archive removed-template attachments (template branch) |