Federated GraphQL Breakdown — Product Details · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (co-located) |
| Total FE Stories | 3 |
| Impact | 🔴 0 High · 🟡 2 Medium · 🟢 1 Low |
| Estimated effort | 8–12 days (single-engineer) |
| Phase-1 surface | 7 operation-to-root-field rows · 2 client files · 4 components |
| Generated | 2026-07-17 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Product Details GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (co-located)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| PDTL-FE-001 | Migrate product-details reads | Query migration | 🟢 Low | 2–3 days | PDTL-BE-B-01 | getProductDetailsById, getProductDetailComponentStatus |
| PDTL-FE-002 | Migrate product-details simple mutations | Mutation migration | 🟡 Medium | 3–4 days | PDTL-BE-D-01, PDTL-BE-D-02, PDTL-BE-D-04 | createProductDetailsSet, productDetailLockUnlock, cloneFilesForProductDetails, updateProductDetailComponentStatus |
| PDTL-FE-003 | Migrate updateProductDetailsSet saga handling | Mutation migration (complex) | 🟡 Medium | 3–5 days | PDTL-BE-E-01 | updateProductDetailsSet |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🟢 PDTL-FE-001 | PDTL-FE-001 → PDTL-BE-B-01 | Reads cutover — needs backend phase A/B reads live |
| 3 | 🟡 PDTL-FE-002 | PDTL-FE-002 → PDTL-BE-D-01, PDTL-BE-D-02, PDTL-BE-D-04 | Writes — needs backend phase D mutations |
| 4 | 🟡 PDTL-FE-003 | PDTL-FE-003 → PDTL-BE-E-01 | Complex writes / sagas — needs backend phase E + ADR ratification |

Cutover flow: PDTL-FE-001 → PDTL-FE-002 → PDTL-FE-003.

Recommended Story Graph — 2 Frontend Engineers

The order map above packed onto two frontend engineers. Lanes re-sync at each step because the step's backend gate — not engineer availability — is the limiter; in a single-story step the second engineer pairs on parity checks/rollout or pre-pulls the next unblocked story. FE→FE chains stay with one engineer for context.

| Step | 👤 FE-1 | 👤 FE-2 | Backend gate (focus) |
| --- | --- | --- | --- |
| 1 | 🟢 PDTL-FE-001 (2–3d) | — | Reads cutover — needs backend phase A/B reads live |
| 3 | 🟡 PDTL-FE-002 (3–4d) | — | Writes — needs backend phase D mutations |
| 4 | 🟡 PDTL-FE-003 (3–5d) | — | Complex writes / sagas — needs backend phase E + ADR ratification |

Elapsed (nominal midpoints): ~10 FE build days with 2 engineers vs ~10 single-engineer — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-BE-productDetails.md — the backend breakdown this cutover follows.