Implementation Plan — 2 Backend + 2 Frontend Engineers

🏷️ Tags: dgs-migration · team-plan — Generated: 2026-07-17 · Derived from the same story parsers as the per-domain breakdowns (grouped-XS merges included), so story counts and day totals reconcile.

Day figures are nominal midpoints of AI-estimated ranges — confirm in refinement. 1 sprint = 10 working days. d0 = program start.

Team & operating model

•  BE-1 owns Product end-to-end (host DGS, shared wiring, largest surface — one owner avoids schema-merge churn), then takes Claims (the separate spark-claims subgraph) and the tiny Impression tail — this balances the two lanes to within a sprint of each other.

•  BE-2 runs the co-located domains in the order the FE waves need them: watchlist → productDetails → measurement → packaging → bom.

•  FE-1 / FE-2 follow the program waves (fe-10): watchlist pilot first (1-sprint production soak is the wave-2 entry gate), then parallel domain cutovers, Product split across both engineers last.

•  A domain's FE cutover starts when its backend phases A–E (reads, search, writes) are live; BE phases F–G (federation stitches, field-resolver parity) trail behind the flip and don't block it. (Refinement lever: FE read-stories can start dual-running right after B/C — that pulls each FE start earlier than shown here.)

•  Phase-0 spikes (SPIKE-01…07) are not on these lanes — run them in the first 1–2 sprints alongside PRODUCT-BE scaffold work; E-phase stories are gated on their outcomes.

Backend lanes

| Lane | # | Domain | Stories | Est. days (lo–hi) | Day window | FE gate (A–E done) |
| --- | --- | --- | --- | --- | --- | --- |
| 👤 BE-1 | 1 | Product | 70 | 202 (139–264) | d0–d202 (spr 1–21) | d102 |
| 👤 BE-1 | 2 | Claims | 21 | 53 (36–70) | d202–d254 (spr 21–26) | d231 |
| 👤 BE-1 | 3 | Impression | 8 | 15 (10–20) | d254–d270 (spr 26–27) | d260 |
| 👤 BE-2 | 1 | Watchlist | 14 | 34 (23–45) | d0–d34 (spr 1–4) | d19 |
| 👤 BE-2 | 2 | Product Details | 13 | 34 (23–45) | d34–d68 (spr 4–7) | d54 |
| 👤 BE-2 | 3 | Measurement | 21 | 44 (30–59) | d68–d112 (spr 7–12) | d99 |
| 👤 BE-2 | 4 | Packaging | 24 | 58 (39–76) | d112–d170 (spr 12–17) | d150 |
| 👤 BE-2 | 5 | BOM | 37 | 91 (62–120) | d170–d261 (spr 18–27) | d214 |

•  Lanes are load-balanced: BE-1 drains at d270, BE-2 at d261 — whoever frees first picks up post-launch F-phase stitches, G-phase parity leftovers, and pairs on the other lane's remaining domain.

•  Cross-subgraph F-phase stories that wait on later-phase domains (attachment/discussion/sample/search subgraphs) are excluded from these gates — they land post-launch when the owning subgraph exists.

Frontend lanes

| Wave | Domain | Engineer | FE days | Waits for | Day window |
| --- | --- | --- | --- | --- | --- |
| 1 | Watchlist | 👤 FE-1 | 8 | BE Watchlist A–E done (d19) | d19–d28 (spr 2–3) |
| 2 | Product Details | 👤 FE-1 | 10 | BE Product Details A–E done (d54) | d54–d64 (spr 6–7) |
| 2 | Measurement | 👤 FE-2 | 16 | BE Measurement A–E done (d99) | d99–d114 (spr 10–12) |
| 2 | Packaging | 👤 FE-2 | 27 | BE Packaging A–E done (d150) | d150–d176 (spr 15–18) |
| 3 | BOM | 👤 FE-1 | 38 | BE BOM A–E done (d214) | d214–d252 (spr 22–26) |
| 3 | Claims | 👤 FE-2 | 22 | BE Claims A–E done (d231) | d231–d253 (spr 24–26) |
| 4 | Product | 👤 FE-1 + FE-2 | 84 | BE Product A–E done (d102) | d253–d295 (spr 26–30) |
| 4 | Impression | 👤 FE-2 | 4 | BE Impression A–E done (d260) | d295–d299 (spr 30–30) |

•  FE engineers are gate-bound, not capacity-bound — between gates they pair on parity dashboards, dual-run monitoring and rollback drills, and pre-pull the next domain's fragment/codegen prep.

•  Search-gated stories (MST-FE-002, BOM-FE-003, PRODUCT-FE-003) also wait on the search read-hub decision — external to this plan and may slide independently.

•  Impression rides its partner flips (IMPRESSION-FE-001 with BOM-FE-002, IMPRESSION-FE-002 with PRODUCT-FE-001).

Milestones

| Milestone | ≈ Day | ≈ Sprint |
| --- | --- | --- |
| 🚦 Watchlist pilot live on the router | d28 | 3 |
| 🔗 First cross-subgraph cutover (Claims FE) | d253 | 26 |
| 🏁 Product backend complete (plm-product host) | d202 | 21 |
| 🧱 All backend lanes drained (both subgraphs schema-complete) | d270 | 27 |
| ✅ All FE cutovers flipped | d299 | 30 |
| Program complete (excl. post-launch F-phase) | d299 | 30 |

≈ 30 sprints (~15 months) with this team, vs the sequential single-pair estimate in 00-program-overview.md. Buffered (+20%) planning figure: ~36 sprints.

How to read this with the other docs

•  Per-domain lane detail: Recommended Story Graph — 2 Backend Engineers in each FederatedGqlBreakDown-BE-{domain} page, and — 2 Frontend Engineers in each FederatedGqlBreakDown-FE-{domain} page.

•  Dependency-only view (no team constraint): Recommended Implementation Order on the same pages.

•  Program waves and external gates: analysis/program/fe-10-migration-sequencing.md.

Team plan · generated 2026-07-17 by generate_team_plan.py.