Federated GraphQL Breakdown — Measurement · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (co-located) |
| Total FE Stories | 4 |
| Impact | 🔴 0 High · 🟡 3 Medium · 🟢 1 Low |
| Estimated effort | 12–19 days (single-engineer) |
| Phase-1 surface | 13 operation-to-root-field rows · 4 client files · 7 components |
| Generated | 2026-07-17 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Measurement GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (co-located)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| MST-FE-001 | Migrate measurement reads and retire humanId | Query migration | 🟡 Medium | 4–6 days | MST-BE-B-01, MST-BE-B-02 | getMeasurementByIds, getMeasurementSetStatus, getMeasurementComponentStatus |
| MST-FE-002 | Migrate measurement list/search reads | Query migration | 🟡 Medium | 3–5 days | MST-BE-C-01, MST-BE-C-02 | getMeasurements, getMeasurementsElastic |
| MST-FE-003 | Migrate measurement master-data reads | Query migration | 🟢 Low | 1–2 days | MST-BE-B-02 | getUnitsOfMeasure, getThicknessUnitsOfMeasure |
| MST-FE-004 | Migrate measurement mutations | Mutation migration | 🟡 Medium | 4–6 days | MST-BE-D-02, MST-BE-D-06, MST-BE-D-07 | lockMeasurementSet, unlockMeasurementSet, putSampleMeasurementSet, deleteSampleMeasurementSet |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🟡 MST-FE-001, 🟢 MST-FE-003 | MST-FE-001 → MST-BE-B-01, MST-BE-B-02<br>MST-FE-003 → MST-BE-B-02 | Reads cutover — needs backend phase A/B reads live |
| 2 | 🟡 MST-FE-002 | MST-FE-002 → MST-BE-C-01, MST-BE-C-02 | Search & listing — needs backend phase C |
| 3 | 🟡 MST-FE-004 | MST-FE-004 → MST-BE-D-02, MST-BE-D-06, MST-BE-D-07 | Writes — needs backend phase D mutations |

Cutover flow: MST-FE-001 → MST-FE-003 → MST-FE-002 → MST-FE-004.

Recommended Story Graph — 2 Frontend Engineers

The order map above packed onto two frontend engineers. Lanes re-sync at each step because the step's backend gate — not engineer availability — is the limiter; in a single-story step the second engineer pairs on parity checks/rollout or pre-pulls the next unblocked story. FE→FE chains stay with one engineer for context.

| Step | 👤 FE-1 | 👤 FE-2 | Backend gate (focus) |
| --- | --- | --- | --- |
| 1 | 🟡 MST-FE-001 (4–6d) | 🟢 MST-FE-003 (1–2d) | Reads cutover — needs backend phase A/B reads live |
| 2 | 🟡 MST-FE-002 (3–5d) | — | Search & listing — needs backend phase C |
| 3 | 🟡 MST-FE-004 (4–6d) | — | Writes — needs backend phase D mutations |

Elapsed (nominal midpoints): ~14 FE build days with 2 engineers vs ~16 single-engineer — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-BE-measurement.md — the backend breakdown this cutover follows.