Federated GraphQL Breakdown — Product · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (host) |
| Total FE Stories | 12 |
| Impact | 🔴 3 High · 🟡 9 Medium · 🟢 0 Low |
| Estimated effort | 66–102 days (single-engineer) |
| Phase-1 surface | 66 operation-to-root-field rows · 20 client files · 48 components |
| Generated | 2026-07-17 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Product GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (host)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| PRODUCT-FE-001 | Migrate getProduct documents in product-queries | Query migration | 🔴 High | 10–15 days | PRODUCT-BE-B-01 | getProduct |
| PRODUCT-FE-002 | Migrate shared-library getProduct consumers | Query migration | 🟡 Medium | 5–8 days | PRODUCT-BE-B-01, PRODUCT-BE-B-02, PRODUCT-FE-001 | getProduct, getProductVersions |
| PRODUCT-FE-003 | Migrate product list and bulk reads | Query migration | 🔴 High | 8–12 days | PRODUCT-BE-S-02, PRODUCT-BE-B-02 | getProducts, getProductsByIds |
| PRODUCT-FE-004 | Migrate product status and workspace-context reads | Query migration | 🟡 Medium | 5–8 days | PRODUCT-BE-B-02 | getProductStatus |
| PRODUCT-FE-005 | Migrate template library and categories reads | Query migration | 🟡 Medium | 5–8 days | PRODUCT-BE-C-02, PRODUCT-BE-C-03 | getProductTemplates, getCategories |
| PRODUCT-FE-006 | Migrate product rules administration | Query + mutation migration | 🟡 Medium | 4–6 days | PRODUCT-BE-B-06, PRODUCT-BE-B-10, PRODUCT-BE-C-05, PRODUCT-BE-D-14 | getProductRules, getProductRulesById, getAllAvailableRules, getProductDeptRules, getProductBPRules, searchProductRules, addProductRule, updateProductRule, deleteProductRule |
| PRODUCT-FE-007 | Migrate simple product mutations | Mutation migration | 🟡 Medium | 6–10 days | PRODUCT-BE-D-01, PRODUCT-BE-D-02, PRODUCT-BE-D-03, PRODUCT-BE-D-04, PRODUCT-BE-D-05, PRODUCT-BE-D-10, PRODUCT-BE-D-14 | addProduct, addProducts, updateProduct, bulkUpdateProducts, carryForwardProduct, updateViewToggle, linkProduct, unlinkProduct |
| PRODUCT-FE-008 | Migrate team and partner assignment mutations | Mutation migration | 🟡 Medium | 4–6 days | PRODUCT-BE-D-06, PRODUCT-BE-D-10, PRODUCT-FE-001 | addTeamsToProduct, addBusinessPartnersToProductWithType, updateProductTeamsWorkspaceContext |
| PRODUCT-FE-009 | Migrate partner drop/undrop orchestration | Mutation migration (complex) | 🔴 High | 8–12 days | PRODUCT-BE-S-03, PRODUCT-BE-D-06 | productBusinessPartnerActions, updateBusinessPartnerStatuses |
| PRODUCT-FE-010 | Migrate TechPack count queries (facade-then-federate) | Query migration (staged) | 🟡 Medium | 4–6 days (step 1) + 4–6 days (step 2) | PRODUCT-BE-E-03, PRODUCT-BE-E-04 | getProductTechPackCountV1, getProductTechPackBulkCountV1 |
| PRODUCT-FE-011 | Migrate component status rollups | Query + mutation migration | 🟡 Medium | 4–6 days | PRODUCT-BE-B-01, PRODUCT-BE-D-18, PRODUCT-BE-E-02 | getProduct, updateComponentStatus, updateComponentStatuses |
| PRODUCT-FE-012 | Verify fragment type-conditions, __typename logic and cache keys against federated type names | Verification / refactor | 🟡 Medium | 3–5 days | PRODUCT-BE-F-14 | cross-cutting (no single operation) |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🔴 PRODUCT-FE-001, 🟡 PRODUCT-FE-004 | PRODUCT-FE-001 → PRODUCT-BE-B-01<br>PRODUCT-FE-004 → PRODUCT-BE-B-02 | Reads cutover — needs backend phase A/B reads live |
| 2 | 🟡 PRODUCT-FE-002, 🟡 PRODUCT-FE-005 | PRODUCT-FE-002 → PRODUCT-BE-B-01, PRODUCT-BE-B-02<br>PRODUCT-FE-005 → PRODUCT-BE-C-02, PRODUCT-BE-C-03 | Search & listing — needs backend phase C |
| 3 | 🟡 PRODUCT-FE-006, 🟡 PRODUCT-FE-007, 🟡 PRODUCT-FE-008 | PRODUCT-FE-006 → PRODUCT-BE-B-06, PRODUCT-BE-B-10, PRODUCT-BE-C-05, PRODUCT-BE-D-14<br>PRODUCT-FE-007 → PRODUCT-BE-D-01, PRODUCT-BE-D-02, PRODUCT-BE-D-03, PRODUCT-BE-D-04 (+3)<br>PRODUCT-FE-008 → PRODUCT-BE-D-06, PRODUCT-BE-D-10 | Writes — needs backend phase D mutations |
| 4 | 🟡 PRODUCT-FE-010, 🟡 PRODUCT-FE-011, 🟡 PRODUCT-FE-012 | PRODUCT-FE-010 → PRODUCT-BE-E-03, PRODUCT-BE-E-04<br>PRODUCT-FE-011 → PRODUCT-BE-B-01, PRODUCT-BE-D-18, PRODUCT-BE-E-02<br>PRODUCT-FE-012 → PRODUCT-BE-F-14 | Complex writes / sagas — needs backend phase E + ADR ratification |
| 5 | 🔴 PRODUCT-FE-003, 🔴 PRODUCT-FE-009 | PRODUCT-FE-003 → PRODUCT-BE-S-02, PRODUCT-BE-B-02<br>PRODUCT-FE-009 → PRODUCT-BE-S-03, PRODUCT-BE-D-06 | Externally gated — search/read-hub decision |

Cutover flow: PRODUCT-FE-001 → PRODUCT-FE-004 → PRODUCT-FE-002 → PRODUCT-FE-005 → PRODUCT-FE-006 → PRODUCT-FE-007 → PRODUCT-FE-008 → PRODUCT-FE-010 → PRODUCT-FE-011 → PRODUCT-FE-012 → PRODUCT-FE-003 → PRODUCT-FE-009.

Recommended Story Graph — 2 Frontend Engineers

The order map above packed onto two frontend engineers. Lanes re-sync at each step because the step's backend gate — not engineer availability — is the limiter; in a single-story step the second engineer pairs on parity checks/rollout or pre-pulls the next unblocked story. FE→FE chains stay with one engineer for context.

| Step | 👤 FE-1 | 👤 FE-2 | Backend gate (focus) |
| --- | --- | --- | --- |
| 1 | 🔴 PRODUCT-FE-001 (10–15d) | 🟡 PRODUCT-FE-004 (5–8d) | Reads cutover — needs backend phase A/B reads live |
| 2 | 🟡 PRODUCT-FE-002 (5–8d) | 🟡 PRODUCT-FE-005 (5–8d) | Search & listing — needs backend phase C |
| 3 | 🟡 PRODUCT-FE-007 (6–10d)<br>🟡 PRODUCT-FE-008 (4–6d) | 🟡 PRODUCT-FE-006 (4–6d) | Writes — needs backend phase D mutations |
| 4 | 🟡 PRODUCT-FE-010 (4–6d)<br>🟡 PRODUCT-FE-012 (3–5d) | 🟡 PRODUCT-FE-011 (4–6d) | Complex writes / sagas — needs backend phase E + ADR ratification |
| 5 | 🔴 PRODUCT-FE-003 (8–12d) | 🔴 PRODUCT-FE-009 (8–12d) | Externally gated — search/read-hub decision |

Elapsed (nominal midpoints): ~51 FE build days with 2 engineers vs ~84 single-engineer — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-BE-product.md — the backend breakdown this cutover follows.