Federated GraphQL Breakdown — Claims · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | spark-claims (separate) |
| Total FE Stories | 4 |
| Impact | 🔴 2 High · 🟡 2 Medium · 🟢 0 Low |
| Estimated effort | 17–27 days (single-engineer) |
| Phase-1 surface | 18 operation-to-root-field rows · 6 client files · 8 components |
| Generated | 2026-07-17 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Claims GraphQL operations in pdex-ui-react at the federated router (subgraph spark-claims (separate)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| CLAIM-FE-001 | Split the claim fragment factory and re-target claim fragments | Refactor | 🟡 Medium | 2–3 days | — | — |
| CLAIM-FE-002 | Migrate claim reads (first cross-subgraph cutover) | Query migration | 🔴 High | 6–10 days | CLAIM-BE-B-01, CLAIM-BE-B-02, CLAIM-FE-001 | getClaims, getClaimByIds, getCommunicationChannels, getAllClaimsAbout, getClaimComponentStatus |
| CLAIM-FE-003 | Migrate claim simple mutations and export | Mutation migration | 🟡 Medium | 4–6 days | CLAIM-BE-D-01, CLAIM-BE-D-02, CLAIM-BE-D-03 | createClaim, bulkUpdateClaim, lockClaim, unlockClaim, requestClaimExport |
| CLAIM-FE-004 | Migrate updateClaim multi-step write handling | Mutation migration (complex) | 🔴 High | 5–8 days | CLAIM-BE-E-01 | updateClaim |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🟡 CLAIM-FE-001 | — | Reads cutover — needs backend phase A/B reads live |
| 2 | 🔴 CLAIM-FE-002 | CLAIM-FE-002 → CLAIM-BE-B-01, CLAIM-BE-B-02 | Search & listing — needs backend phase C |
| 3 | 🟡 CLAIM-FE-003 | CLAIM-FE-003 → CLAIM-BE-D-01, CLAIM-BE-D-02, CLAIM-BE-D-03 | Writes — needs backend phase D mutations |
| 4 | 🔴 CLAIM-FE-004 | CLAIM-FE-004 → CLAIM-BE-E-01 | Complex writes / sagas — needs backend phase E + ADR ratification |

Cutover flow: CLAIM-FE-001 → CLAIM-FE-002 → CLAIM-FE-003 → CLAIM-FE-004.

Recommended Story Graph — 2 Frontend Engineers

The order map above packed onto two frontend engineers. Lanes re-sync at each step because the step's backend gate — not engineer availability — is the limiter; in a single-story step the second engineer pairs on parity checks/rollout or pre-pulls the next unblocked story. FE→FE chains stay with one engineer for context.

| Step | 👤 FE-1 | 👤 FE-2 | Backend gate (focus) |
| --- | --- | --- | --- |
| 1 | 🟡 CLAIM-FE-001 (2–3d) | — | Reads cutover — needs backend phase A/B reads live |
| 2 | 🔴 CLAIM-FE-002 (6–10d) | — | Search & listing — needs backend phase C |
| 3 | 🟡 CLAIM-FE-003 (4–6d) | — | Writes — needs backend phase D mutations |
| 4 | 🔴 CLAIM-FE-004 (5–8d) | — | Complex writes / sagas — needs backend phase E + ADR ratification |

Elapsed (nominal midpoints): ~22 FE build days with 2 engineers vs ~22 single-engineer — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-BE-claims.md — the backend breakdown this cutover follows.