Federated GraphQL Breakdown — Bill of Materials (BOM)

Target DGS: plm-product (co-located)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 36 | T-Shirt Size XL | Complexity 🔴 1 🟠 2 🟡 12 🟢 21 | Phases A, B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-product (co-located)   |   Generated: 2026-07-15

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

- We are moving the Bill of Materials (BOM) domain off the shared Node.js spark-internal-graphql gateway and into the `plm-product` Netflix DGS service, where it lives next to Product, Measurement, Impression and Packaging. - BOM is the structured record of every material, supplier and impression that makes up a product, and it is referenced by many sibling domains.

- BOM is mid-sized: 13 queries, 6 mutations, and ~46 field resolvers across 18 type blocks, on a 735-line resolver. - Its defining challenge is material polymorphism — 7 concrete material types (Trim, Wash, Fabric, FabricSpec, Combination, Packaging, plus the base) resolved by a category dispatcher, and 5 impression sub-types. - The single hardest piece of work is updateBom, a 3-step write (workspace → body → permissions) that today has no rollback.

- The schema is wide but shallow: the large majority of attributes are direct pass-throughs (cheap to migrate). - Risk concentrates in ~38 cross-domain field resolvers (material-library and color lookups) and the 2 polymorphic interfaces. - See [05-attribute-inventory.md](./05-attribute-inventory.md).

Note on ACL: the current gateway uses ACL to obtain a per-resource capability token. Per decision, Per the program-level working decision, the DGS layer carries no ACL plumbing story — each domain service performs its own access control; scenario ADRs (complexStories/*/02-adr-noacl-*.md) record the assumption's impact and ratify with the global decision. ACL is noted in stories for context only.

---

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 12 | 4 are cacheable master-data lookups. getBomDataV2 removed (Bom_Unified deprecated) |
| Mutations | 6 | 5 simple + updateBom (complex) |
| Field-resolver type blocks | 17 | one story each. BomMaterial_Unified removed; impression branch (G-10) rescoped, not removed |
| Material polymorphism | 7 types + interface + type resolver | B-01 |
| Impression polymorphism | 5 types + interface | B-01 |
| External dependencies | 12 loader keys (2 🔴 · 6 🟡 · 4 🔵) | sibling DGS + VMM platform |
| Federation contributions | 2 (Product extension, ResourcesCount.bomsCount) | BLOCKED-BY product |
| Total stories | 36 | green-field build stories. The 3 Phase-0 spike stubs are tracked as program spikes in the global breakdown and Jira, not as rows here (see global Phase 0) |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 BOM-BE-A-04 — @DgsTypeResolver for the 2 BOM interfaces | SPIKE-05 | Polymorphic Type Resolution |
| 🔴🔬 BOM-BE-B-05 — getBomMaterialTypes (merge with Material Hub) | SPIKE-06a | Hydration |
| 🔴🔬 BOM-BE-E-01 — updateBom — 3-step orchestrated write | SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20% buffer) | Ready when |
| --- | --- | --- | --- | --- |
| A | BOM material @DgsTypeResolver (1) | 1 | 2–3d |  |
| B | Core Reads | 7 | 7–12d | after B-01. (B-02 removed) |
| C | Search & Listing | 5 | 9–15d | after B-01 |
| D | Mutations (simple) | 5 | 5–10d | after B-01 |
| E | Complex (updateBom) | 1 | 6–10d | after B-01, D-02 · gated on SPIKE-01 |
| F | Federation Contributions | 2 | 4–7d | BLOCKED-BY product |
| G | Field Resolvers & Tests | 15 | 32–52d | after B-01. (G-02 removed, G-10 rescoped) |
| Total | — | 36 | 68–113d (buffered) | — |

ℹ️  One engineer ≈ 14–23 sprints (5d). Phases B/C/D/G parallelize heavily after B-01.

Capacity Planning

| Team size | Calendar (5d sprints) | Notes |
| --- | --- | --- |
| 1 engineer | ~15–25 sprints | sequential |
| 2 engineers | ~9–15 sprints | B/C/D + most of G parallel |
| 3 engineers | ~6–10 sprints | critical path A → E-01 → G-08/G-10 → G-16 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 0 | Program spikes | run in Sprint 0 (see global Phase 0 — Program Spikes) so E-01/rollout-order aren't waiting |
| 1 | B-01 (DGS module init + service wiring + first resolver) | schema, stubs, type resolvers, service port |
| 2 | B-01, B-03–B-08 + D-03/D-04 | reads (incl. 4 cacheable) + lock/unlock |
| 3 | C-01–C-05 + D-01/D-02/D-05 | search/supplier + simple mutations |
| 4 | E-01 | updateBom 3-step write (focused; needs SPIKE-01 concluded) |
| 5 | G-01, G-03–G-07 | entity + simple material field resolvers |
| 6 | G-08 + G-09 | trim (large) + wash |
| 7 | G-10–G-15 | impression branches + search-result enrichment + trivial bundle |
| 8 | G-16 | tests, parity harness, load test |
| post-launch | F-01, F-02 | federation contributions (unblocked by product) |

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

🧱 Phase A — Foundation & Type Resolvers  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔴🔬 🔸 BOM-BE-A-04 @DgsTypeResolver for the 2 BOM interfaces 🔴🔬 Spike-gated on SPIKE-05 (Polymorphic Type Resolution) | 🟡 Medium [M] | Field Resolver | SPIKE-05 | Intent — Route each material/impression row to the right concrete type by its category code. Today — - Material: switch on material.materialCategory.code → 4→Trim, 6→Wash, 2→Fabric, 15→Combination, 16→FabricSpec, {10,11,12,13,14,17–24}→Packaging, default… Done when: • Each materialCategory.code maps to the type in the table above; unknown codes → BomMaterial • Each impression type maps correctly; unknown → BomBaseImpressionDetails • BomConstants holds all 21 category codes + 5 impression codes (verify values against backend) |

📖 Phase B — Core Reads  (7 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 BOM-BE-B-01 getBomByIds data fetcher | 🟢 Low [XS] | Query | — | Intent — Looks up full BOM records for a set of BOM ids (the core 'give me these BOMs' read). Today — if ids empty → []; else GET … → camelCase. - ACL ignored in DGS Done when: • getBomByIds(["B1","B2"]) returns mapped Bom objects from the REST list endpoint • Empty ids → returns [] with no REST call • Response snake_case → camelCase per schema |
| 🔷 BOM-BE-B-03 getBomStatus (cacheable master data) | 🟢 Low [XS] | Query | — | Intent — Returns the list of possible BOM statuses — the options you'd see in a status dropdown. Today — GET …; transform {key:value} map → [{code,description}]. No ACL Done when: • Returns [{code,description}] from the status map • Second call served from cache (no REST) • Map key→code, value→description |
| 🔷 BOM-BE-B-04 getBomByParentId data fetcher | 🟢 Low [XS] | Query | — | Intent — Lists all the BOMs that belong to one product, newest first. Today — today, the gateway fetches boms for a product and sorts them by createdAt DESC itself, in application code — the backend returns them unsorted. ignored in DGS. -… Done when: • Returns boms for parentId sorted createdAt DESC, sorted by the backend, not client code • Empty → {content: []} • No sortedByDescending (or equivalent) remains in the Kotlin data fetcher — sorting happens once, server-side |
| 🔴🔬 🔷 BOM-BE-B-05 getBomMaterialTypes (merge with Material Hub) 🔴🔬 Spike-gated on SPIKE-06a (Hydration) | 🟡 Medium [M] | Query Calls: materialHub | SPIKE-06a | Intent — Returns the catalog of material types, combined with the shared material-hub types. Today — load bom material types (GET …/master_data/bom_material_types[?ids]) and materialHub.getHubMaterialTypes (today sequential), concat; map each hub type → {code:9… Done when: • Returns bom types + synthesized hub types • Hub rows carry code=9, libraryLink=true, freeText=true, bomType={1,'Product'} • The two fetches run concurrently • EXT hub failure → return bom types only (partial), logged |
| 🔷 BOM-BE-B-06 getBomPackagingMaterialTypes (cacheable) | 🟢 Low [XS] | Query | — | Intent — Returns the packaging material-type lookup list (cached, rarely changes). Today — GET …/master_data/packaging_bom_material_types → camelCase. No ACL Done when: • Returns packaging material types • Cached on second call |
| 🔷 BOM-BE-B-07 getBomPackagingSubstrates (cacheable) | 🟢 Low [XS] | Query | — | Intent — Returns the packaging substrate lookup list (cached). Today — GET …/master_data/packaging_bom_substrate_types → camelCase Done when: • Returns substrate list • Cached |
| 🔷 BOM-BE-B-08 getBomPackagingUnitOfMeasure (cacheable) | 🟢 Low [XS] | Query | — | Intent — Returns the packaging unit-of-measure lookup list (cached). Today — GET …/master_data/packaging_unit_of_measure → camelCase (units_of_measure) Done when: • Returns UoM list • Cached |

ℹ️  BOM-BE-B-01: Note — DGS Module Init (this PR only): Creates bom.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [03-schema.graphql](./03-schema.graphql). This scaffold is a prerequisite for every B/C/D/G story — they need the module + schema file to compile their DGS wrapper — so it is assumed globally (shown once in the dependency graph) and not repeated in each story's Depends On. After it lands, the wrappers parallelize.

🔍 Phase C — Search & Listing  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 BOM-BE-C-01 getBomElastic data fetcher | 🟢 Low [XS] | Query Calls: search | — | Intent — Runs a BOM search and returns the BOMs that match. Today — {content} = search.getBomElastic; return content. The entire query object is passed to elastic — document the exact field set. - EXT Service Calls: EXT → key: search ·… Done when: • Returns content boms for a query • Query DTO field set documented + matches backend • Empty → [] |
| 🔷 BOM-BE-C-02 searchMaterialsBom data fetcher | 🟡 Medium [M] | Query Calls: search, vmm | — | Intent — Searches for materials inside BOMs, with filters and paging. Today — in plain terms — before hitting the search backend, this resolver (1) looks up fabric suppliers by calling straight into another domain's resolver code (not a clean… Done when: • Returns BomMaterialSearch{content,paging} • With nestedSearchFilters, the request serializes to the same nestedSearchFilters[i].* keys as today (or the agreed structured DTO, once the search-request-shape decision has landed) • size defaults to 20 • Fabric-supplier prefetch via service/federation, not a resolver import |
| 🔷 BOM-BE-C-03 getComboSupplierForBom data fetcher | 🟡 Medium [M] | Query Calls: combination, vmm | — | Intent — Finds which suppliers are available for a BOM's combination materials. Today — fabricSpecCombos = SPARK_Combination.searchFabricSpecCombos({q:parentComboId:${comboId}, page:0, size:100}) (cross-resolver import). 2. Filter combos: keep where fsId… Done when: • Returns suppliers only for combos with a resolvable fsId and bpName • Filter logic matches the rule above (document the mvIds.length===1 behaviour) • VMM lookups run concurrently |
| 🔷 BOM-BE-C-04 getValidTrimSuppliersForBom data fetcher | 🟢 Low [XS] | Query Calls: vmm | — | Intent — Lists the valid trim suppliers for a BOM. Today — getRelatedSuppliersForMVs(ctx, merchVendorIds, [TRIM_SUPPLIER.code]) → [Int] partner ids. - EXT Service Calls: EXT → key: vmm · Done when: • Returns related trim-supplier partner ids • Role filter = TRIM_SUPPLIER only • Empty input → [] |
| 🔷 BOM-BE-C-05 getValidRawMaterialSuppliersForBom data fetcher | 🟢 Low [XS] | Query Calls: vmm | — | Intent — Lists the valid raw-material suppliers for a BOM. Today — same as C-04 with roles [RAW_MATERIAL_SUPPLIER, FABRIC_SUPPLIER, TRIM_SUPPLIER] Done when: • Returns ids matching the 3 roles • Empty input → [] |

✏️ Phase D — Mutations  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 BOM-BE-D-01 addBom mutation | 🟡 Medium [M] | Mutation | — | Intent — Creates a new BOM. Today — bom = bomService.addBom(sparkBom) → POST … (transformRequest: deepToSnakeCase, primeKey: humanId); if bom.validationErrors \¦\¦ bom.message → throw. No ACL (new… Done when: • POST creates a bom and returns it mapped to Bom • Backend validationErrors/message → BomValidationException (not a silent return) • Request body is snake_case • Read cache primed with humanId |
| 🔶 BOM-BE-D-02 manageBomWorkspaces mutation | 🟢 Low [XS] | Mutation Calls: workspaceV2 | — | Intent — Adds or removes which workspaces a BOM belongs to. Today — if toAdd/toRemove non-empty → workspaceAssociationHelper(BOM, bomId, toAdd, toRemove) → PUT …/{bomId}/{associate\¦dissociate}_workspace; else returns undefined. - EXT… Done when: • Adds/removes workspace associations via the correct endpoint • Both lists empty → null, no REST call • Returns the updated bom |
| 🔶 BOM-BE-D-03 lockBom mutation | 🟢 Low [XS] | Mutation | — | Intent — Locks a BOM so others can't edit it. Today — PUT …/{bomId}/lock. ignored in DGS Done when: • PUT to /lock returns the locked bom • 404 → null |
| 🔶 BOM-BE-D-04 unlockBom mutation | 🟢 Low [XS] | Mutation | — | Intent — Unlocks a BOM so it can be edited again. Today — PUT …/{bomId}/unlock Done when: • PUT to /unlock returns the unlocked bom • 404 → null |
| 🔶 BOM-BE-D-05 updateBomComponentStatus mutation | 🟢 Low [XS] | Mutation | — | Intent — Updates the status of one or more components on a BOM. Today — PUT …/bom/v1/component_status_update body {productId, ids, status}. No ACL token — the only write without one (every other BOM write obtains one) Done when: • PUT sends {productId, ids, status} (snake_case) • Returns BomPaged{content} |

⚙️ Phase E — Complex Operations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 BOM-BE-E-01 updateBom — 3-step orchestrated write 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🔴 Very High [XL] | Mutation Calls: workspaceV2 | SPIKE-01, D-02 | Intent — Edit a BOM — a 3-step write (workspace + body + permissions) that has no rollback today. Today — editing a bom today is really three separate backend calls made one - after another, with no undo button: (1) if the caller changed which workspaces the bom belongs… Done when: • Parity for 5 fixtures: body-only; body+workspace-add; body+workspace-remove; body+partners; body+workspace+partners • Workspace step runs before the body PUT; permissions step only when businessPartners present • Body PUT omits humanId from the body • Chosen failure strategy implemented; partial failure emits a compensation-log entry (if (b)/(c)) or compensates (if (a)) • Backend validationErrors/message → BomValidationException • Read cache updated with the returned bom | ☐ Unit: order workspace→body→perms ☐ Unit: no-workspace skip ☐ Unit: no-partners skip ☐ Unit: step-3 failure path (strategy) ☐ Parity: 5 fixtures |

🔗 Phase F — Federation & Stitching  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 BOM-BE-F-01 Implement Product.productBoms / boms / packagingBoms (internal) | 🟡 Medium [M] | Field Resolver | — | Intent — Serve a product's BOM lists from BOM's own service instead of product reaching across. Today — when a client asks a Product for its boms today, that resolver lives - in product's code and reaches across to BOM's data loader. - After migration, product and bom… Done when: • Product.productBoms/boms/packagingBoms resolve via bomService internally • the equivalent product-side resolvers are removed • boms(types) filters by bom type • no gateway hop |
| 🔸 BOM-BE-F-02 Fill ResourcesCount.bomsCount (internal) | 🟢 Low [XS] | Field Resolver Calls: search | — | Intent — Let BOM own the 'how many boms' count shown on the TechPack panel. Today — the TechPack summary panel shows "12 boms" for a product today by having product's orchestration code run an elastic count query. Once BOM owns this field, BOM's own… Done when: • bomsCount resolves internally on ResourcesCount • count matches current elastic semantics • no gateway hop for this field |

🧪 Phase G — Field Resolvers & Tests  (15 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 BOM-BE-G-01 Bom field resolvers (9 shared fields) | 🟡 Medium [M] | Field Resolver Calls: workspaceV2, tag | — | Intent — Resolve the 9 shared Bom fields (people, product, workspaces, partners, participants). Today — 9 fields — humanId, access, currentUserPermissions, businessPartners, createdBy, updatedBy, product, workspaces, participantDetails — that all need a little lookup… Done when: • All 9 fields resolve on Bom from one impl • product null when parentId not PID* (defensive guard; in practice always PID*, per the confirmed decision) • Sibling fields emit correct @keys for federation • No ACL plumbing introduced | — |
| 🔸 BOM-BE-G-03 BomMaterial field resolvers (8 fields) | 🟡 Medium [M] | Field Resolver Calls: materialHub, tag | — | Intent — Resolve the generic material row's fields (library lookup, origins, weight). Today — BomMaterial is the generic ("hub") material row. Two of its fields — - libraryResource and genericMaterialType — both need the same lookup from the Material Hub… Done when: • genericMaterialType returns hub value when relatedMaterialType differs from local, else local • origins/certifications filtered to known codes and enriched to {code,description} • weight uses UoM fallback code 23 (grams) • Hub fetched once per material | — |
| 🔸 BOM-BE-G-04 BomPackagingMaterial field resolvers (2 fields) | 🟢 Low [XS] | Field Resolver Calls: tag | — | Intent — Resolve a packaging material's impressions and country-of-origin. Today — impressionDetails (material.impressions), countryOfOrigin (tag) Done when: • impressionDetails = parent impressions • countryOfOrigin resolves from countryOfOriginIds (empty → []) | — |
| 🔸 BOM-BE-G-05 BomFabricMaterial field resolvers (4 fields) | 🟢 Low [XS] | Field Resolver Calls: search, tag, materialHub | — | Intent — Resolve a fabric material's spec/combo, weight and origin. Today — libraryResource = search.searchFabricSpecCombos({q:id:${fscId},page:0,size:1}) → content[0] ?? {id:fscId}; weight (H1), countryOfOrigin, impressionDetails… Done when: • Returns the matched fabricSpecCombo or {id} • weight/countryOfOrigin as G-03 | — |
| 🔸 BOM-BE-G-06 BomFabricSpecMaterial field resolvers (4 fields) | 🟢 Low [XS] | Field Resolver Calls: fabric, tag, materialHub | — | Intent — Resolve a fabric-spec material's fields. Today — libraryResource = fabric.getSpecificationByID ?? {id}; weight, countryOfOrigin, impressionDetails. - EXT: fabric, materialHub; tag Done when: • Returns fabric spec or {id} • weight/countryOfOrigin as G-03 | — |
| 🔸 BOM-BE-G-07 BomCombinationMaterial field resolvers (4 fields) | 🟢 Low [XS] | Field Resolver Calls: combination, tag, materialHub | — | Intent — Resolve a combination material's fields. Today — libraryResource = combination.getById ?? {id}; weight, countryOfOrigin Done when: • Returns combination or {id} • weight/countryOfOrigin as G-03 | — |
| 🔸 BOM-BE-G-08 BomTrimMaterial field resolvers (7 fields) — trim size dispatchers | 🟠 High [L] | Field Resolver Calls: trim, location, tag | — | Intent — Resolve a trim material's fields, including the per-trim-type size dispatch. Today — - libraryResource = trim.getTrimBatch. - materialLibraryUom = trim UoMs, find by materialLibraryUomId.toString() (preserve int→string coercion). - sizeValue = reload… Done when: • sizeValue matches getTrimSizeValue for all 15 trim types (parity table) incl. THREAD/LABEL subtype branches • sizeCaption returns the correct {edit,view} per type incl. compatible-size and finished-size cases • materialLibraryUom matches via string-coerced code • facilityName returns the pre-set value if present, else the resolved VMM facility name • Trim is fetched once per material (one REST call) | ☐ Unit: 15 trim-type sizeValue cases ☐ Unit: caption edit/view per type ☐ Unit: UoM string coercion ☐ Unit: facilityName pre-set vs resolved ☐ Unit: single trim fetch ☐ Parity: recorded trim fixtures |
| 🔸 BOM-BE-G-09 BomWashMaterial field resolvers (4 fields) | 🟢 Low [XS] | Field Resolver Calls: wash, tag, materialHub | — | Intent — Resolve a wash material's fields. Today — libraryResource = wash.getWash(jwt) ?? {id}; weight, countryOfOrigin, impressionDetails. ACL context: wash uses a capability token; ignore in impl Done when: • Returns wash or {id} • weight/countryOfOrigin as G-03 | — |
| 🔸 BOM-BE-G-10 Impression library-resource resolution (shared internal/external branch + MaterialDataLoader) | 🟠 High [L] | Field Resolver Calls: search | — | Intent — Resolve an impression's colour/library links, branching on internal vs external caller. Today — resolving "what material does this impression's color/library field - point to" needs to behave differently depending on who's asking. - An internal user gets the… Done when: • Internal path resolves libraryResource via material-by-id; external path via proxy-id search • bomIds come from DGS local context, not field args (the fragile args.ids contract is removed) • Missing libraryResource.id → null • 5 color fields resolve via batched material loader • G-11/G-12/G-13 call this shared service rather than re-implementing the branch | ☐ Unit: internal branch ☐ Unit: external branch (proxyIds) ☐ Unit: null id ☐ Unit: color batch ☐ Parity: internal vs external |
| 🔸 BOM-BE-G-11 BomFabricLibraryImpressionDetails.libraryResource | 🟡 Medium [M] | Field Resolver Calls: search | G-10 | Intent — Resolve this impression type's library link (shares G-10's branch). Today — single libraryResource field with the same internal/external branch as G-10 Done when: • Same behaviour as G-10's libraryResource for this type • Uses local-context bomIds | — |
| 🔸 BOM-BE-G-12 BomTrimLibraryImpressionDetails field resolvers (3 fields) | 🟡 Medium [M] | Field Resolver Calls: search | G-10 | Intent — Resolve this trim-impression's library link and two colours. Today — libraryResource (G-10 branch) + groundColor, textColor via searchMaterialById Done when: • libraryResource behaves as G-10 • groundColor/textColor resolve via material loader | — |
| 🔸 BOM-BE-G-13 BomTrimZipperLibraryImpressionDetails field resolvers (3 colors) | 🟢 Low [XS] | Field Resolver Calls: search | G-10 | Intent — Resolve a zipper impression's three colours. Today — sliderColor, tapeColor, teethColor via searchMaterialById. Unlike G-11/G-12, this type has no libraryResource field at all — just three colors — so it only needs… Done when: • Three color fields resolve by id • Missing id → null | — |
| 🔸 BOM-BE-G-14 Trivial pass-through fields (bundle) | 🟢 Low [XS] | Field Resolver | — | Intent — Resolve the trivial computed / pass-through fields (no service call). Today — the only allowed bundle — fields that return a parent value with no service call: BomMaterialType.id = ` ${code}_${description} (computed); BomMaterialSearch.paging =… Done when: • BomMaterialType.id = code_description • impressionDetails maps from impressions • libraryResourceId from nested id • No EXT calls | — |
| 🔸 BOM-BE-G-15 BomMaterialSearchResult field resolvers (5 fields) | 🟡 Medium [M] | Field Resolver Calls: fabric, search | C-02 | Intent — Resolve the material-search-result fields (tolerant of both response shapes). Today — description (description ?? name), status (status?.description ?? status), - fabricSpec (if type==='fabric_spec_combo' & fabricSpecId → fabric.getSpecificationByID)… Done when: • description/status handle both shapes • fabricSpec/fabric/fabricId gated by type • relatedMaterials buckets intentLineIds correctly • proxyIds not mutated (copy used) | — |
| 📄 BOM-BE-G-16 Test coverage & parity harness | 🟡 Medium [M] | Tests | E-01, G-08, G-10 | Intent — The safety net: automated tests + a parity harness that prove the new BOM DGS returns exactly what the old gateway did before we switch traffic. Today — ≥80% unit coverage on fetchers/services; a parity harness recording ≥30 Done when: • Unit coverage ≥80% • Parity harness covers all 7 material types + internal/external impression branch + updateBom 5 fixtures • Schema-conformance check fails the build if an impl misses an interface field | — |