Federated GraphQL Breakdown — Impression

Target DGS: plm-product (co-located)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 7 | T-Shirt Size XS | Complexity 🔴 0 🟠 0 🟡 2 🟢 5 | Phases B, D, F, G |
| --- | --- | --- | --- |

Target DGS: plm-product (co-located)   |   Generated: 2026-07-15

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

What Are We Building?

- We are moving the Impression domain (the product's printed/embellished artwork "impressions" and their per-partner counts) off the spark-internal-graphql gateway into the `plm-product` DGS. - It is the smallest and lowest-risk of the thirteen domains: 2 queries, 1 mutation, and 6 field resolvers across a 66-line resolver — no polymorphism, no orchestration. We recommend migrating it first as a team warm-up that proves the pipeline end-to-end.

- The only mild wrinkle is the counts query: today it returns the impressions list and a field resolver aggregates per-partner counts (re-fetching the product). - We recommend a cleaner typed result as a fast-follow, but the existing contract can be preserved exactly.

ACL note: the current code obtains a per-product capability token via ACL; Per the program-level working decision, the DGS layer carries no ACL plumbing story — each domain service performs its own access control; scenario ADRs (complexStories/*/02-adr-noacl-*.md) record the assumption's impact and ratify with the global decision. ACL is noted in stories for context only.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 2 | one reuses the other's REST call |
| Mutations | 1 | delete + update sets in one PUT |
| Field-resolver type blocks | 2 | Impression (5), ImpressionCount (1) |
| External dependencies | 4 keys (0 🔴 · 1 🟡 · 3 🔵) | workspace, VMM, user-profile |
| Federation contributions | 1 (Product extension) | BLOCKED-BY product |
| Total stories | 7 | green-field |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

No spike-gated stories in this domain.

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads (incl. DGS module init + ImpressionService wiring) | 2 | 4–6d |
| D | Mutations | 1 | 2–3d |
| F | Federation (Product) | 1 | 1–2d (BLOCKED-BY product) |
| G | Field Resolvers & Tests | 3 | 4–7d |
| Total | — | 7 | 11–18d (buffered) |

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~3–5 sprints | sequential |
| 2 engineers | ~2–3 sprints | reads + field resolvers parallel |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1 | B-01 + B-02 | B-01: DGS module init (schema/types/stubs/scalars) + ImpressionService wiring + searchImpressionsByProductId; B-02: counts query |
| 2 | D-01 + G-01 + G-02 | mutation + field resolvers + counts aggregation |
| 3 | G-03 | tests & parity |
| post-launch | F-01 | Product extension (unblocked by product) |

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 IMPRESSION-BE-B-01 searchImpressionsByProductId data fetcher | 🟢 Low [XS] | Query | — | Intent — Find a product's impressions (colour / artwork placements). Done when: • searchImpressionsByProductId(id) returns impressions list; empty product → [] • partnerIds and workspaceIds are forwarded as repeated query params (not CSV) • enableWorkspaceContextFiltering intent is documented in code (forwarded or intentionally ignored) • ./gradlew generateJava passes and DateTime round-trips ISO-8601. (One-time gate — verify once in this PR.) |
| 🔷 IMPRESSION-BE-B-02 getImpressionCountsByProductId data fetcher | 🟢 Low [XS] | Query | B-01 | Intent — Count a product's impressions. Done when: • Returns the impressions list as the ImpressionCount parent type • The contract decision (list-as-parent vs typed result) is recorded in story comments • Empty product → counts yields totalCount: 0 (verified by G-02) |

ℹ️  IMPRESSION-BE-B-01: Note — DGS Module Init (this PR only): Creates impression.graphqls (federation v2.3 header,
> scalar DateTime → Instant, owned types Impression @key(fields:"id"), ImpressionCount,
> CountsByBp, 3 inputs, @shareable CountsByBp, plus external stubs for VMM_BusinessPartner,
> Product, WorkspaceV2, UserProfileAttributes) + registers the scalar in ScalarConfig.kt +
> wires ImpressionClient (Feign, GET repeated params + PUT snake/camel) and ImpressionService
> (searchByProductId, update). Full type list: [03-schema.graphql](./03-schema.graphql).

✏️ Phase D — Mutations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 IMPRESSION-BE-D-01 updateImpressions mutation | 🟡 Medium [M] | Mutation | B-01 | Intent — Update a product's impressions. Done when: • PUT body includes both delete and update sets in snake_case • Response is mapped to camelCase and returned as List<Impression> • Backend validationErrors or message → typed ImpressionValidationException thrown (not a silent partial return) |

🔗 Phase F — Federation & Stitching  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 IMPRESSION-BE-F-01 Product.impressions / impressionCounts (internal field resolver) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Expose impressions and their counts on the Product type. Done when: • Product.impressions and Product.impressionCounts resolve in-process via impressionService • No HTTP call is made during resolution (verified by unit test mock) • Output matches the current product-side resolver (parity) |

🧪 Phase G — Field Resolvers & Tests  (3 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 IMPRESSION-BE-G-01 Impression field resolvers (5 fields) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Resolve the individual Impression fields. Done when: • businessPartners and owningBusinessPartner resolve correctly from partnerIds / owningPartnerId • workspaces returns [] when workspaceContext is empty; the workspace service is not called • createdBy / updatedBy: null id returns null — no exception thrown |
| 🔸 IMPRESSION-BE-G-02 ImpressionCount.counts aggregation | 🟡 Medium [M] | Field Resolver | B-01 | Intent — Aggregate the per-type impression counts. Done when: • One row per product partner containing the correct filtered impression count • Final row is always { bpType: 'totalCount', counts: <total impressions length> } • Empty impressions list or missing product → [{ bpType: 'totalCount', counts: 0 }] — no exception is propagated • Product is fetched in-process; no HTTP call is made |
| 🔸 IMPRESSION-BE-G-03 Test coverage & parity | 🟢 Low [XS] | Field Resolver | B-01, B-02, D-01, G-02 | Intent — Prove the impression logic matches the old gateway. Done when: • Unit test coverage ≥ 80% for all impression data fetchers • Parity tests are green for search, counts, and the update mutation • The counts error-fallback path is explicitly covered by a unit test |