Project Plan — Combined Backend + Frontend Story Order

🏷️ Tags: dgs-migration · project-plan — Generated: 2026-07-19 · One combined implementation sequence per domain: backend build steps from the story dependency graph, frontend cutovers slotted into the earliest step after their backend dependencies (reads flip before writes before sagas).

Staffing + calendar for the 1 BE + 1 FE team: see 01-implementation-plan-1BE-1FE.md (team size set in team_config.py). Day figures are AI-estimated nominal midpoints — confirm in refinement.

Domain order

| # | Domain | Why here | BE stories | FE stories |
| --- | --- | --- | --- | --- |
| 1 | Watchlist | Wave 1 pilot — smallest isolated surface; proves flag flip + rollback | 13 | 3 |
| 2 | Product Details | Wave 2 — small, isolated, no shared blockers | 12 | 3 |
| 3 | Measurement | Wave 2 — parallel with Product Details | 20 | 4 |
| 4 | Packaging | Wave 2 — parallel with the other wave-2 domains | 23 | 5 |
| 5 | BOM | Wave 3 — high complexity, search-gated list views | 37 | 7 |
| 6 | Claims | Wave 3 — first cross-subgraph cutover (spark-claims) | 20 | 4 |
| 7 | Product | Wave 4 — largest surface, incremental slices, orchestrated writes last | 69 | 12 |
| 8 | Impression | Wave 4 rider — flips with its partner domains (BOM / Product) | 7 | 2 |

Wave-2/3 domains parallelize across the team — the numbering is the flip order. Phase-0 spikes (SPIKE-01…07) run before/alongside step 1 of the first domains; E-phase stories are gated on their outcomes.

Watchlist

Wave 1 pilot — smallest isolated surface; proves flag flip + rollback · 13 BE + 3 FE stories · ≈ 31 BE + 8 FE nominal days · Owners: Backend BE-2 · Frontend FE-1. Stories in the same step are independent and parallelize; a FE story never starts before every BE story it depends on is delivered.

Roadmap

•  Backend (BE-2): B-01 → (11 in parallel: B-02 … G-03) → G-05

•  ↓ unlocks frontend after backend step 2

•  Frontend (FE-1): WATCHLIST-FE-001 → WATCHLIST-FE-002 → WATCHLIST-FE-003

| Step | 🛠️ Backend — build | 🖥️ Frontend — cutover | Gates / notes |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | — |
| 2 | 🟢 B-02, 🟢 B-03, 🟡 C-01, 🟡 D-01, 🟡 D-02, 🟠 E-01, 🟢 F-01, 🟢 F-02, 🟢 G-01, 🟡 G-02, 🟡 G-03 | — | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module) |
| 3 | 🟢 G-05 | 🟢 WATCHLIST-FE-001 | — |
| 4 | — | 🟢 WATCHLIST-FE-002 | — |
| 5 | — | 🟡 WATCHLIST-FE-003 | — |

Story sequence

One row per story in implementation order. Depends On/Blocks reference story ids + names (never order numbers). Every operation story also implicitly requires the B-01 module-init scaffold — not repeated per row. Parallelizable = Yes means other stories share its step.

| Order | Step | Story | Team · Owner | Depends On | Blocks | ∥ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 🟢 B-01 — getWatchlistByIds | Backend · BE-2 | None | every story in this domain (module scaffold) | No |
| 2 | 2 | 🟢 B-02 — getWatchlistReasons | Backend · BE-2 | B-01 — getWatchlistByIds | None | Yes |
| 3 | 2 | 🟢 B-03 — getWatchlistInspectionActions | Backend · BE-2 | B-01 — getWatchlistByIds | None | Yes |
| 4 | 2 | 🟡 C-01 — getWatchlistByFilter | Backend · BE-2 | B-01 — getWatchlistByIds | WATCHLIST-FE-001 | Yes |
| 5 | 2 | 🟡 D-01 — createWatchlistEntries | Backend · BE-2 | B-01 — getWatchlistByIds | WATCHLIST-FE-002 | Yes |
| 6 | 2 | 🟡 D-02 — cloneFilesForWatchlist | Backend · BE-2 | B-01 — getWatchlistByIds | WATCHLIST-FE-002 | Yes |
| 7 | 2 | 🟠 E-01 — updateWatchlistEntries | Backend · BE-2 | B-01 — getWatchlistByIds | WATCHLIST-FE-003 | Yes |
| 8 | 2 | 🟢 F-01 — Product.watchlists | Backend · BE-2 | B-01 — getWatchlistByIds | None | Yes |
| 9 | 2 | 🟢 F-02 — ResourcesCount.watchlists | Backend · BE-2 | B-01 — getWatchlistByIds | None | Yes |
| 10 | 2 | 🟢 G-01 — Computed flatteners | Backend · BE-2 | B-01 — getWatchlistByIds | None | Yes |
| 11 | 2 | 🟡 G-02 — createdBy + updatedBy + workspaces + pa… | Backend · BE-2 | B-01 — getWatchlistByIds | G-05 | Yes |
| 12 | 2 | 🟡 G-03 — attachments + product | Backend · BE-2 | B-01 — getWatchlistByIds | None | Yes |
| 13 | 3 | 🟢 G-05 — WatchlistPartner.partner entity referen… | Backend · BE-2 | G-02 — createdBy + updatedBy +… | None | Yes |
| 14 | 3 | 🟢 WATCHLIST-FE-001 — Migrate watchlist reads | Frontend · FE-1 | B-01 — getWatchlistByIds, C-01 — getWatchlistByFilter | None | Yes |
| 15 | 4 | 🟢 WATCHLIST-FE-002 — Migrate watchlist create and clone muta… | Frontend · FE-1 | D-01 — createWatchlistEntries, D-02 — cloneFilesForWatchlist | None | No |
| 16 | 5 | 🟡 WATCHLIST-FE-003 — Migrate updateWatchlistEntries saga han… | Frontend · FE-1 | E-01 — updateWatchlistEntries | None | No |

Backend critical path: B-01 → G-02 → G-05.

Frontend cutover flow: WATCHLIST-FE-001 → WATCHLIST-FE-002 → WATCHLIST-FE-003.

Domain done when: the last FE story is flipped and stable; BE F/G stories (federation stitches, field-resolver parity) may trail post-flip.

Product Details

Wave 2 — small, isolated, no shared blockers · 12 BE + 3 FE stories · ≈ 31 BE + 10 FE nominal days · Owners: Backend BE-2 · Frontend FE-1. Stories in the same step are independent and parallelize; a FE story never starts before every BE story it depends on is delivered.

Roadmap

•  Backend (BE-2): B-01 → (11 in parallel: C-01 … G-03)

•  ↓ unlocks frontend after backend step 1

•  Frontend (FE-1): PDTL-FE-001 → PDTL-FE-002 → PDTL-FE-003

| Step | 🛠️ Backend — build | 🖥️ Frontend — cutover | Gates / notes |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | — |
| 2 | 🟡 C-01, 🟡 D-01, 🟢 D-02, 🟢 D-03, 🟡 D-04, 🟢 D-05, 🟠 E-01, 🟢 F-01, 🟡 G-01, 🟡 G-02, 🟡 G-03 | 🟢 PDTL-FE-001 | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module) |
| 3 | — | 🟡 PDTL-FE-002 | — |
| 4 | — | 🟡 PDTL-FE-003 | — |

Story sequence

One row per story in implementation order. Depends On/Blocks reference story ids + names (never order numbers). Every operation story also implicitly requires the B-01 module-init scaffold — not repeated per row. Parallelizable = Yes means other stories share its step.

| Order | Step | Story | Team · Owner | Depends On | Blocks | ∥ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 🟢 B-01 — getProductDetailsById | Backend · BE-2 | None | every story in this domain (module scaffold) | No |
| 2 | 2 | 🟡 C-01 — getProductDetailsElastic | Backend · BE-2 | B-01 — getProductDetailsById | None | Yes |
| 3 | 2 | 🟡 D-01 — createProductDetailsSet | Backend · BE-2 | B-01 — getProductDetailsById | PDTL-FE-002 | Yes |
| 4 | 2 | 🟢 D-02 — updateProductDetailAccess | Backend · BE-2 | B-01 — getProductDetailsById | None | Yes |
| 5 | 2 | 🟢 D-03 — productDetailLockUnlock | Backend · BE-2 | B-01 — getProductDetailsById | PDTL-FE-002 | Yes |
| 6 | 2 | 🟡 D-04 — cloneFilesForProductDetails | Backend · BE-2 | B-01 — getProductDetailsById | PDTL-FE-002 | Yes |
| 7 | 2 | 🟢 D-05 — updateProductDetailComponentStatus | Backend · BE-2 | B-01 — getProductDetailsById | PDTL-FE-002 | Yes |
| 8 | 2 | 🟠 E-01 — updateProductDetailsSet | Backend · BE-2 | B-01 — getProductDetailsById | PDTL-FE-003 | Yes |
| 9 | 2 | 🟢 F-01 — Product.productDetails | Backend · BE-2 | B-01 — getProductDetailsById | None | Yes |
| 10 | 2 | 🟡 G-01 — access + currentUserPermissions + parti… | Backend · BE-2 | B-01 — getProductDetailsById | None | Yes |
| 11 | 2 | 🟡 G-02 — product + createdBy + updatedBy + busin… | Backend · BE-2 | B-01 — getProductDetailsById | None | Yes |
| 12 | 2 | 🟡 G-03 — attachment + item attachment/constructi… | Backend · BE-2 | B-01 — getProductDetailsById | None | Yes |
| 13 | 2 | 🟢 PDTL-FE-001 — Migrate product-details reads | Frontend · FE-1 | B-01 — getProductDetailsById | None | Yes |
| 14 | 3 | 🟡 PDTL-FE-002 — Migrate product-details simple mutations | Frontend · FE-1 | D-01 — createProductDetailsSet, D-03 — productDetailLockUnlock, D-04 — cloneFilesForProductDet…, D-05 — updateProductDetailComp… | None | No |
| 15 | 4 | 🟡 PDTL-FE-003 — Migrate updateProductDetailsSet saga ha… | Frontend · FE-1 | E-01 — updateProductDetailsSet | None | No |

Backend critical path: B-01 → C-01.

Frontend cutover flow: PDTL-FE-001 → PDTL-FE-002 → PDTL-FE-003.

Domain done when: the last FE story is flipped and stable; BE F/G stories (federation stitches, field-resolver parity) may trail post-flip.

Measurement

Wave 2 — parallel with Product Details · 20 BE + 4 FE stories · ≈ 42 BE + 16 FE nominal days · Owners: Backend BE-2 · Frontend FE-2. Stories in the same step are independent and parallelize; a FE story never starts before every BE story it depends on is delivered.

Roadmap

•  Backend (BE-2): B-01 → (18 in parallel: B-02 … H-01) → G-04

•  ↓ unlocks frontend after backend step 2

•  Frontend (FE-2): MST-FE-001 ‖ MST-FE-003 → MST-FE-002 → MST-FE-004

| Step | 🛠️ Backend — build | 🖥️ Frontend — cutover | Gates / notes |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | — |
| 2 | 🟢 B-02, 🟢 B-03, 🟢 B-04, 🟢 B-05, 🟡 C-01, 🟢 C-02, 🟡 D-01, 🟢 D-02, 🟢 D-03, 🟢 D-04, 🟢 D-05, 🟡 D-06, 🟢 D-07, 🟠 E-01, 🟡 F-01, 🟡 G-01, 🟢 G-02, 🟢 H-01 | — | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module)<br>H-01 → ⛔ BLOCKED-BY sample |
| 3 | 🟢 G-04 | 🟡 MST-FE-001, 🟢 MST-FE-003 | — |
| 4 | — | 🟡 MST-FE-002 | — |
| 5 | — | 🟡 MST-FE-004 | — |

Story sequence

One row per story in implementation order. Depends On/Blocks reference story ids + names (never order numbers). Every operation story also implicitly requires the B-01 module-init scaffold — not repeated per row. Parallelizable = Yes means other stories share its step.

| Order | Step | Story | Team · Owner | Depends On | Blocks | ∥ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 🟢 B-01 — getMeasurementByIds data fetcher | Backend · BE-2 | None | every story in this domain (module scaffold) | No |
| 2 | 2 | 🟢 B-02 — getUnitsOfMeasure | Backend · BE-2 | B-01 — getMeasurementByIds dat… | G-04, MST-FE-003 | Yes |
| 3 | 2 | 🟢 B-03 — getThicknessUnitsOfMeasure | Backend · BE-2 | B-01 — getMeasurementByIds dat… | MST-FE-003 | Yes |
| 4 | 2 | 🟢 B-04 — getMeasurementSetStatus | Backend · BE-2 | B-01 — getMeasurementByIds dat… | MST-FE-001 | Yes |
| 5 | 2 | 🟢 B-05 — getSampleMeasurement data fetcher | Backend · BE-2 | B-01 — getMeasurementByIds dat… | G-04 | Yes |
| 6 | 2 | 🟡 C-01 — getMeasurements data fetcher | Backend · BE-2 | B-01 — getMeasurementByIds dat… | MST-FE-002 | Yes |
| 7 | 2 | 🟢 C-02 — getMeasurementsElastic data fetcher | Backend · BE-2 | B-01 — getMeasurementByIds dat… | MST-FE-002 | Yes |
| 8 | 2 | 🟡 D-01 — addMeasurement mutation | Backend · BE-2 | B-01 — getMeasurementByIds dat… | None | Yes |
| 9 | 2 | 🟢 D-02 — updateMeasurementAccess mutation | Backend · BE-2 | B-01 — getMeasurementByIds dat… | None | Yes |
| 10 | 2 | 🟢 D-03 — lockMeasurementSet mutation | Backend · BE-2 | B-01 — getMeasurementByIds dat… | MST-FE-004 | Yes |
| 11 | 2 | 🟢 D-04 — unlockMeasurementSet mutation | Backend · BE-2 | B-01 — getMeasurementByIds dat… | MST-FE-004 | Yes |
| 12 | 2 | 🟢 D-05 — updateMeasurementComponentStatus mutati… | Backend · BE-2 | B-01 — getMeasurementByIds dat… | None | Yes |
| 13 | 2 | 🟡 D-06 — putSampleMeasurementSet mutation | Backend · BE-2 | B-01 — getMeasurementByIds dat… | MST-FE-004 | Yes |
| 14 | 2 | 🟢 D-07 — deleteSampleMeasurementSet mutation | Backend · BE-2 | B-01 — getMeasurementByIds dat… | MST-FE-004 | Yes |
| 15 | 2 | 🟠 E-01 — updateMeasurement — 2-step orchestrated… | Backend · BE-2 | B-01 — getMeasurementByIds dat… | None | Yes |
| 16 | 2 | 🟡 F-01 — Implement Product.measurementSets | Backend · BE-2 | B-01 — getMeasurementByIds dat… | None | Yes |
| 17 | 2 | 🟡 G-01 — Measurement field resolvers | Backend · BE-2 | B-01 — getMeasurementByIds dat… | None | Yes |
| 18 | 2 | 🟢 G-02 — SampleMeasurementSet field resolvers | Backend · BE-2 | B-01 — getMeasurementByIds dat… | None | Yes |
| 19 | 2 | 🟢 H-01 — Contribute sampleMeasurement to the Sam… | Backend · BE-2 | B-01 — getMeasurementByIds dat… | None | Yes |
| 20 | 3 | 🟢 G-04 — SampleMeasurementSet.sample forward ref… | Backend · BE-2 | B-02 — getUnitsOfMeasure, B-05 — getSampleMeasurement da… | None | Yes |
| 21 | 3 | 🟡 MST-FE-001 — Migrate measurement reads and retire hu… | Frontend · FE-2 | B-01 — getMeasurementByIds dat…, B-04 — getMeasurementSetStatus | None | Yes |
| 22 | 3 | 🟢 MST-FE-003 — Migrate measurement master-data reads | Frontend · FE-2 | B-02 — getUnitsOfMeasure, B-03 — getThicknessUnitsOfMeas… | None | Yes |
| 23 | 4 | 🟡 MST-FE-002 — Migrate measurement list/search reads | Frontend · FE-2 | C-01 — getMeasurements data fe…, C-02 — getMeasurementsElastic … | None | No |
| 24 | 5 | 🟡 MST-FE-004 — Migrate measurement mutations | Frontend · FE-2 | D-03 — lockMeasurementSet muta…, D-04 — unlockMeasurementSet mu…, D-06 — putSampleMeasurementSet…, D-07 — deleteSampleMeasurement… | None | No |

Backend critical path: B-01 → B-02 → G-04.

Frontend cutover flow: MST-FE-001 → MST-FE-003 → MST-FE-002 → MST-FE-004.

Domain done when: the last FE story is flipped and stable; BE F/G stories (federation stitches, field-resolver parity) may trail post-flip.

Packaging

Wave 2 — parallel with the other wave-2 domains · 23 BE + 5 FE stories · ≈ 54 BE + 27 FE nominal days · Owners: Backend BE-2 · Frontend FE-2. Stories in the same step are independent and parallelize; a FE story never starts before every BE story it depends on is delivered.

Roadmap

•  Backend (BE-2): B-01 → (22 in parallel: B-02 … G-05)

•  ↓ unlocks frontend after backend step 2

•  Frontend (FE-2): PKG-FE-001 ‖ PKG-FE-002 → PKG-FE-003 ‖ PKG-FE-004 → PKG-FE-005

| Step | 🛠️ Backend — build | 🖥️ Frontend — cutover | Gates / notes |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | — |
| 2 | 🟢 B-02, 🟢 B-03, 🟢 B-04, 🟢 B-05, 🟢 B-06, 🟡 C-01, 🟡 D-01, 🟢 D-02, 🟡 D-03, 🟡 D-04, 🟢 D-05, 🟢 D-06, 🟢 D-07, 🟡 D-08, 🟢 D-09, 🟠 E-01, 🟢 F-01, 🟡 G-01, 🟢 G-02, 🟡 G-03, 🟠 G-04, 🟡 G-05 | — | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module) |
| 3 | — | 🟡 PKG-FE-001, 🟢 PKG-FE-002 | — |
| 4 | — | 🟡 PKG-FE-003, 🟡 PKG-FE-004 | — |
| 5 | — | 🔴 PKG-FE-005 | — |

Story sequence

One row per story in implementation order. Depends On/Blocks reference story ids + names (never order numbers). Every operation story also implicitly requires the B-01 module-init scaffold — not repeated per row. Parallelizable = Yes means other stories share its step.

| Order | Step | Story | Team · Owner | Depends On | Blocks | ∥ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 🟢 B-01 — getPackagings | Backend · BE-2 | None | every story in this domain (module scaffold) | No |
| 2 | 2 | 🟢 B-02 — getPackagingById | Backend · BE-2 | B-01 — getPackagings | PKG-FE-001 | Yes |
| 3 | 2 | 🟢 B-03 — getDielines | Backend · BE-2 | B-01 — getPackagings | PKG-FE-003 | Yes |
| 4 | 2 | 🟢 B-04 — getPackagingFieldValuesByType | Backend · BE-2 | B-01 — getPackagings | PKG-FE-002 | Yes |
| 5 | 2 | 🟢 B-05 — getDielineEvaluationStatuses | Backend · BE-2 | B-01 — getPackagings | PKG-FE-003 | Yes |
| 6 | 2 | 🟢 B-06 — getCountries | Backend · BE-2 | B-01 — getPackagings | PKG-FE-002 | Yes |
| 7 | 2 | 🟡 C-01 — getPackagingElastic | Backend · BE-2 | B-01 — getPackagings | None | Yes |
| 8 | 2 | 🟡 D-01 — addPackaging | Backend · BE-2 | B-01 — getPackagings | PKG-FE-004 | Yes |
| 9 | 2 | 🟢 D-02 — evaluateDieline | Backend · BE-2 | B-01 — getPackagings | PKG-FE-003 | Yes |
| 10 | 2 | 🟡 D-03 — bulkAddPackagings | Backend · BE-2 | B-01 — getPackagings | PKG-FE-004 | Yes |
| 11 | 2 | 🟡 D-04 — bulkUpdatePackagings | Backend · BE-2 | B-01 — getPackagings | PKG-FE-004 | Yes |
| 12 | 2 | 🟢 D-05 — exportPackaging | Backend · BE-2 | B-01 — getPackagings | PKG-FE-004 | Yes |
| 13 | 2 | 🟢 D-06 — lockPackaging | Backend · BE-2 | B-01 — getPackagings | PKG-FE-004 | Yes |
| 14 | 2 | 🟢 D-07 — unlockPackaging | Backend · BE-2 | B-01 — getPackagings | PKG-FE-004 | Yes |
| 15 | 2 | 🟡 D-08 — cloneFilesForDielines | Backend · BE-2 | B-01 — getPackagings | None | Yes |
| 16 | 2 | 🟢 D-09 — updatePackagingComponentStatus | Backend · BE-2 | B-01 — getPackagings | PKG-FE-004 | Yes |
| 17 | 2 | 🟠 E-01 — updatePackaging | Backend · BE-2 | B-01 — getPackagings | PKG-FE-005 | Yes |
| 18 | 2 | 🟢 F-01 — Product packaging links | Backend · BE-2 | B-01 — getPackagings | None | Yes |
| 19 | 2 | 🟡 G-01 — access + businessPartner + participantD… | Backend · BE-2 | B-01 — getPackagings | None | Yes |
| 20 | 2 | 🟢 G-02 — createdBy + updatedBy + dielineEvaluato… | Backend · BE-2 | B-01 — getPackagings | None | Yes |
| 21 | 2 | 🟡 G-03 — product + workspaces + attachments | Backend · BE-2 | B-01 — getPackagings | None | Yes |
| 22 | 2 | 🟠 G-04 — suggestedRetailPriceByDPCI + waveDescri… | Backend · BE-2 | B-01 — getPackagings | None | Yes |
| 23 | 2 | 🟡 G-05 — Dieline + PrinterDieline + PackagingEle… | Backend · BE-2 | B-01 — getPackagings | None | Yes |
| 24 | 3 | 🟡 PKG-FE-001 — Migrate packaging reads | Frontend · FE-2 | B-01 — getPackagings, B-02 — getPackagingById | None | Yes |
| 25 | 3 | 🟢 PKG-FE-002 — Migrate packaging master-data reads and… | Frontend · FE-2 | B-04 — getPackagingFieldValues…, B-06 — getCountries | None | Yes |
| 26 | 4 | 🟡 PKG-FE-003 — Migrate dieline flows | Frontend · FE-2 | B-03 — getDielines, B-05 — getDielineEvaluationSta…, D-02 — evaluateDieline | None | Yes |
| 27 | 4 | 🟡 PKG-FE-004 — Migrate packaging simple mutations and … | Frontend · FE-2 | D-01 — addPackaging, D-03 — bulkAddPackagings, D-04 — bulkUpdatePackagings, D-05 — exportPackaging, D-06 — lockPackaging, D-07 — unlockPackaging, D-09 — updatePackagingComponen… | None | Yes |
| 28 | 5 | 🔴 PKG-FE-005 — Migrate updatePackaging saga handling a… | Frontend · FE-2 | E-01 — updatePackaging | None | No |

Backend critical path: B-01 → B-02.

Frontend cutover flow: PKG-FE-001 → PKG-FE-002 → PKG-FE-003 → PKG-FE-004 → PKG-FE-005.

Domain done when: the last FE story is flipped and stable; BE F/G stories (federation stitches, field-resolver parity) may trail post-flip.

BOM

Wave 3 — high complexity, search-gated list views · 37 BE + 7 FE stories · ≈ 91 BE + 38 FE nominal days · Owners: Backend BE-2 · Frontend FE-1. Stories in the same step are independent and parallelize; a FE story never starts before every BE story it depends on is delivered.

Roadmap

•  Backend (BE-2): B-01 → (29 in parallel: A-04 … G-14) → (7 in parallel: A-05 … G-17)

•  ↓ unlocks frontend after backend step 2

•  Frontend (FE-1): BOM-FE-001 ‖ BOM-FE-004 → BOM-FE-002 ‖ BOM-FE-005 → BOM-FE-007 → BOM-FE-003 ‖ BOM-FE-006

| Step | 🛠️ Backend — build | 🖥️ Frontend — cutover | Gates / notes |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | — |
| 2 | 🟡 A-04, 🟢 B-03, 🟢 B-04, 🟡 B-05, 🟢 B-06, 🟢 B-07, 🟢 B-08, 🟢 C-01, 🟡 C-02, 🟡 C-03, 🟢 C-04, 🟢 C-05, 🟡 D-01, 🟢 D-02, 🟢 D-03, 🟢 D-04, 🟢 D-05, 🟡 F-01, 🟢 F-02, 🟡 G-01, 🟡 G-03, 🟢 G-04, 🟢 G-05, 🟢 G-06, 🟢 G-07, 🟠 G-08, 🟢 G-09, 🟠 G-10, 🟢 G-14 | — | A-04 → 🔬 SPIKE-05<br>B-05 → 🔬 SPIKE-06a |
| 3 | 🟡 A-05, 🔴 E-01, 🟡 G-11, 🟡 G-12, 🟢 G-13, 🟡 G-15, 🟡 G-17 | 🔴 BOM-FE-001, 🟢 BOM-FE-004 | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module) |
| 4 | — | 🔴 BOM-FE-002, 🟡 BOM-FE-005 | — |
| 5 | — | 🟢 BOM-FE-007 | — |
| 6 | — | 🔴 BOM-FE-003, 🔴 BOM-FE-006 | — |

Story sequence

One row per story in implementation order. Depends On/Blocks reference story ids + names (never order numbers). Every operation story also implicitly requires the B-01 module-init scaffold — not repeated per row. Parallelizable = Yes means other stories share its step.

| Order | Step | Story | Team · Owner | Depends On | Blocks | ∥ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 🟢 B-01 — getBomByIds data fetcher | Backend · BE-2 | None | every story in this domain (module scaffold) | No |
| 2 | 2 | 🟡 A-04 — @DgsTypeResolver for the 2 BOM interfac… | Backend · BE-2 | None | A-05 | Yes |
| 3 | 2 | 🟢 B-03 — getBomStatus | Backend · BE-2 | None | BOM-FE-002 | Yes |
| 4 | 2 | 🟢 B-04 — getBomByParentId data fetcher | Backend · BE-2 | None | BOM-FE-002 | Yes |
| 5 | 2 | 🟡 B-05 — getBomMaterialTypes | Backend · BE-2 | None | BOM-FE-004 | Yes |
| 6 | 2 | 🟢 B-06 — getBomPackagingMaterialTypes | Backend · BE-2 | None | BOM-FE-004 | Yes |
| 7 | 2 | 🟢 B-07 — getBomPackagingSubstrates | Backend · BE-2 | None | BOM-FE-004 | Yes |
| 8 | 2 | 🟢 B-08 — getBomPackagingUnitOfMeasure | Backend · BE-2 | None | BOM-FE-004 | Yes |
| 9 | 2 | 🟢 C-01 — getBomElastic data fetcher | Backend · BE-2 | None | BOM-FE-003 | Yes |
| 10 | 2 | 🟡 C-02 — searchMaterialsBom data fetcher | Backend · BE-2 | None | G-15 | Yes |
| 11 | 2 | 🟡 C-03 — getComboSupplierForBom data fetcher | Backend · BE-2 | None | BOM-FE-005 | Yes |
| 12 | 2 | 🟢 C-04 — getValidTrimSuppliersForBom data fetcher | Backend · BE-2 | None | BOM-FE-005 | Yes |
| 13 | 2 | 🟢 C-05 — getValidRawMaterialSuppliersForBom data… | Backend · BE-2 | None | BOM-FE-005 | Yes |
| 14 | 2 | 🟡 D-01 — addBom mutation | Backend · BE-2 | None | BOM-FE-006 | Yes |
| 15 | 2 | 🟢 D-02 — manageBomWorkspaces mutation | Backend · BE-2 | None | E-01 | Yes |
| 16 | 2 | 🟢 D-03 — lockBom mutation | Backend · BE-2 | None | BOM-FE-006 | Yes |
| 17 | 2 | 🟢 D-04 — unlockBom mutation | Backend · BE-2 | None | BOM-FE-006 | Yes |
| 18 | 2 | 🟢 D-05 — updateBomComponentStatus mutation | Backend · BE-2 | None | BOM-FE-006 | Yes |
| 19 | 2 | 🟡 F-01 — Implement Product.productBoms / boms / … | Backend · BE-2 | None | None | Yes |
| 20 | 2 | 🟢 F-02 — Fill ResourcesCount.bomsCount | Backend · BE-2 | None | None | Yes |
| 21 | 2 | 🟡 G-01 — Bom field resolvers | Backend · BE-2 | None | G-17 | Yes |
| 22 | 2 | 🟡 G-03 — BomMaterial field resolvers | Backend · BE-2 | None | None | Yes |
| 23 | 2 | 🟢 G-04 — BomPackagingMaterial field resolvers | Backend · BE-2 | None | None | Yes |
| 24 | 2 | 🟢 G-05 — BomFabricMaterial field resolvers | Backend · BE-2 | None | None | Yes |
| 25 | 2 | 🟢 G-06 — BomFabricSpecMaterial field resolvers | Backend · BE-2 | None | None | Yes |
| 26 | 2 | 🟢 G-07 — BomCombinationMaterial field resolvers | Backend · BE-2 | None | None | Yes |
| 27 | 2 | 🟠 G-08 — BomTrimMaterial field resolvers — trim… | Backend · BE-2 | None | None | Yes |
| 28 | 2 | 🟢 G-09 — BomWashMaterial field resolvers | Backend · BE-2 | None | None | Yes |
| 29 | 2 | 🟠 G-10 — Impression library-resource resolution | Backend · BE-2 | None | G-11, G-12, G-13 | Yes |
| 30 | 2 | 🟢 G-14 — Trivial pass-through fields | Backend · BE-2 | None | None | Yes |
| 31 | 3 | 🟡 A-05 — Shared CI conformance gate + code → typ… | Backend · BE-2 | A-04 — @DgsTypeResolver for th… | None | Yes |
| 32 | 3 | 🔴 E-01 — updateBom — 3-step orchestrated write | Backend · BE-2 | D-02 — manageBomWorkspaces mut… | None | Yes |
| 33 | 3 | 🟡 G-11 — BomFabricLibraryImpressionDetails.libra… | Backend · BE-2 | G-10 — Impression library-reso… | None | Yes |
| 34 | 3 | 🟡 G-12 — BomTrimLibraryImpressionDetails field r… | Backend · BE-2 | G-10 — Impression library-reso… | None | Yes |
| 35 | 3 | 🟢 G-13 — BomTrimZipperLibraryImpressionDetails f… | Backend · BE-2 | G-10 — Impression library-reso… | None | Yes |
| 36 | 3 | 🟡 G-15 — BomMaterialSearchResult field resolvers | Backend · BE-2 | C-02 — searchMaterialsBom data… | None | Yes |
| 37 | 3 | 🟡 G-17 — supplier entity references on material … | Backend · BE-2 | G-01 — Bom field resolvers | BOM-FE-007 | Yes |
| 38 | 3 | 🔴 BOM-FE-001 — Statically expand BOM fragment factories | Frontend · FE-1 | None | BOM-FE-002 | Yes |
| 39 | 3 | 🟢 BOM-FE-004 — Migrate BOM master-data reads | Frontend · FE-1 | B-05 — getBomMaterialTypes, B-06 — getBomPackagingMaterial…, B-07 — getBomPackagingSubstrat…, B-08 — getBomPackagingUnitOfMe… | None | Yes |
| 40 | 4 | 🔴 BOM-FE-002 — Migrate BOM core reads | Frontend · FE-1 | B-01 — getBomByIds data fetcher, B-03 — getBomStatus, B-04 — getBomByParentId data f…, BOM-FE-001 — Statically expand BOM f… | BOM-FE-007 | Yes |
| 41 | 4 | 🟡 BOM-FE-005 — Migrate BOM supplier reads | Frontend · FE-1 | C-03 — getComboSupplierForBom …, C-04 — getValidTrimSuppliersFo…, C-05 — getValidRawMaterialSupp… | None | Yes |
| 42 | 5 | 🟢 BOM-FE-007 — Adopt BOM supplier entity references | Frontend · FE-1 | G-17 — supplier entity referen…, BOM-FE-002 — Migrate BOM core reads | None | No |
| 43 | 6 | 🔴 BOM-FE-003 — Migrate BOM search and elastic reads | Frontend · FE-1 | C-01 — getBomElastic data fetc…, BOM-BE-S-03 | None | Yes |
| 44 | 6 | 🔴 BOM-FE-006 — Migrate BOM mutations including updateB… | Frontend · FE-1 | D-01 — addBom mutation, D-03 — lockBom mutation, D-04 — unlockBom mutation, D-05 — updateBomComponentStatu…, BOM-BE-S-01 | None | Yes |

Backend critical path: B-01 → A-04 → A-05.

Frontend cutover flow: BOM-FE-001 → BOM-FE-004 → BOM-FE-002 → BOM-FE-005 → BOM-FE-007 → BOM-FE-003 → BOM-FE-006.

Domain done when: the last FE story is flipped and stable; BE F/G stories (federation stitches, field-resolver parity) may trail post-flip.

Claims

Wave 3 — first cross-subgraph cutover (spark-claims) · 20 BE + 4 FE stories · ≈ 50 BE + 22 FE nominal days · Owners: Backend BE-1 · Frontend FE-2. Stories in the same step are independent and parallelize; a FE story never starts before every BE story it depends on is delivered.

Roadmap

•  Backend (BE-1): B-01 → (18 in parallel: B-02 … H-02) → G-03

•  ↓ unlocks frontend after step 1 (no backend dependency)

•  Frontend (FE-2): CLAIM-FE-001 → CLAIM-FE-002 → CLAIM-FE-003 → CLAIM-FE-004

| Step | 🛠️ Backend — build | 🖥️ Frontend — cutover | Gates / notes |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | 🟡 CLAIM-FE-001 | — |
| 2 | 🟢 B-02, 🟢 B-03, 🟢 B-04, 🟢 B-05, 🟡 C-01, 🟡 C-02, 🟡 D-01, 🟡 D-02, 🟢 D-03, 🟢 D-04, 🟢 D-05, 🟠 E-01, 🟡 G-01, 🟡 G-02, 🟡 G-04, 🟢 G-06, 🟡 H-01, 🟢 H-02 | — | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module)<br>H-01 → ⛔ BLOCKED-BY product<br>H-02 → ⛔ BLOCKED-BY product |
| 3 | 🟠 G-03 | 🔴 CLAIM-FE-002 | — |
| 4 | — | 🟡 CLAIM-FE-003 | — |
| 5 | — | 🔴 CLAIM-FE-004 | — |

Story sequence

One row per story in implementation order. Depends On/Blocks reference story ids + names (never order numbers). Every operation story also implicitly requires the B-01 module-init scaffold — not repeated per row. Parallelizable = Yes means other stories share its step.

| Order | Step | Story | Team · Owner | Depends On | Blocks | ∥ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 🟢 B-01 — getClaims | Backend · BE-1 | None | every story in this domain (module scaffold) | Yes |
| 2 | 1 | 🟡 CLAIM-FE-001 — Split the claim fragment factory and re… | Frontend · FE-2 | None | CLAIM-FE-002 | Yes |
| 3 | 2 | 🟢 B-02 — getClaimByIds | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-002 | Yes |
| 4 | 2 | 🟢 B-03 — getCommunicationChannels | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-002 | Yes |
| 5 | 2 | 🟢 B-04 — getAllClaimsAbout | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-002 | Yes |
| 6 | 2 | 🟢 B-05 — getClaimExports | Backend · BE-1 | B-01 — getClaims | None | Yes |
| 7 | 2 | 🟡 C-01 — searchGuestFacing | Backend · BE-1 | B-01 — getClaims | None | Yes |
| 8 | 2 | 🟡 C-02 — getClaimsElastic | Backend · BE-1 | B-01 — getClaims | None | Yes |
| 9 | 2 | 🟡 D-01 — createClaim | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-003 | Yes |
| 10 | 2 | 🟡 D-02 — bulkUpdateClaim | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-003 | Yes |
| 11 | 2 | 🟢 D-03 — requestClaimExport | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-003 | Yes |
| 12 | 2 | 🟢 D-04 — lockClaim | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-003 | Yes |
| 13 | 2 | 🟢 D-05 — unlockClaim | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-003 | Yes |
| 14 | 2 | 🟠 E-01 — updateClaim | Backend · BE-1 | B-01 — getClaims | CLAIM-FE-004 | Yes |
| 15 | 2 | 🟡 G-01 — access + currentUserPermissions + parti… | Backend · BE-1 | B-01 — getClaims | None | Yes |
| 16 | 2 | 🟡 G-02 — createdBy + updatedBy + businessPartner… | Backend · BE-1 | B-01 — getClaims | None | Yes |
| 17 | 2 | 🟡 G-04 — workspaces + ClaimSubstantiate.substant… | Backend · BE-1 | B-01 — getClaims | None | Yes |
| 18 | 2 | 🟢 G-06 — Shared value-type alignment | Backend · BE-1 | B-01 — getClaims | G-03 | Yes |
| 19 | 2 | 🟡 H-01 — Product.claims | Backend · BE-1 | B-01 — getClaims | None | Yes |
| 20 | 2 | 🟢 H-02 — ResourcesCount.claims | Backend · BE-1 | B-01 — getClaims | None | Yes |
| 21 | 3 | 🟠 G-03 — product + parentDetails | Backend · BE-1 | B-01 — getClaims, G-06 — Shared value-type align… | None | Yes |
| 22 | 3 | 🔴 CLAIM-FE-002 — Migrate claim reads | Frontend · FE-2 | B-01 — getClaims, B-02 — getClaimByIds, B-03 — getCommunicationChannels, B-04 — getAllClaimsAbout, CLAIM-FE-001 — Split the claim fragmen…, PRODUCT-BE-H-06 | None | Yes |
| 23 | 4 | 🟡 CLAIM-FE-003 — Migrate claim simple mutations and expo… | Frontend · FE-2 | D-01 — createClaim, D-02 — bulkUpdateClaim, D-03 — requestClaimExport, D-04 — lockClaim, D-05 — unlockClaim | None | No |
| 24 | 5 | 🔴 CLAIM-FE-004 — Migrate updateClaim multi-step write ha… | Frontend · FE-2 | E-01 — updateClaim | None | No |

Backend critical path: B-01 → G-06 → G-03.

Frontend cutover flow: CLAIM-FE-001 → CLAIM-FE-002 → CLAIM-FE-003 → CLAIM-FE-004.

Domain done when: the last FE story is flipped and stable; BE F/G stories (federation stitches, field-resolver parity) may trail post-flip.

Product

Wave 4 — largest surface, incremental slices, orchestrated writes last · 69 BE + 12 FE stories · ≈ 200 BE + 84 FE nominal days · Owners: Backend BE-1 · Frontend FE-1 + FE-2. Stories in the same step are independent and parallelize; a FE story never starts before every BE story it depends on is delivered.

Roadmap

•  Backend (BE-1): B-01 → (51 in parallel: B-02 … H-06) → (14 in parallel: E-01 … H-05) → F-09 ‖ F-11 ‖ F-12

•  ↓ unlocks frontend after backend step 2

•  Frontend (FE-1 + FE-2): PRODUCT-FE-001 ‖ PRODUCT-FE-004 → PRODUCT-FE-002 ‖ PRODUCT-FE-005 → PRODUCT-FE-006 ‖ PRODUCT-FE-007 ‖ PRODUCT-FE-008 → PRODUCT-FE-010 ‖ PRODUCT-FE-011 ‖ PRODUCT-FE-012 → PRODUCT-FE-003 ‖ PRODUCT-FE-009

| Step | 🛠️ Backend — build | 🖥️ Frontend — cutover | Gates / notes |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | — |
| 2 | 🟢 B-02, 🟢 B-03, 🟢 B-04, 🟢 B-05, 🟢 B-06, 🟢 B-07, 🟢 B-08, 🟢 B-09, 🟢 B-10, 🟢 B-11, 🟠 C-01, 🟡 C-02, 🟡 C-03, 🟡 C-04, 🟡 C-05, 🟡 D-01, 🟡 D-02, 🟡 D-03, 🟡 D-04, 🟡 D-05, 🟢 D-06, 🟢 D-07, 🟢 D-08, 🟢 D-09, 🟢 D-10, 🟢 D-11, 🟢 D-12, 🟢 D-13, 🟢 D-14, 🟢 D-15, 🟢 D-16, 🟢 D-17, 🟢 D-18, 🟠 E-00, 🔴 E-03, 🟢 F-14, 🔴 G-01, 🔴 G-02, 🟡 G-04, 🟡 G-05, 🟡 G-06, 🟡 G-07, 🟡 G-08, 🟡 G-09, 🟡 G-10, 🟡 G-11-1, 🟡 G-11-2, 🟡 G-13, 🟢 G-14, 🟡 G-15, 🟡 H-06 | — | C-01 → 🔬 SPIKE-06a<br>D-01 → 🔬 SPIKE-06b<br>D-02 → 🔬 SPIKE-06b<br>D-04 → 🔬 SPIKE-06b<br>E-00 → 🔬 SPIKE-01<br>E-03 → 🔬 SPIKE-02<br>G-07 → 🔬 SPIKE-04<br>G-11-1 → 🔬 SPIKE-04 |
| 3 | 🔴 E-01, 🟠 E-02, 🔴 E-04, 🟢 F-04, 🟢 F-06, 🟢 F-08, 🟢 F-10, 🟠 G-03, 🟡 G-17, 🟡 H-01, 🟡 H-02, 🟡 H-03, 🟡 H-04, 🟡 H-05 | 🔴 PRODUCT-FE-001, 🟡 PRODUCT-FE-004 | E-01 → 🔬 SPIKE-03<br>E-02 → 🔬 SPIKE-01<br>E-04 → 🔬 SPIKE-02<br>H-01 → ⛔ BLOCKED-BY attachment domain (⛔ cross-subgraph — does not ship until plm-attachment is live)<br>H-02 → ⛔ BLOCKED-BY discussion domain (⛔ cross-subgraph)<br>H-03 → ⛔ BLOCKED-BY sample domain (⛔ cross-subgraph)<br>H-04 → ⛔ BLOCKED-BY claim domain (⛔ cross-subgraph)<br>H-05 → ⛔ BLOCKED-BY construction domain (⛔ cross-subgraph) |
| 4 | 🟢 F-09, 🟢 F-11, 🟢 F-12 | 🟡 PRODUCT-FE-002, 🟡 PRODUCT-FE-005 | — |
| 5 | — | 🟡 PRODUCT-FE-006, 🟡 PRODUCT-FE-007, 🟡 PRODUCT-FE-008 | — |
| 6 | — | 🟡 PRODUCT-FE-010, 🟡 PRODUCT-FE-011, 🟡 PRODUCT-FE-012 | — |
| 7 | — | 🔴 PRODUCT-FE-003, 🔴 PRODUCT-FE-009 | — |

Story sequence

One row per story in implementation order. Depends On/Blocks reference story ids + names (never order numbers). Every operation story also implicitly requires the B-01 module-init scaffold — not repeated per row. Parallelizable = Yes means other stories share its step.

| Order | Step | Story | Team · Owner | Depends On | Blocks | ∥ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 🟢 B-01 — getProduct | Backend · BE-1 | None | every story in this domain (module scaffold) | No |
| 2 | 2 | 🟢 B-02 — getProductsByIds | Backend · BE-1 | None | PRODUCT-FE-003 | Yes |
| 3 | 2 | 🟢 B-03 — getProductStatus | Backend · BE-1 | None | PRODUCT-FE-004 | Yes |
| 4 | 2 | 🟢 B-04 — getProductVersions | Backend · BE-1 | None | PRODUCT-FE-002 | Yes |
| 5 | 2 | 🟢 B-05 — getCopyStatus | Backend · BE-1 | None | None | Yes |
| 6 | 2 | 🟢 B-06 — getProductTemplateById | Backend · BE-1 | None | None | Yes |
| 7 | 2 | 🟢 B-07 — getProductRules | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 8 | 2 | 🟢 B-08 — getProductRulesById | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 9 | 2 | 🟢 B-09 — getAllAvailableRules | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 10 | 2 | 🟢 B-10 — getProductDeptRules | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 11 | 2 | 🟢 B-11 — getProductBPRules | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 12 | 2 | 🟠 C-01 — getProducts two-stage hydration | Backend · BE-1 | None | None | Yes |
| 13 | 2 | 🟡 C-02 — getProductTemplates | Backend · BE-1 | None | PRODUCT-FE-005 | Yes |
| 14 | 2 | 🟡 C-03 — getCategories | Backend · BE-1 | None | PRODUCT-FE-005 | Yes |
| 15 | 2 | 🟡 C-04 — getRatingByTcin | Backend · BE-1 | None | None | Yes |
| 16 | 2 | 🟡 C-05 — searchProductRules | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 17 | 2 | 🟡 D-01 — addProduct | Backend · BE-1 | None | PRODUCT-FE-007 | Yes |
| 18 | 2 | 🟡 D-02 — addProducts | Backend · BE-1 | None | PRODUCT-FE-007 | Yes |
| 19 | 2 | 🟡 D-03 — bulkUpdateProducts | Backend · BE-1 | None | PRODUCT-FE-007 | Yes |
| 20 | 2 | 🟡 D-04 — updateProduct | Backend · BE-1 | None | PRODUCT-FE-007 | Yes |
| 21 | 2 | 🟡 D-05 — carryForwardProduct | Backend · BE-1 | None | PRODUCT-FE-007 | Yes |
| 22 | 2 | 🟢 D-06 — addTeamsToProduct 🔀 Collab Canvas | Backend · BE-1 | None | PRODUCT-FE-008 | Yes |
| 23 | 2 | 🟢 D-07 — addBusinessPartnersToProductWithType 🔀 … | Backend · BE-1 | None | PRODUCT-FE-008 | Yes |
| 24 | 2 | 🟢 D-08 — removeProductResources | Backend · BE-1 | None | None | Yes |
| 25 | 2 | 🟢 D-09 — updateBusinessPartnerStatuses | Backend · BE-1 | None | PRODUCT-FE-009 | Yes |
| 26 | 2 | 🟢 D-10 — updateViewToggle | Backend · BE-1 | None | PRODUCT-FE-007 | Yes |
| 27 | 2 | 🟢 D-11 — updateWorkspaceAttributes 🔀 Collab Canv… | Backend · BE-1 | None | None | Yes |
| 28 | 2 | 🟢 D-12 — updateProductTeamsWorkspaceContext | Backend · BE-1 | None | PRODUCT-FE-008 | Yes |
| 29 | 2 | 🟢 D-13 — linkProduct | Backend · BE-1 | None | PRODUCT-FE-007 | Yes |
| 30 | 2 | 🟢 D-14 — unlinkProduct | Backend · BE-1 | None | PRODUCT-FE-007 | Yes |
| 31 | 2 | 🟢 D-15 — addProductRule | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 32 | 2 | 🟢 D-16 — updateProductRule | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 33 | 2 | 🟢 D-17 — deleteProductRule | Backend · BE-1 | None | PRODUCT-FE-006 | Yes |
| 34 | 2 | 🟢 D-18 — updateComponentStatus | Backend · BE-1 | None | PRODUCT-FE-011 | Yes |
| 35 | 2 | 🟠 E-00 — WriteSaga shared module | Backend · BE-1 | None | E-01, E-02 | Yes |
| 36 | 2 | 🔴 E-03 — getProductTechPackCountV1 stub + aggreg… | Backend · BE-1 | None | 10 stories: E-04, F-04, F-06, F-08, H-01, H-02 … | Yes |
| 37 | 2 | 🟢 F-14 — Cross-subgraph contract alignment | Backend · BE-1 | None | F-10, PRODUCT-FE-012 | Yes |
| 38 | 2 | 🔴 G-01 — Product.attachmentsWithMetaData | Backend · BE-1 | None | G-03, G-17 | Yes |
| 39 | 2 | 🔴 G-02 — Product.components | Backend · BE-1 | None | None | Yes |
| 40 | 2 | 🟡 G-04 — ProductsCategories.categories + Dopple… | Backend · BE-1 | None | None | Yes |
| 41 | 2 | 🟡 G-05 — Product.samples + sampleIds + elasticSa… | Backend · BE-1 | None | None | Yes |
| 42 | 2 | 🟡 G-06 — Product.teams + discussionsV2 + discuss… | Backend · BE-1 | None | None | Yes |
| 43 | 2 | 🟡 G-07 — Product.vendorAttributes + businessPart… | Backend · BE-1 | None | None | Yes |
| 44 | 2 | 🟡 G-08 — Product.measurementSets + claims + bom … | Backend · BE-1 | None | None | Yes |
| 45 | 2 | 🟡 G-09 — Product.productWorkspaceAttributes + pr… | Backend · BE-1 | None | None | Yes |
| 46 | 2 | 🟡 G-10 — Product.ancestryProducts + rating + res… | Backend · BE-1 | None | None | Yes |
| 47 | 2 | 🟡 G-11-1 — Product.notRemovablePartnerIds + notRem… | Backend · BE-1 | None | None | Yes |
| 48 | 2 | 🟡 G-11-2 — Product.associateProductsAsks + Product… | Backend · BE-1 | None | None | Yes |
| 49 | 2 | 🟡 G-13 — IG/tag/tcin/spg + template trivial-fiel… | Backend · BE-1 | None | None | Yes |
| 50 | 2 | 🟢 G-14 — Simple user/status fields + trivial pas… | Backend · BE-1 | None | None | Yes |
| 51 | 2 | 🟡 G-15 — Port product utils to Kotlin | Backend · BE-1 | None | None | Yes |
| 52 | 2 | 🟡 H-06 — Product entity fetcher for cross-subgr… | Backend · BE-1 | B-01 — getProduct | F-10 | Yes |
| 53 | 3 | 🔴 E-01 — productBusinessPartnerActions | Backend · BE-1 | E-00 — WriteSaga shared module | F-12 | Yes |
| 54 | 3 | 🟠 E-02 — updateComponentStatuses | Backend · BE-1 | E-00 — WriteSaga shared module | PRODUCT-FE-011 | Yes |
| 55 | 3 | 🔴 E-04 — getProductTechPackBulkCountV1 | Backend · BE-1 | E-03 — getProductTechPackCount… | PRODUCT-FE-010 | Yes |
| 56 | 3 | 🟢 F-04 — ResourcesCount.measurementSets | Backend · BE-1 | E-03 — getProductTechPackCount… | F-09 | Yes |
| 57 | 3 | 🟢 F-06 — ResourcesCount.productBoms + packagingB… | Backend · BE-1 | E-03 — getProductTechPackCount… | F-09 | Yes |
| 58 | 3 | 🟢 F-08 — ResourcesCount.watchlists | Backend · BE-1 | E-03 — getProductTechPackCount… | F-09 | Yes |
| 59 | 3 | 🟢 F-10 — Hive Gateway supergraph composition | Backend · BE-1 | H-06 — Product entity fetcher …, F-14 — Cross-subgraph contract… | F-11 | Yes |
| 60 | 3 | 🟠 G-03 — Product.attachments + attachmentsV3 + a… | Backend · BE-1 | G-01 — Product.attachmentsWith… | None | Yes |
| 61 | 3 | 🟡 G-17 — Entity references on partner/lineage va… | Backend · BE-1 | G-01 — Product.attachmentsWith… | None | Yes |
| 62 | 3 | 🟡 H-01 — ResourcesCount.productAttachments + dis… | Backend · BE-1 | E-03 — getProductTechPackCount… | F-09, PRODUCT-FE-010 | Yes |
| 63 | 3 | 🟡 H-02 — ResourcesCount.discussions | Backend · BE-1 | E-03 — getProductTechPackCount… | F-09, PRODUCT-FE-010 | Yes |
| 64 | 3 | 🟡 H-03 — ResourcesCount.sample | Backend · BE-1 | E-03 — getProductTechPackCount… | F-09, PRODUCT-FE-010 | Yes |
| 65 | 3 | 🟡 H-04 — ResourcesCount.claims | Backend · BE-1 | E-03 — getProductTechPackCount… | F-09, PRODUCT-FE-010 | Yes |
| 66 | 3 | 🟡 H-05 — ResourcesCount.constructions | Backend · BE-1 | E-03 — getProductTechPackCount… | F-09, PRODUCT-FE-010 | Yes |
| 67 | 3 | 🔴 PRODUCT-FE-001 — Migrate getProduct documents in product… | Frontend · FE-1 + FE-2 | B-01 — getProduct | PRODUCT-FE-002, PRODUCT-FE-008 | Yes |
| 68 | 3 | 🟡 PRODUCT-FE-004 — Migrate product status and workspace-co… | Frontend · FE-1 + FE-2 | B-03 — getProductStatus | None | Yes |
| 69 | 4 | 🟢 F-09 — Retire the TechPack aggregation facade | Backend · BE-1 | H-01 — ResourcesCount.productA…, H-02 — ResourcesCount.discussi…, H-03 — ResourcesCount.sample, F-04 — ResourcesCount.measurem…, H-04 — ResourcesCount.claims, F-06 — ResourcesCount.productB…, H-05 — ResourcesCount.construc…, F-08 — ResourcesCount.watchlis… | None | Yes |
| 70 | 4 | 🟢 F-11 — Platform stub verification | Backend · BE-1 | F-10 — Hive Gateway supergraph… | None | Yes |
| 71 | 4 | 🟢 F-12 — Deferred partner-wrapper decision | Backend · BE-1 | E-01 — productBusinessPartnerA… | None | Yes |
| 72 | 4 | 🟡 PRODUCT-FE-002 — Migrate shared-library getProduct consu… | Frontend · FE-1 + FE-2 | B-01 — getProduct, B-04 — getProductVersions, PRODUCT-FE-001 — Migrate getProduct docu… | None | Yes |
| 73 | 4 | 🟡 PRODUCT-FE-005 — Migrate template library and categories… | Frontend · FE-1 + FE-2 | C-02 — getProductTemplates, C-03 — getCategories | None | Yes |
| 74 | 5 | 🟡 PRODUCT-FE-006 — Migrate product rules administration | Frontend · FE-1 + FE-2 | B-07 — getProductRules, B-08 — getProductRulesById, B-09 — getAllAvailableRules, B-10 — getProductDeptRules, B-11 — getProductBPRules, C-05 — searchProductRules, D-15 — addProductRule, D-16 — updateProductRule, D-17 — deleteProductRule | None | Yes |
| 75 | 5 | 🟡 PRODUCT-FE-007 — Migrate simple product mutations | Frontend · FE-1 + FE-2 | D-01 — addProduct, D-02 — addProducts, D-03 — bulkUpdateProducts, D-04 — updateProduct, D-05 — carryForwardProduct, D-10 — updateViewToggle, D-13 — linkProduct, D-14 — unlinkProduct | None | Yes |
| 76 | 5 | 🟡 PRODUCT-FE-008 — Migrate team and partner assignment mut… | Frontend · FE-1 + FE-2 | D-06 — addTeamsToProduct 🔀 Col…, D-07 — addBusinessPartnersToPr…, D-12 — updateProductTeamsWorks…, PRODUCT-FE-001 — Migrate getProduct docu… | None | Yes |
| 77 | 6 | 🟡 PRODUCT-FE-010 — Migrate TechPack count queries | Frontend · FE-1 + FE-2 | E-03 — getProductTechPackCount…, E-04 — getProductTechPackBulkC…, H-01 — ResourcesCount.productA…, H-02 — ResourcesCount.discussi…, H-03 — ResourcesCount.sample, H-04 — ResourcesCount.claims, H-05 — ResourcesCount.construc… | None | Yes |
| 78 | 6 | 🟡 PRODUCT-FE-011 — Migrate component status rollups | Frontend · FE-1 + FE-2 | B-01 — getProduct, D-18 — updateComponentStatus, E-02 — updateComponentStatuses | None | Yes |
| 79 | 6 | 🟡 PRODUCT-FE-012 — Verify fragment type-conditions, __type… | Frontend · FE-1 + FE-2 | F-14 — Cross-subgraph contract… | None | Yes |
| 80 | 7 | 🔴 PRODUCT-FE-003 — Migrate product list and bulk reads | Frontend · FE-1 + FE-2 | PRODUCT-BE-S-02, B-02 — getProductsByIds | None | Yes |
| 81 | 7 | 🔴 PRODUCT-FE-009 — Migrate partner drop/undrop orchestrati… | Frontend · FE-1 + FE-2 | PRODUCT-BE-S-03, D-09 — updateBusinessPartnerSt… | None | Yes |

Backend critical path: B-01 → E-03 → F-04 → F-09.

Frontend cutover flow: PRODUCT-FE-001 → PRODUCT-FE-004 → PRODUCT-FE-002 → PRODUCT-FE-005 → PRODUCT-FE-006 → PRODUCT-FE-007 → PRODUCT-FE-008 → PRODUCT-FE-010 → PRODUCT-FE-011 → PRODUCT-FE-012 → PRODUCT-FE-003 → PRODUCT-FE-009.

Domain done when: the last FE story is flipped and stable; BE F/G stories (federation stitches, field-resolver parity) may trail post-flip.

Impression

Wave 4 rider — flips with its partner domains (BOM / Product) · 7 BE + 2 FE stories · ≈ 14 BE + 4 FE nominal days · Owners: Backend BE-1 · Frontend FE-2. Stories in the same step are independent and parallelize; a FE story never starts before every BE story it depends on is delivered.

Roadmap

•  Backend (BE-1): B-01 → (6 in parallel: B-02 … G-04)

•  ↓ unlocks frontend after backend step 1

•  Frontend (FE-2): IMPRESSION-FE-001 ‖ IMPRESSION-FE-002

| Step | 🛠️ Backend — build | 🖥️ Frontend — cutover | Gates / notes |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | — |
| 2 | 🟢 B-02, 🟡 D-01, 🟢 F-01, 🟢 G-01, 🟡 G-02, 🟢 G-04 | 🟢 IMPRESSION-FE-001, 🟢 IMPRESSION-FE-002 | F-01 → ⛔ BLOCKED-BY product (PRODUCT-BE-B-01)<br>IMPRESSION-FE-001 → cross-domain: rides BOM-FE-002<br>IMPRESSION-FE-002 → cross-domain: rides PRODUCT-FE-001 |

Story sequence

One row per story in implementation order. Depends On/Blocks reference story ids + names (never order numbers). Every operation story also implicitly requires the B-01 module-init scaffold — not repeated per row. Parallelizable = Yes means other stories share its step.

| Order | Step | Story | Team · Owner | Depends On | Blocks | ∥ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 🟢 B-01 — searchImpressionsByProductId data fetch… | Backend · BE-1 | None | every story in this domain (module scaffold) | No |
| 2 | 2 | 🟢 B-02 — getImpressionCountsByProductId data fet… | Backend · BE-1 | B-01 — searchImpressionsByProd… | None | Yes |
| 3 | 2 | 🟡 D-01 — updateImpressions mutation | Backend · BE-1 | B-01 — searchImpressionsByProd… | None | Yes |
| 4 | 2 | 🟢 F-01 — Product.impressions / impressionCounts | Backend · BE-1 | B-01 — searchImpressionsByProd… | None | Yes |
| 5 | 2 | 🟢 G-01 — Impression field resolvers | Backend · BE-1 | B-01 — searchImpressionsByProd… | None | Yes |
| 6 | 2 | 🟡 G-02 — ImpressionCount.counts aggregation | Backend · BE-1 | B-01 — searchImpressionsByProd… | None | Yes |
| 7 | 2 | 🟢 G-04 — attachment entity reference | Backend · BE-1 | B-01 — searchImpressionsByProd… | None | Yes |
| 8 | 2 | 🟢 IMPRESSION-FE-001 — Migrate getBomDataAndImpressions | Frontend · FE-2 | B-01 — searchImpressionsByProd…, B-01 — searchImpressionsByProd…, BOM-FE-002 | None | Yes |
| 9 | 2 | 🟢 IMPRESSION-FE-002 — Migrate getCarryForwardFormData | Frontend · FE-2 | B-01 — searchImpressionsByProd…, B-01 — searchImpressionsByProd…, PRODUCT-FE-001 | None | Yes |

Backend critical path: B-01 → B-02.

Frontend cutover flow: IMPRESSION-FE-001 → IMPRESSION-FE-002.

Domain done when: the last FE story is flipped and stable; BE F/G stories (federation stitches, field-resolver parity) may trail post-flip.

Project plan · generated 2026-07-19 by generate_project_plan.py.