Federated GraphQL Breakdown — Measurement

Target DGS: plm-product (co-located)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 20 | T-Shirt Size M | Complexity 🔴 0 🟠 1 🟡 5 🟢 14 | Phases B, C, D, E, F, G, H |
| --- | --- | --- | --- |

Target DGS: plm-product (co-located)   |   Generated: 2026-07-19

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

Backend

What Are We Building?

- We are moving the Measurement domain — measurement sets (the size/point-of-measure specs for a product), their sample measurements, and the master-data unit lists — off the spark-internal-graphql gateway into the `plm-product` DGS. - It is mid-sized and mid-low risk: 7 queries, 8 mutations, 15 field resolvers on a 175-line resolver, with no polymorphism. - The one genuinely harder piece is updateMeasurement, a 2-step write (workspace association, then body) with no rollback today.

getMeasurements depends on the relationship service to find a product's measurement-set ids, and the template/size/tight-fit references are separate sibling domains we only reference (not migrate here).

ACL note: the current code obtains per-resource capability tokens via ACL. Per ADR-019 (complexStories/acl/01-adr-acl-mid-request-update.md), permission-check and own-domain-token call sites stay resolver-local (context-only, unchanged); measurement has zero downstream-token sites.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 7 | 3 cacheable master-data |
| Mutations | 8 | 6 simple + updateMeasurement (2-step) + add |
| Field-resolver type blocks | 2 | Measurement (13), SampleMeasurementSet (2) |
| External dependencies | 11 keys (2 🔴 · 6 🟡 · 3 🔵) | relationship/search 🔴; templates 🟡 |
| Federation contributions | 2 (Product, SampleV2) | BLOCKED-BY product/sample |
| Total stories | 20 | green-field |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 MST-BE-E-01 — updateMeasurement — 2-step orchestrated write | SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 5 | 5–9d |
| C | Listing | 2 | 4–7d |
| D | Mutations (simple) | 7 | 8–14d |
| E | Complex (updateMeasurement) | 1 | 4–7d |
| F | Federation | 2 | 3–5d (BLOCKED-BY product/sample) |
| G | Field Resolvers & Tests | 3 | 8–13d |
| Total | — | 20 | 32–55d (buffered) |

ℹ️  One engineer ≈ 7–11 sprints.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~8–14 sprints | sequential |
| 2 engineers | ~5–8 sprints | reads + mutations parallel |
| 3 engineers | ~4–6 sprints | critical path A → E-01 → G-01 → G-04 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1 | B-01 (DGS module init + service wiring + first resolver) | schema, service port, reads |
| 2 | C-01/C-02 + D-01–D-04 | listing + simple mutations |
| 3 | D-05–D-07 + E-01 | remaining mutations + updateMeasurement |
| 4 | G-01–G-02, G-04 | field resolvers (G-04 recommended, PO-gated). Test coverage/parity tracked outside this Jira pipeline, created manually. |
| post-launch | F-01, H-01 | federation contributions |

Recommended Implementation Order

Derived from each story's Depends On edges (plus the module-init scaffold as the implicit first step). A story appears in the earliest step where everything it depends on is already done; stories in the same step are independent of each other and parallelize across engineers. Focus names the phase category each step advances — same convention as the frontend order map.

🔬 spike gates and ⛔ cross-subgraph blocks are entry criteria, not ordering edges — a gated story slides later without reshuffling the map.

| Step | Stories (parallel set) | Entry gates in this step | Focus |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | 🧱 Module init — schema skeleton, service wiring (unblocks everything) |
| 2 | 🟢 B-02, 🟢 B-03, 🟢 B-04, 🟢 B-05, 🟡 C-01, 🟢 C-02, 🟡 D-01, 🟢 D-02, 🟢 D-03, 🟢 D-04, 🟢 D-05, 🟡 D-06, 🟢 D-07, 🟠 E-01, 🟡 F-01, 🟡 G-01, 🟢 G-02, 🟢 H-01 | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module)<br>H-01 → ⛔ BLOCKED-BY sample | Fan-out — 📖 Core Reads · 🔍 Search & Listing · ✏️ Mutations · ⚙️ Complex Operations · 🔗 Federation & Stitching · 🧪 Field Resolvers & Tests · 🧬 Entity Resolution |
| 3 | 🟢 G-04 | — | 🧪 Field Resolvers & Tests |

Critical path: B-01 → B-02 → G-04 — 3 sequential stories; everything else hangs off this chain in parallel.

Recommended Story Graph — 1 Backend Engineer

The order map above assumes unlimited parallelism; this packs the same dependency graph onto 1 backend engineer (greedy critical-chain scheduling, nominal day-ranges from complexity — confirm in refinement). Read each column top-to-bottom as one engineer's queue; ⏳ marks a slot that waits on a dependency, 🔬/⛔ are entry gates that slide a slot without reshuffling the lanes.

| Slot | 👤 BE-1 |
| --- | --- |
| 1 | 🟢 B-01 (1–2d) |
| 2 | 🟠 E-01 (4–7d) 🔬 ⛔ |
| 3 | 🟢 B-02 (1–2d) |
| 4 | 🟢 B-05 (1–2d) |
| 5 | 🟡 C-01 (2–4d) |
| 6 | 🟡 D-01 (2–4d) |
| 7 | 🟡 D-06 (2–4d) |
| 8 | 🟡 F-01 (2–4d) |
| 9 | 🟡 G-01 (2–4d) |
| 10 | 🟢 B-03 (1–2d) |
| 11 | 🟢 B-04 (1–2d) |
| 12 | 🟢 C-02 (1–2d) |
| 13 | 🟢 D-02 (1–2d) |
| 14 | 🟢 D-03 (1–2d) |
| 15 | 🟢 D-04 (1–2d) |
| 16 | 🟢 D-05 (1–2d) |
| 17 | 🟢 D-07 (1–2d) |
| 18 | 🟢 G-02 (1–2d) |
| 19 | 🟢 G-04 (1–2d) |
| 20 | 🟢 H-01 (1–2d) ⛔ |

BE-1: B-01 → E-01 → B-02 → B-05 → C-01 → D-01 → D-06 → F-01 → G-01 → B-03 → B-04 → C-02 → D-02 → D-03 → D-04 → D-05 → D-07 → G-02 → G-04 → H-01

Elapsed (nominal midpoints): ~42 working days.

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 MST-BE-B-01 getMeasurementByIds data fetcher | 🟢 Low [XS] | Query | — | Intent — Fetch measurement sets by id. Today — GET … → camelCase. ignored in DGS Done when: • Returns measurements for ids with calculated flag forwarded • Empty ids → [] • snake→camel mapping |
| 🔷 MST-BE-B-02 getUnitsOfMeasure (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the unit-of-measure lookup list (cached). Today — GET … → units_of_measure camelCase Done when: • Returns UoM list (optionally filtered by ids) • Cached |
| 🔷 MST-BE-B-03 getThicknessUnitsOfMeasure (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the thickness unit-of-measure lookup (cached). Today — GET … → units_of_measure Done when: • Returns thickness UoM list • Cached |
| 🔷 MST-BE-B-04 getMeasurementSetStatus (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the measurement-set status lookup (cached). Today — GET … → {key:value} map → [{code, description}] Done when: • Returns statuses • Cached • key→code, value→description |
| 🔷 MST-BE-B-05 getSampleMeasurement data fetcher | 🟢 Low [XS] | Query | B-01 | Intent — Fetch the measurement set for a sample. Today — GET … → camelCase. ignored in DGS Done when: • Returns the sample measurement set for sampleId • Not found → null |

ℹ️  MST-BE-B-01: Note — DGS Module Init (this PR only): Creates measurement.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [be-03-schema.graphql](./be-03-schema.graphql).

🔍 Phase C — Search & Listing  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 MST-BE-C-01 getMeasurements data fetcher (relationship + listing) | 🟡 Medium [M] | Query Calls: relationship | B-01 | Intent — List a resource's measurement sets (resolves the relationship first). Today — relationships = relationship.findRelationships(resourceId, {includeNodeTypes:['measurement_set'], maxDepth:0}). 2. ids = relationships.map(n => n.id); if empty → [].… Done when: • Resolves ids via relationship then fetches measurements • No ids → {content:[]} (no measurement call) • Sorted createdAt DESC (location documented) |
| 🔷 MST-BE-C-02 getMeasurementsElastic data fetcher | 🟢 Low [XS] | Query Calls: search | B-01 | Intent — Search a product's measurement sets via elastic. Today — {content} = search.getMeasurementSets → sort createdAt DESC → {content}. - EXT Service Calls: EXT → key: search · severity: — elastic measurement-set index Done when: • Returns elastic content for parentId • Sorted createdAt DESC • Empty → {content:[]} |

✏️ Phase D — Mutations  (7 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 MST-BE-D-01 addMeasurement mutation | 🟡 Medium [M] | Mutation | B-01 | Intent — Create a measurement set. Today — POST … (snake_case request, primeKey: humanId); on validationErrors\¦\¦message → throw. No ACL (new resource) Done when: • POST creates + returns mapped Measurement • validationErrors/message → exception • Cache primed with humanId |
| 🔶 MST-BE-D-02 updateMeasurementAccess mutation | 🟢 Low [XS] | Mutation | B-01 | Intent — Change who can access a measurement set. Today — PUT …/{id}/permission body {systemTeamIds} or {systemTeamDto} (whichever provided). ignored in DGS Done when: • Sends {systemTeamIds} when provided, else {systemTeamDto} • Returns updated measurement • Input-shape decision recorded |
| 🔶 MST-BE-D-03 lockMeasurementSet mutation | 🟢 Low [XS] | Mutation | B-01 | Intent — Lock a measurement set from edits. Today — PUT …/{id}/lock. ignored in DGS Done when: • PUT /lock returns locked set • 404 → null |
| 🔶 MST-BE-D-04 unlockMeasurementSet mutation | 🟢 Low [XS] | Mutation | B-01 | Intent — Unlock a measurement set. Today — PUT …/{id}/unlock Done when: • PUT /unlock returns unlocked set • 404 → null |
| 🔶 MST-BE-D-05 updateMeasurementComponentStatus mutation | 🟢 Low [XS] | Mutation | B-01 | Intent — Update the component status on measurement sets. Today — PUT …/component_status_update body {productId, ids, status}. No ACL token — confirm backend enforces (like BOM D-05) Done when: • PUT sends {productId, ids, status} snake_case • Returns MeasurementPaged{content} • Auth decision recorded |
| 🔶 MST-BE-D-06 putSampleMeasurementSet mutation | 🟡 Medium [M] | Mutation | B-01 | Intent — Create or replace a sample's measurement set. Today — PUT …/sample (primeKey: sampleId); token for [measurementSetId, sampleId]; on validationErrors\¦\¦message → throw Done when: • PUT upserts the sample set • validationErrors/message → exception • Cache primed by sampleId |
| 🔶 MST-BE-D-07 deleteSampleMeasurementSet mutation | 🟢 Low [XS] | Mutation | B-01 | Intent — Delete a sample's measurement set. Today — DELETE …/sample/{sampleId}. ignored in DGS Done when: • DELETE removes the sample set; returns the deleted/empty result • 404 → null |

⚙️ Phase E — Complex Operations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 MST-BE-E-01 updateMeasurement — 2-step orchestrated write 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: workspaceV2 | SPIKE-01, B-01 | Intent — Edit a measurement set — a 2-step write (workspace + body) that has no rollback today. Today — workspaceAssociations = sparkMeasurement.updateWorkspaceAssociations \¦\¦ {}. token for [humanId]. 2. If add/remove workspaces → workspaceAssociationHelper(MEASUREMENT… Done when: • Parity for 3 fixtures: body-only; body+workspace-add; body+workspace-remove • Workspace step runs before body PUT • Body PUT omits humanId • Chosen failure strategy implemented • validationErrors/message → exception | ☐ Unit: order workspace→body ☐ Unit: no-workspace skip ☐ Unit: body-failure path ☐ Parity: 3 fixtures |

🔗 Phase F — Federation & Stitching  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 MST-BE-F-01 Implement Product.measurementSets (internal) | 🟡 Medium [M] | Field Resolver Calls: relationship | B-01 | Intent — Expose a product's measurement sets on the Product type. Today — product navigates to measurement sets via the relationship + getMeasurements flow Done when: • Product.measurementSets resolves internally via measurementService • no gateway hop • Parity vs current product resolver |

🧪 Phase G — Field Resolvers & Tests  (3 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 MST-BE-G-01 Measurement field resolvers (13 fields) | 🟡 Medium [M] | Field Resolver Calls: workspaceV2, sampleV2, measurementTemplate, sizeTemplate, tightFit, vmm, userAttributes | B-01 | Intent — Resolve the everyday measurement fields (people, product, partners). Today — access/currentUserPermissions , businessPartners (loadBps), createdBy/updatedBy (getUserByIDOrNullIfNotFound), product (PID-prefixed → internal product.getByID)… Done when: • All 13 fields resolve • product null when resourceId not PID* • status = {statusId, statusName} • workspaces empty → null • updatedFromResource resolves only for type==='sample' |
| 🔸 MST-BE-G-02 SampleMeasurementSet field resolvers (2 fields) | 🟢 Low [XS] | Field Resolver Calls: userAttributes | B-01 | Intent — Resolve the sample-measurement-set fields. Today — 2 @DgsData fields Done when: • createdBy resolves by user id (null id → null) • measurementSizeId = measurementSize.code |
| 🔸 MST-BE-G-04 SampleMeasurementSet.sample forward reference (recommended, PO-gated) | 🟢 Low [XS] | Field Resolver Calls: sample | B-02 (carries B-05 `getSampleMeasurement`, grouped-XS merged) | Intent — Adds sample { … } on the sample measurement set — the forward twin of the existing Today — schema adds sample: SampleV2 on SampleMeasurementSet; resolver emits Done when: • PO approval recorded (OQ-5) before implementation starts • sample { id } resolves as a stub; sampleId unchanged • Pairs cleanly with MST-BE-H-01 (no circular resolution at the gateway — verified by a two-hop smoke query) |

🧬 Phase H — Entity Resolution  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 MST-BE-H-01 Contribute sampleMeasurement to the SampleV2 entity | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Contribute a sample's measurement set to the Sample entity. Today — sample navigates to its measurement set via getSampleMeasurement Done when: • SampleV2.sampleMeasurement resolves • Parity vs current |

Frontend

# Federated GraphQL Breakdown — Measurement · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (co-located) |
| Total FE Stories | 4 |
| Impact | 🔴 0 High · 🟡 3 Medium · 🟢 1 Low |
| Estimated effort | 12–19 days (single-engineer) |
| Phase-1 surface | 13 operation-to-root-field rows · 4 client files · 7 components |
| Generated | 2026-07-19 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Measurement GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (co-located)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| MST-FE-001 | Migrate measurement reads and retire humanId | Query migration | 🟡 Medium | 4–6 days | MST-BE-B-01, MST-BE-B-04 | getMeasurementByIds, getMeasurementSetStatus, getMeasurementComponentStatus |
| MST-FE-002 | Migrate measurement list/search reads | Query migration | 🟡 Medium | 3–5 days | MST-BE-C-01, MST-BE-C-02 | getMeasurements, getMeasurementsElastic |
| MST-FE-003 | Migrate measurement master-data reads | Query migration | 🟢 Low | 1–2 days | MST-BE-B-02, MST-BE-B-03 | getUnitsOfMeasure, getThicknessUnitsOfMeasure |
| MST-FE-004 | Migrate measurement mutations | Mutation migration | 🟡 Medium | 4–6 days | MST-BE-D-03, MST-BE-D-04, MST-BE-D-06, MST-BE-D-07 | lockMeasurementSet, unlockMeasurementSet, putSampleMeasurementSet, deleteSampleMeasurementSet |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🟡 MST-FE-001, 🟢 MST-FE-003 | MST-FE-001 → MST-BE-B-01, MST-BE-B-04<br>MST-FE-003 → MST-BE-B-02, MST-BE-B-03 | Reads cutover — needs backend phase A/B reads live |
| 2 | 🟡 MST-FE-002 | MST-FE-002 → MST-BE-C-01, MST-BE-C-02 | Search & listing — needs backend phase C |
| 3 | 🟡 MST-FE-004 | MST-FE-004 → MST-BE-D-03, MST-BE-D-04, MST-BE-D-06, MST-BE-D-07 | Writes — needs backend phase D mutations |

Cutover flow: MST-FE-001 → MST-FE-003 → MST-FE-002 → MST-FE-004.

Recommended Story Graph — 1 Frontend Engineer

The staged order map above, run by one frontend engineer. Steps re-sync at each stage because the stage's backend gate — not engineer availability — is the limiter.

| Step | 👤 FE-1 | Backend gate (focus) |
| --- | --- | --- |
| 1 | 🟡 MST-FE-001 (4–6d)<br>🟢 MST-FE-003 (1–2d) | Reads cutover — needs backend phase A/B reads live |
| 2 | 🟡 MST-FE-002 (3–5d) | Search & listing — needs backend phase C |
| 3 | 🟡 MST-FE-004 (4–6d) | Writes — needs backend phase D mutations |

Elapsed (nominal midpoints): ~16 FE build days — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-measurement.md — the combined Backend + Frontend breakdown this section lives in.