Federated GraphQL Breakdown — Watchlist

Target DGS: plm-product (co-located)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 13 | T-Shirt Size M | Complexity 🔴 0 🟠 1 🟡 5 🟢 7 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-product (co-located)   |   Generated: 2026-07-19

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

Backend

What Are We Building?

- We are moving the Watchlist domain — quality watchlist entries on a product (reasons, statuses, inspections, partners, attachments) — off the spark-internal-graphql gateway into the `plm-product` DGS. - It is small and mid-low risk: 4 queries, 3 mutations, 13 field resolvers on a 129-line resolver, with no polymorphism. - It is co-located in the product family, so Product.watchlists and the TechPack ResourcesCount.watchlists count resolve internally (not across the federation gateway).

The one genuinely harder piece is `updateWatchlistEntries`, a multi-step write (user-group upsert, then the body, then attachment archival) that today does not await its per-entry user-group updates — a race to fix on the port.

ACL note: the current code obtains per-resource capability tokens via ACL. Per ADR-019 (complexStories/acl/01-adr-acl-mid-request-update.md), permission-check and own-domain-token call sites stay resolver-local (context-only, unchanged); downstream-token call sites (e.g. the attachment-archive step in updateWatchlistEntries) use Mid-Request ACL Update before the downstream call.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 4 | 2 cacheable master-data; 1 four-step filtered read |
| Mutations | 3 | 2 simple + updateWatchlistEntries (multi-step) |
| Field-resolver type blocks | 3 | Watchlist (10), inspection (2), partner (1) |
| External dependencies | 6 keys (2 🔴 · 2 🟡 · 2 🔵) | search/attachment 🔴 |
| Federation contributions | 2 (Product, ResourcesCount) | internal (co-located) |
| Total stories | 13 | green-field |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 WATCHLIST-BE-E-01 — updateWatchlistEntries (multi-step write) | SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20%) |
| --- | --- | --- | --- |
| B | Core Reads | 3 | 3–6d |
| C | Search & Listing | 1 | 3–5d |
| D | Mutations (simple) | 2 | 4–7d |
| E | Complex (updateWatchlistEntries) | 1 | 4–7d |
| F | Federation (Product + TechPack, internal) | 2 | 2–4d |
| G | Field Resolvers & Tests | 4 | 9–15d |
| Total | — | 13 | 25–44d (buffered) |

ℹ️  One engineer ≈ 5–9 sprints.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~6–11 sprints | sequential |
| 2 engineers | ~4–6 sprints | reads + mutations parallel after B-01 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1 | B-01 (DGS module init + service wiring + first resolver) | schema, service port, reads |
| 2 | C-01 + D-01/D-02 | filtered read + simple mutations |
| 3 | E-01 + F-01/F-02 | multi-step update + Product/TechPack internal contributions |
| 4 | G-01–G-03, G-05 (recommended, PO-gated) | field resolvers. Test coverage/parity tracked outside this Jira pipeline, created manually. |

Recommended Implementation Order

Derived from each story's Depends On edges (plus the module-init scaffold as the implicit first step). A story appears in the earliest step where everything it depends on is already done; stories in the same step are independent of each other and parallelize across engineers. Focus names the phase category each step advances — same convention as the frontend order map.

🔬 spike gates and ⛔ cross-subgraph blocks are entry criteria, not ordering edges — a gated story slides later without reshuffling the map.

| Step | Stories (parallel set) | Entry gates in this step | Focus |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | 🧱 Module init — schema skeleton, service wiring (unblocks everything) |
| 2 | 🟢 B-02, 🟢 B-03, 🟡 C-01, 🟡 D-01, 🟡 D-02, 🟠 E-01, 🟢 F-01, 🟢 F-02, 🟢 G-01, 🟡 G-02, 🟡 G-03 | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module) | Fan-out — 📖 Core Reads · 🔍 Search & Listing · ✏️ Mutations · ⚙️ Complex Operations · 🔗 Federation & Stitching · 🧪 Field Resolvers & Tests |
| 3 | 🟢 G-05 | — | 🧪 Field Resolvers & Tests |

Critical path: B-01 → G-02 → G-05 — 3 sequential stories; everything else hangs off this chain in parallel.

Recommended Story Graph — 1 Backend Engineer

The order map above assumes unlimited parallelism; this packs the same dependency graph onto 1 backend engineer (greedy critical-chain scheduling, nominal day-ranges from complexity — confirm in refinement). Read each column top-to-bottom as one engineer's queue; ⏳ marks a slot that waits on a dependency, 🔬/⛔ are entry gates that slide a slot without reshuffling the lanes.

| Slot | 👤 BE-1 |
| --- | --- |
| 1 | 🟢 B-01 (1–2d) |
| 2 | 🟠 E-01 (4–7d) 🔬 ⛔ |
| 3 | 🟡 G-02 (2–4d) |
| 4 | 🟡 C-01 (2–4d) |
| 5 | 🟡 D-01 (2–4d) |
| 6 | 🟡 D-02 (2–4d) |
| 7 | 🟡 G-03 (2–4d) |
| 8 | 🟢 B-02 (1–2d) |
| 9 | 🟢 B-03 (1–2d) |
| 10 | 🟢 F-01 (1–2d) |
| 11 | 🟢 F-02 (1–2d) |
| 12 | 🟢 G-01 (1–2d) |
| 13 | 🟢 G-05 (1–2d) |

BE-1: B-01 → E-01 → G-02 → C-01 → D-01 → D-02 → G-03 → B-02 → B-03 → F-01 → F-02 → G-01 → G-05

Elapsed (nominal midpoints): ~31 working days.

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (3 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 WATCHLIST-BE-B-01 getWatchlistByIds(ids) | 🟢 Low [XS] | Query | — | Intent — Fetch watchlist entries by id. Today — token → GET watchlist/v1?watchlistIds={csv} → camelCase Done when: • returns entries for ids; empty → [] |
| 🔷 WATCHLIST-BE-B-02 getWatchlistReasons (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the watchlist-reason lookup (cached). Today — GET watchlist/v1/watchlist_reasons Done when: • returns reasons; cached |
| 🔷 WATCHLIST-BE-B-03 getWatchlistInspectionActions (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the inspection-action lookup (cached). Today — GET watchlist/v1/watchlist_inspection_action_types Done when: • returns actions; cached |

ℹ️  WATCHLIST-BE-B-01: Note — DGS Module Init (this PR only): Creates watchlist.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [be-03-schema.graphql](./be-03-schema.graphql).

🔍 Phase C — Search & Listing  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 WATCHLIST-BE-C-01 getWatchlistByFilter(...) (4-step read) | 🟡 Medium [M] | Query Calls: search, product | B-01 | Intent — List watchlist entries for a workspace's products (a 4-step read). Today — (internal) product.getWorkspaceProducts({q,filter,workspaceId,page,size}) → product humanIds → (search) searchWatchlist({ q:"parentId:(... OR ...) AND… Done when: • product→search→watchlist chain preserved • elastic query string exact (incl. statusId: 501) |

✏️ Phase D — Mutations  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 WATCHLIST-BE-D-01 createWatchlistEntries | 🟡 Medium [M] | Mutation Calls: userGroup | B-01 | Intent — Create watchlist entries (and their user-groups). Today — Promise.all(entries.map(w => { createWatchlistEntries([w]); throw on validationErrors/message; then (user-group) addUserGroup({resourceId:humanId, participantDetails… Done when: • creates each entry + its user group • either failure → exception |
| 🔶 WATCHLIST-BE-D-02 cloneFilesForWatchlist | 🟡 Medium [M] | Mutation Calls: attachment | B-01 | Intent — Copy attachment files for watchlist entries. Today — token → Promise.all(attachmentIds.map((id,i) => (attachment) cloneAttachmentV3({cloneReferences:[cloneReference[i]]}, id))), stamp parentResource=id, flatten. EXT… Done when: • clones each id with its paired cloneReference; parentResource stamped |

⚙️ Phase E — Complex Operations  (1 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 WATCHLIST-BE-E-01 updateWatchlistEntries (multi-step write) 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: attachment, userGroup | SPIKE-01, B-01 | Intent — Edit watchlist entries — a multi-step write (user-groups + body); today the group step isn't awaited (a bug). Today — per-entry (currently NOT awaited — bug): getUserGroups([humanId]); if existing participants → updateUserGroup, else (user-group) addUserGroup (throw on error); 2)… Done when: • user-group upserts complete before the watchlist update (race fixed) • removed attachments archived • partial-failure strategy | ☐ existing-participants path ☐ new-participants path ☐ attachment archive ☐ ordering/await ☐ partial-failure ☐ Parity: DGS response matches spark-internal-graphql baseline |

🔗 Phase F — Federation & Stitching  (2 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 WATCHLIST-BE-F-01 Product.watchlists (internal) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Expose a product's watchlists on the Product type. Today — Product exposes watchlists resolved from the co-located watchlist service Done when: • resolves in-process; no gateway hop |
| 🔸 WATCHLIST-BE-F-02 ResourcesCount.watchlists (internal — TechPack) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Contribute the watchlists count to the TechPack rollup. Today — fill the TechPack `ResourcesCount Done when: • count resolves in-process; parity vs the TechPack facade |

🧪 Phase G — Field Resolvers & Tests  (4 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 WATCHLIST-BE-G-01 Computed flatteners (status/reasons/inspection action) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Flatten status / reason / inspection-action codes into readable fields. Today — statusId=status.code, statusName=status.description, reasonIds=reasons[].code, reasons=reasons[].description; WatchlistInspection.actionId=action.code… Done when: • each flattener maps correctly |
| 🔸 WATCHLIST-BE-G-02 createdBy + updatedBy + workspaces + participantDetails + partnerName | 🟡 Medium [M] | Field Resolver Calls: userAttributes, workspaceV2, userGroup, vmm | B-01 | Intent — Resolve the people, workspace and partner fields. Done when: • each resolves; null-safe |
| 🔸 WATCHLIST-BE-G-03 attachments + product | 🟡 Medium [M] | Field Resolver Calls: search | B-01 | Intent — Resolve a watchlist entry's attachments and parent product. Done when: • attachments via elastic • product null when not PID* |
| 🔸 WATCHLIST-BE-G-05 WatchlistPartner.partner entity reference (recommended, PO-gated) | 🟢 Low [XS] | Field Resolver Calls: vmm | G-02 | Intent — Adds partner { … } next to partnerId/partnerName on watchlist partner rows. Today — schema adds partner: VMM_BusinessPartner on WatchlistPartner; resolver Done when: • PO approval recorded (OQ-5) before implementation starts • partner { id name } resolves via the gateway; partnerName parity is preserved • No additional VMM calls from the watchlist subgraph (stub emission only) |

Frontend

# Federated GraphQL Breakdown — Watchlist · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (co-located) |
| Total FE Stories | 3 |
| Impact | 🔴 0 High · 🟡 1 Medium · 🟢 2 Low |
| Estimated effort | 7–10 days (single-engineer) |
| Phase-1 surface | 5 operation-to-root-field rows · 1 client files · 4 components |
| Generated | 2026-07-19 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Watchlist GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (co-located)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| WATCHLIST-FE-001 | Migrate watchlist reads | Query migration | 🟢 Low | 2–3 days | WATCHLIST-BE-B-01, WATCHLIST-BE-C-01 | getWatchlistByIds, getWatchlistByFilter |
| WATCHLIST-FE-002 | Migrate watchlist create and clone mutations | Mutation migration | 🟢 Low | 2–3 days | WATCHLIST-BE-D-01, WATCHLIST-BE-D-02 | createWatchlistEntries, cloneFilesForWatchlist |
| WATCHLIST-FE-003 | Migrate updateWatchlistEntries saga handling | Mutation migration (complex) | 🟡 Medium | 3–4 days | WATCHLIST-BE-E-01 | updateWatchlistEntries |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 2 | 🟢 WATCHLIST-FE-001 | WATCHLIST-FE-001 → WATCHLIST-BE-B-01, WATCHLIST-BE-C-01 | Search & listing — needs backend phase C |
| 3 | 🟢 WATCHLIST-FE-002 | WATCHLIST-FE-002 → WATCHLIST-BE-D-01, WATCHLIST-BE-D-02 | Writes — needs backend phase D mutations |
| 4 | 🟡 WATCHLIST-FE-003 | WATCHLIST-FE-003 → WATCHLIST-BE-E-01 | Complex writes / sagas — needs backend phase E + ADR ratification |

Cutover flow: WATCHLIST-FE-001 → WATCHLIST-FE-002 → WATCHLIST-FE-003.

Recommended Story Graph — 1 Frontend Engineer

The staged order map above, run by one frontend engineer. Steps re-sync at each stage because the stage's backend gate — not engineer availability — is the limiter.

| Step | 👤 FE-1 | Backend gate (focus) |
| --- | --- | --- |
| 2 | 🟢 WATCHLIST-FE-001 (2–3d) | Search & listing — needs backend phase C |
| 3 | 🟢 WATCHLIST-FE-002 (2–3d) | Writes — needs backend phase D mutations |
| 4 | 🟡 WATCHLIST-FE-003 (3–4d) | Complex writes / sagas — needs backend phase E + ADR ratification |

Elapsed (nominal midpoints): ~8 FE build days — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-watchlist.md — the combined Backend + Frontend breakdown this section lives in.