Federated GraphQL Breakdown — Product Details

Target DGS: plm-product (co-located)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 12 | T-Shirt Size M | Complexity 🔴 0 🟠 1 🟡 6 🟢 5 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-product (co-located)   |   Generated: 2026-07-19

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

Backend

What Are We Building?

We are moving the ProductDetails domain — the product's "construction" sets (build/assembly detail rows, their attachments, and per-partner access) — off the spark-internal-graphql gateway into the `plm-product` DGS. It is mid-sized and mid-low risk: 2 queries, 6 mutations, 12 field resolvers on a 129-line resolver, with no polymorphism. (In the backend this domain is called construction — construction/v1; the GraphQL names stay productDetails.)

The one genuinely harder piece is `updateProductDetailsSet`, a multi-step write — workspace associations, then bulk-archive removed attachments, then the body — with no rollback today.

ACL note: the current code obtains per-resource capability tokens via ACL. Per ADR-019 (complexStories/acl/01-adr-acl-mid-request-update.md), permission-check and own-domain-token call sites stay resolver-local (context-only, unchanged); downstream-token call sites (e.g. the attachment-archive step in updateProductDetailsSet) use Mid-Request ACL Update before the downstream call.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 2 | one by-ids (internal), one elastic (🔴 search) |
| Mutations | 6 | 5 simple + updateProductDetailsSet (multi-step) |
| Field-resolver type blocks | 3 | ProductDetails (10), item (2), category (1) |
| External dependencies | 6 keys (2 🔴 · 2 🟡 · 2 🔵) | search/attachment 🔴 |
| Federation contributions | 1 (Product) | internal (co-located) |
| Total stories | 13 | green-field |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 PDTL-BE-E-01 — updateProductDetailsSet (multi-step write) | SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20% buffer) |
| --- | --- | --- | --- |
| B | Core Reads | 1 | 1–2d |
| C | Search & Listing | 1 | 2–5d |
| D | Mutations | 5 | 8–17d |
| E | Complex Operations | 1 | 5–8d |
| F | Federation & Stitching | 1 | 1–2d |
| G | Field Resolvers & Tests | 3 | 7–14d |
| Total | — | 12 | 24–48d (buffered) |

ℹ️  Computed live from be-04-stories.md (phase + complexity per story) — always reconciles with the story tables below and the program overview. Effort = sum of per-story nominal day-ranges (Low 1–2 · Medium 2–4 · High 4–7 · Very High 7–12) × 1.2 buffer, AI-estimated — confirm in refinement. See each story's Depends On column for real sequencing.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~6–11 sprints | sequential |
| 2 engineers | ~4–6 sprints | reads + mutations parallel after B-01 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1 | B-01 (DGS module init + service wiring + first resolver) | schema, service port, reads |
| 2 | D-01–D-05 | simple mutations |
| 3 | E-01 + F-01 | multi-step write + Product field |
| 4 | G-01–G-03 | field resolvers. Test coverage/parity tracked outside this Jira pipeline, created manually. |

Recommended Implementation Order

Derived from each story's Depends On edges (plus the module-init scaffold as the implicit first step). A story appears in the earliest step where everything it depends on is already done; stories in the same step are independent of each other and parallelize across engineers. Focus names the phase category each step advances — same convention as the frontend order map.

🔬 spike gates and ⛔ cross-subgraph blocks are entry criteria, not ordering edges — a gated story slides later without reshuffling the map.

| Step | Stories (parallel set) | Entry gates in this step | Focus |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | 🧱 Module init — schema skeleton, service wiring (unblocks everything) |
| 2 | 🟡 C-01, 🟡 D-01, 🟢 D-02, 🟢 D-03, 🟡 D-04, 🟢 D-05, 🟠 E-01, 🟢 F-01, 🟡 G-01, 🟡 G-02, 🟡 G-03 | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module) | Fan-out — 🔍 Search & Listing · ✏️ Mutations · ⚙️ Complex Operations · 🔗 Federation & Stitching · 🧪 Field Resolvers & Tests |

Critical path: B-01 → C-01 — 2 sequential stories; everything else hangs off this chain in parallel.

Recommended Story Graph — 1 Backend Engineer

The order map above assumes unlimited parallelism; this packs the same dependency graph onto 1 backend engineer (greedy critical-chain scheduling, nominal day-ranges from complexity — confirm in refinement). Read each column top-to-bottom as one engineer's queue; ⏳ marks a slot that waits on a dependency, 🔬/⛔ are entry gates that slide a slot without reshuffling the lanes.

| Slot | 👤 BE-1 |
| --- | --- |
| 1 | 🟢 B-01 (1–2d) |
| 2 | 🟠 E-01 (4–7d) 🔬 ⛔ |
| 3 | 🟡 C-01 (2–4d) |
| 4 | 🟡 D-01 (2–4d) |
| 5 | 🟡 D-04 (2–4d) |
| 6 | 🟡 G-01 (2–4d) |
| 7 | 🟡 G-02 (2–4d) |
| 8 | 🟡 G-03 (2–4d) |
| 9 | 🟢 D-02 (1–2d) |
| 10 | 🟢 D-03 (1–2d) |
| 11 | 🟢 D-05 (1–2d) |
| 12 | 🟢 F-01 (1–2d) |

BE-1: B-01 → E-01 → C-01 → D-01 → D-04 → G-01 → G-02 → G-03 → D-02 → D-03 → D-05 → F-01

Elapsed (nominal midpoints): ~31 working days.

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (1 story)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 PDTL-BE-B-01 getProductDetailsById(ids) | 🟢 Low [XS] | Query | — | Intent — Fetch product-detail (construction) sets by id. Today — token for ids → GET construction/v1?ids={csv} → camelCase Done when: • returns list for ids; empty → [] |

ℹ️  PDTL-BE-B-01: Note — DGS Module Init (this PR only): Creates productDetails.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [be-03-schema.graphql](./be-03-schema.graphql).

🔍 Phase C — Search & Listing  (1 story)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 PDTL-BE-C-01 getProductDetailsElastic(resourceId) | 🟡 Medium [M] | Query Calls: search | B-01 | Intent — Search a product's product-detail sets via elastic. Today — (search) search.getProductDetailsElastic → paged. - EXT: search Done when: • parentId: elastic query built • paged shape returned |

✏️ Phase D — Mutations  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 PDTL-BE-D-01 createProductDetailsSet | 🟡 Medium [M] | Mutation | B-01 | Intent — Create a product-detail set. Today — token for literal capability → POST construction/v1 (snake_case). If response has validationErrors or message → throw Done when: • creates set • validation error → exception (not a partial object) |
| 🔶 PDTL-BE-D-02 updateProductDetailAccess | 🟢 Low [XS] | Mutation | B-01 | Intent — Change who can access a product-detail set. Today — map managePermissionsRequest[].resourceId → token → PUT construction/v1/manage-permissions (primeKey=humanId) Done when: • updates partner access for each resource |
| 🔶 PDTL-BE-D-03 productDetailLockUnlock | 🟢 Low [XS] | Mutation | B-01 | Intent — Lock or unlock a product-detail set. Today — token for [constructionSetId] → PUT construction/v1/{id}/{lock\¦unlock} Done when: • isLock=true→lock path, false→unlock path |
| 🔶 PDTL-BE-D-04 cloneFilesForProductDetails | 🟡 Medium [M] | Mutation Calls: attachment | B-01 | Intent — Copy attachment files for product details. Today — token → Promise.all(attachmentIds.map((id,i) => (attachment) cloneAttachmentV3({cloneReferences:[cloneReference[i]]}, id))), stamp parentResource=id, flatten. No… Done when: • clones each id with its paired cloneReference • parentResource stamped |
| 🔶 PDTL-BE-D-05 updateProductDetailComponentStatus | 🟢 Low [XS] | Mutation | B-01 | Intent — Update component status on product-detail sets. Today — PUT construction/v1/component_status_update; wraps result as {content}. No JWT — confirm backend-enforced Done when: • updates statuses; result wrapped as {content} • no-token behaviour documented |

⚙️ Phase E — Complex Operations  (1 story)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 PDTL-BE-E-01 updateProductDetailsSet (multi-step write) 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: attachment, workspaceV2 | SPIKE-01, B-01 | Intent — Edit a product-detail set — a multi-step write (workspace + body) with no rollback today. Today — if workspaceContext.{add,remove}Workspaces non-empty → workspaceAssociationHelper(PRODUCT_DETAIL, id, add, remove) (throws on error); 2) null workspaceContext; 3) if… Done when: • all 4 steps in order • partial-failure strategy implemented • workspace assoc throws propagate | ☐ full path ☐ workspace-only ☐ attachment-archive ☐ partial-failure ☐ Parity: DGS response matches spark-internal-graphql baseline |

🔗 Phase F — Federation & Stitching  (1 story)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 PDTL-BE-F-01 Product.productDetails (internal, same subgraph) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Expose a product's product-details on the Product type (same subgraph). Today — Product exposes productDetails resolved from the co-located ProductDetails service Done when: • Product.productDetails resolves in-process; no gateway hop |

🧪 Phase G — Field Resolvers & Tests  (3 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 PDTL-BE-G-01 access + currentUserPermissions + participantDetails | 🟡 Medium [M] | Field Resolver Calls: userGroup | B-01 | Intent — Resolve access / permission / participant fields. Today — access → accessControl.getPermissions([humanId\¦\¦id])[0]; currentUserPermissions → getUserAccessUnencoded(humanId\¦\¦id)[0]; participantDetails → getUserGroup(humanId) Done when: • each field resolves; null-safe on empty |
| 🔸 PDTL-BE-G-02 product + createdBy + updatedBy + businessPartners + workspaces | 🟡 Medium [M] | Field Resolver Calls: userAttributes, workspaceV2, vmm | B-01 | Intent — Resolve the product, people, partner and workspace fields. Today — product (internal, only if parentId starts 'PID'), createdBy/updatedBy (user-profile), businessPartners (vmm loadBpsWithType), workspaces (workspaceV2 by ids) Done when: • each resolves; product null when parentId not PID* • null id → null user |
| 🔸 PDTL-BE-G-03 attachment + item attachment/constructionSetAttachments + category subCategories | 🟡 Medium [M] | Field Resolver Calls: search | B-01 | Intent — Resolve attachment and category fields on product details. Today — ProductDetails.attachment → (search) searchAttachments([humanId\¦\¦id]), find - relatedResources.length<=2; ProductDetailsItem.attachment →… Done when: • each field resolves to the right source • attachment length-≤2 filter preserved |

Frontend

# Federated GraphQL Breakdown — Product Details · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (co-located) |
| Total FE Stories | 3 |
| Impact | 🔴 0 High · 🟡 2 Medium · 🟢 1 Low |
| Estimated effort | 8–12 days (single-engineer) |
| Phase-1 surface | 7 operation-to-root-field rows · 2 client files · 4 components |
| Generated | 2026-07-19 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Product Details GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (co-located)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| PDTL-FE-001 | Migrate product-details reads | Query migration | 🟢 Low | 2–3 days | PDTL-BE-B-01, PDTL-BE-G-01, PDTL-BE-G-02, PDTL-BE-G-03 | getProductDetailsById, getProductDetailComponentStatus |
| PDTL-FE-002 | Migrate product-details simple mutations | Mutation migration | 🟡 Medium | 3–4 days | PDTL-BE-D-01, PDTL-BE-D-03, PDTL-BE-D-04, PDTL-BE-D-05 | createProductDetailsSet, productDetailLockUnlock, cloneFilesForProductDetails, updateProductDetailComponentStatus |
| PDTL-FE-003 | Migrate updateProductDetailsSet saga handling | Mutation migration (complex) | 🟡 Medium | 3–5 days | PDTL-BE-E-01 | updateProductDetailsSet |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 3 | 🟡 PDTL-FE-002 | PDTL-FE-002 → PDTL-BE-D-01, PDTL-BE-D-03, PDTL-BE-D-04, PDTL-BE-D-05 | Writes — needs backend phase D mutations |
| 4 | 🟢 PDTL-FE-001, 🟡 PDTL-FE-003 | PDTL-FE-001 → PDTL-BE-B-01, PDTL-BE-G-01, PDTL-BE-G-02, PDTL-BE-G-03<br>PDTL-FE-003 → PDTL-BE-E-01 | Complex writes / sagas — needs backend phase E + ADR ratification |

Cutover flow: PDTL-FE-002 → PDTL-FE-001 → PDTL-FE-003.

Recommended Story Graph — 1 Frontend Engineer

The staged order map above, run by one frontend engineer. Steps re-sync at each stage because the stage's backend gate — not engineer availability — is the limiter.

| Step | 👤 FE-1 | Backend gate (focus) |
| --- | --- | --- |
| 3 | 🟡 PDTL-FE-002 (3–4d) | Writes — needs backend phase D mutations |
| 4 | 🟡 PDTL-FE-003 (3–5d)<br>🟢 PDTL-FE-001 (2–3d) | Complex writes / sagas — needs backend phase E + ADR ratification |

Elapsed (nominal midpoints): ~10 FE build days — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-productDetails.md — the combined Backend + Frontend breakdown this section lives in.