Federated GraphQL Breakdown — Packaging

Target DGS: plm-product (co-located)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 23 | T-Shirt Size L | Complexity 🔴 0 🟠 2 🟡 8 🟢 13 | Phases B, C, D, E, F, G |
| --- | --- | --- | --- |

Target DGS: plm-product (co-located)   |   Generated: 2026-07-21

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

Backend

What Are We Building?

- We are moving the Packaging domain — packaging records, their dielines (print artwork specs), printers, elements, and exports — off the spark-internal-graphql gateway into the `plm-product` DGS. - It is mid-sized with a wide schema (24 object types, 20 inputs): 7 queries, 10 mutations, 17 field resolvers on a 273-line resolver, but no polymorphism.

Two pieces carry the real work: `updatePackaging`, a multi-step write (body, then attachment remove via archive + relationship, then attachment add via relationship + attribute update) with no rollback; and `suggestedRetailPriceByDPCI`, a multi-hop pricing field (printers → dielines → DPCIs → pricing service).

ACL note: the current code obtains per-resource capability tokens via ACL. Per ADR-019 (complexStories/acl/01-adr-acl-mid-request-update.md), permission-check and own-domain-token call sites stay resolver-local (context-only, unchanged); downstream-token call sites (e.g. the attachment-archive steps in updatePackaging) use Mid-Request ACL Update before the downstream call.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 7 | 2 cacheable master-data; 1 elastic (🔴 search) |
| Mutations | 10 | 9 simple + updatePackaging (multi-step) |
| Field-resolver type blocks | 4 | Packaging (12), Dieline (3), PrinterDieline (1), PackagingElement (1) |
| External dependencies | 7 keys (2 🔴 · 3 🟡 · 2 🔵) | search/attachment 🔴; relationship/user-profile/tag 🟡 |
| Federation contributions | 1 (Product) | internal (co-located) |
| Total stories | 23 | green-field (G-06 test coverage tracked outside Jira pipeline) |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 PKG-BE-E-01 — updatePackaging (multi-step write) | SPIKE-01 | Non-Atomic Write Saga |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20% buffer) |
| --- | --- | --- | --- |
| B | Core Reads | 6 | 7–14d |
| C | Search & Listing | 1 | 2–5d |
| D | Mutations | 9 | 16–31d |
| E | Complex Operations | 1 | 5–8d |
| F | Federation & Stitching | 1 | 1–2d |
| G | Field Resolvers & Tests | 5 | 13–25d |
| Total | — | 23 | 44–85d (buffered) |

ℹ️  Computed live from be-04-stories.md (phase + complexity per story) — always reconciles with the story tables below and the program overview. Effort = sum of per-story nominal day-ranges (Low 1–2 · Medium 2–4 · High 4–7 · Very High 7–12) × 1.2 buffer, AI-estimated — confirm in refinement. See each story's Depends On column for real sequencing.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~10–17 sprints | sequential |
| 2 engineers | ~6–10 sprints | reads + mutations parallel after B-01 |
| 3 engineers | ~4–7 sprints | critical path A → E-01 → G-04 → G-05 |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 1 | B-01 (DGS module init + service wiring + first resolver) | schema, service port, core reads |
| 2 | B-04–B-06 + C-01 + D-02/D-05–D-07 | master-data + search + simple mutations |
| 3 | D-01/D-03/D-04/D-08/D-09 | create/bulk/clone/component-status |
| 4 | E-01 + F-01 | multi-step update + Product links |
| 5 | G-01–G-03 | ACL/users/refs field resolvers |
| 6 | G-04/G-05 | pricing + dieline resolvers. Test coverage/parity tracked outside this Jira pipeline, created manually. |

Recommended Implementation Order

Derived from each story's Depends On edges (plus the module-init scaffold as the implicit first step). A story appears in the earliest step where everything it depends on is already done; stories in the same step are independent of each other and parallelize across engineers. Focus names the phase category each step advances — same convention as the frontend order map.

🔬 spike gates and ⛔ cross-subgraph blocks are entry criteria, not ordering edges — a gated story slides later without reshuffling the map.

| Step | Stories (parallel set) | Entry gates in this step | Focus |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | 🧱 Module init — schema skeleton, service wiring (unblocks everything) |
| 2 | 🟢 B-02, 🟢 B-03, 🟢 B-04, 🟢 B-05, 🟢 B-06, 🟡 C-01, 🟡 D-01, 🟢 D-02, 🟡 D-03, 🟡 D-04, 🟢 D-05, 🟢 D-06, 🟢 D-07, 🟡 D-08, 🟢 D-09, 🟠 E-01, 🟢 F-01, 🟡 G-01, 🟢 G-02, 🟡 G-03, 🟠 G-04, 🟡 G-05 | E-01 → 🔬 SPIKE-01 · ⛔ BLOCKED-BY product (PRODUCT-BE-E-00, the shared WriteSaga module) | Fan-out — 📖 Core Reads · 🔍 Search & Listing · ✏️ Mutations · ⚙️ Complex Operations · 🔗 Federation & Stitching · 🧪 Field Resolvers & Tests |

Critical path: B-01 → B-02 — 2 sequential stories; everything else hangs off this chain in parallel.

Recommended Story Graph — 1 Backend Engineer

The order map above assumes unlimited parallelism; this packs the same dependency graph onto 1 backend engineer (greedy critical-chain scheduling, nominal day-ranges from complexity — confirm in refinement). Read each column top-to-bottom as one engineer's queue; ⏳ marks a slot that waits on a dependency, 🔬/⛔ are entry gates that slide a slot without reshuffling the lanes.

| Slot | 👤 BE-1 |
| --- | --- |
| 1 | 🟢 B-01 (1–2d) |
| 2 | 🟠 E-01 (4–7d) 🔬 ⛔ |
| 3 | 🟠 G-04 (4–7d) |
| 4 | 🟡 C-01 (2–4d) |
| 5 | 🟡 D-01 (2–4d) |
| 6 | 🟡 D-03 (2–4d) |
| 7 | 🟡 D-04 (2–4d) |
| 8 | 🟡 D-08 (2–4d) |
| 9 | 🟡 G-01 (2–4d) |
| 10 | 🟡 G-03 (2–4d) |
| 11 | 🟡 G-05 (2–4d) |
| 12 | 🟢 B-02 (1–2d) |
| 13 | 🟢 B-03 (1–2d) |
| 14 | 🟢 B-04 (1–2d) |
| 15 | 🟢 B-05 (1–2d) |
| 16 | 🟢 B-06 (1–2d) |
| 17 | 🟢 D-02 (1–2d) |
| 18 | 🟢 D-05 (1–2d) |
| 19 | 🟢 D-06 (1–2d) |
| 20 | 🟢 D-07 (1–2d) |
| 21 | 🟢 D-09 (1–2d) |
| 22 | 🟢 F-01 (1–2d) |
| 23 | 🟢 G-02 (1–2d) |

BE-1: B-01 → E-01 → G-04 → C-01 → D-01 → D-03 → D-04 → D-08 → G-01 → G-03 → G-05 → B-02 → B-03 → B-04 → B-05 → B-06 → D-02 → D-05 → D-06 → D-07 → D-09 → F-01 → G-02

Elapsed (nominal midpoints): ~54 working days.

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (6 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 PKG-BE-B-01 getPackagings(...) | 🟢 Low [XS] | Query | — | Intent — List packagings with paging and filters. Today — getPackagings() → paged Done when: • all 7 filter args forwarded; defaults page=0/size=10000 |
| 🔷 PKG-BE-B-02 getPackagingById(packagingId) | 🟢 Low [XS] | Query | B-01 | Intent — Fetch one packaging by id. Today — token → getPackagingById Done when: • returns packaging; miss→null |
| 🔷 PKG-BE-B-03 getDielines(...) | 🟢 Low [XS] | Query | B-01 | Intent — List dielines (print layouts) for a packaging. Today — getDielines → .dielines Done when: • filters forwarded; returns the dielines array |
| 🔷 PKG-BE-B-04 getPackagingFieldValuesByType(type, ids) | 🟢 Low [XS] | Query | B-01 | Intent — Return packaging field-value lookups by type. Today — getPackagingFieldValuesByType(type, ids) Done when: • by type (+optional ids) |
| 🔷 PKG-BE-B-05 getDielineEvaluationStatuses (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the dieline evaluation-status lookup (cached). Today — getDielineEvaluationStatuses() Done when: • returns statuses; cached |
| 🔷 PKG-BE-B-06 getCountries(codes) (cacheable) | 🟢 Low [XS] | Query | B-01 | Intent — Return the country lookup (cached). Today — getCountries(codes) Done when: • returns countries (optionally filtered by codes) |

ℹ️  PKG-BE-B-01: Note — DGS Module Init (this PR only): Creates packaging.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [be-03-schema.graphql](./be-03-schema.graphql).

🔍 Phase C — Search & Listing  (1 story)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 PKG-BE-C-01 getPackagingElastic(parentHumanId) | 🟡 Medium [M] | Query Calls: search | B-01 | Intent — Search a product's packagings via elastic. Today — (search) search.getPackagingElastic → .content. EXT: search Done when: • parentId: elastic query built; returns content |

✏️ Phase D — Mutations  (9 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔶 PKG-BE-D-01 addPackaging | 🟡 Medium [M] | Mutation | B-01 | Intent — Create a packaging. Today — POST packaging/v1. Throw on validationErrors/message Done when: • creates • validation error → exception |
| 🔶 PKG-BE-D-02 evaluateDieline | 🟢 Low [XS] | Mutation | B-01 | Intent — Trigger evaluation of a dieline. Today — PUT packaging/v1/dielines/{dielineId}/evaluate Done when: • evaluates the dieline |
| 🔶 PKG-BE-D-03 bulkAddPackagings | 🟡 Medium [M] | Mutation | B-01 | Intent — Create many packagings at once. Today — bulkAddPackagings. Throw on validationErrors/message Done when: • bulk creates • error → throw |
| 🔶 PKG-BE-D-04 bulkUpdatePackagings | 🟡 Medium [M] | Mutation | B-01 | Intent — Update many packagings at once. Today — token for packaging[].humanId → bulkUpdatePackagings. Throw on error Done when: • bulk updates • error → throw |
| 🔶 PKG-BE-D-05 exportPackaging | 🟢 Low [XS] | Mutation | B-01 | Intent — Kick off a packaging export. Today — token → requestPackagingExport({workspace_id, workspace_description, product_ids}) → request id Done when: • returns the export request id |
| 🔶 PKG-BE-D-06 lockPackaging | 🟢 Low [XS] | Mutation | B-01 | Intent — Lock a packaging from edits. Today — token → PUT packaging/v1/{id}/lock Done when: • locks |
| 🔶 PKG-BE-D-07 unlockPackaging | 🟢 Low [XS] | Mutation | B-01 | Intent — Unlock a packaging. Today — token → PUT packaging/v1/{id}/unlock Done when: • unlocks |
| 🔶 PKG-BE-D-08 cloneFilesForDielines | 🟡 Medium [M] | Mutation Calls: attachment | B-01 | Intent — Copy attachment files for dielines. Today — token → Promise.all(attachmentIds.map(id => (attachment) cloneAttachmentV3({cloneReferences}, id))), flatten. EXT: attachment Done when: • clones each id with the shared cloneReferences |
| 🔶 PKG-BE-D-09 updatePackagingComponentStatus | 🟢 Low [XS] | Mutation | B-01 | Intent — Update component status on packagings. Today — updatePackagingComponentStatus({productId, ids, status}). No JWT — confirm backend-enforced Done when: • updates statuses • no-token behaviour documented |

⚙️ Phase E — Complex Operations  (1 story)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔶 PKG-BE-E-01 updatePackaging (multi-step write) 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: attachment, relationship | SPIKE-01, B-01 | Intent — Edit a packaging — a multi-step write (body + attachments + relationships) with no rollback today. Today — token; set humanId=packagingId; PUT packaging/v1 (body); 2) if attachmentsToRemove → (attachment) archiveAttachmentBulkV2 + (relationship) removeRelationship; 3) if… Done when: • all branches in order • add rejects on status≥400; remove error handling decided • partial-failure strategy | ☐ body-only ☐ remove ☐ add ☐ status≥400 ☐ partial-failure ☐ Parity: DGS response matches spark-internal-graphql baseline |

🔗 Phase F — Federation & Stitching  (1 story)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 PKG-BE-F-01 Product packaging links (internal, same subgraph) | 🟢 Low [XS] | Field Resolver | B-01 | Intent — Expose a product's packagings on the Product type (same subgraph). Today — Product references packaging (e.g. components(...packaging), packaging attributes) from the co-located packaging service Done when: • resolves in-process; no gateway hop • Field resolver uses a MappedBatchLoader<String, List<SPARK_Packaging>> (packagingByProductIdLoader) — when the parent query returns N products, packaging is resolved in 1 batched call (not N) |

🧪 Phase G — Field Resolvers & Tests  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 PKG-BE-G-01 access + businessPartner + participantDetails | 🟡 Medium [M] | Field Resolver Calls: vmm, userGroup | B-01 | Intent — Resolve a packaging's access / partner / participant fields. Done when: • each resolves; null-safe | — |
| 🔸 PKG-BE-G-02 createdBy + updatedBy + dielineEvaluators | 🟢 Low [XS] | Field Resolver Calls: userAttributes | B-01 | Intent — Resolve the people fields on a packaging. Done when: • each resolves; null id → null | — |
| 🔸 PKG-BE-G-03 product + workspaces + attachments | 🟡 Medium [M] | Field Resolver Calls: search | B-01 | Intent — Resolve a packaging's product, workspaces and attachments. Done when: • product null when not PID* • workspaces/attachments via elastic | — |
| 🔸 PKG-BE-G-04 suggestedRetailPriceByDPCI + waveDescription + retailPrice | 🟠 High [L] | Field Resolver Calls: tag, apex | B-01 | Intent — Resolve pricing fields (the dieline→DPCI→price chain). Today — suggestedRetailPriceByDPCI — gated on requiresSuggestedRetailPrice + a BP id: - collect printer ids from packagingElements → getDielines(printerIds) → unique dpcis →… Done when: • price chain matches source; gate honored • wave tag fallback • retailPrice→0 | ☐ price chain ☐ gate ☐ wave ☐ retailPrice |
| 🔸 PKG-BE-G-05 Dieline + PrinterDieline + PackagingElement field resolvers | 🟡 Medium [M] | Field Resolver Calls: attachment, search, userAttributes | B-01 | Intent — Resolve the dieline / printer-dieline / element sub-type fields. Done when: • each field resolves to the right source | — |

Frontend

# Federated GraphQL Breakdown — Packaging · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (co-located) |
| Total FE Stories | 5 |
| Impact | 🔴 1 High · 🟡 3 Medium · 🟢 1 Low |
| Estimated effort | 21–33 days (single-engineer) |
| Phase-1 surface | 21 operation-to-root-field rows · 5 client files · 8 components |
| Generated | 2026-07-21 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Packaging GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (co-located)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| PKG-FE-001 | Migrate packaging reads | Query migration | 🟡 Medium | 5–8 days | PKG-BE-B-01, PKG-BE-B-02, PKG-BE-G-01, PKG-BE-G-02, PKG-BE-G-04 | getPackagings, getPackagingById, getPackagingComponentStatus |
| PKG-FE-002 | Migrate packaging master-data reads and retire deprecated fields | Query migration | 🟢 Low | 2–3 days | PKG-BE-B-04, PKG-BE-B-06 | getCountries, getPackagingFieldValuesByType |
| PKG-FE-003 | Migrate dieline flows | Query + mutation migration | 🟡 Medium | 4–6 days | PKG-BE-B-03, PKG-BE-B-05, PKG-BE-D-02, PKG-BE-G-05 | getDielines, getDielineEvaluationStatuses, evaluateDieline |
| PKG-FE-004 | Migrate packaging simple mutations and export | Mutation migration | 🟡 Medium | 5–8 days | PKG-BE-D-01, PKG-BE-D-03, PKG-BE-D-04, PKG-BE-D-05, PKG-BE-D-06, PKG-BE-D-07, PKG-BE-D-09 | addPackaging, bulkAddPackagings, bulkUpdatePackagings, exportPackaging, lockPackaging, unlockPackaging, updatePackagingComponentStatus |
| PKG-FE-005 | Migrate updatePackaging saga handling and packet information | Mutation migration (complex) | 🔴 High | 5–8 days | PKG-BE-E-01 | updatePackaging, getPackagingPacketsInformation, getPackagingPacketInformation |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🟢 PKG-FE-002 | PKG-FE-002 → PKG-BE-B-04, PKG-BE-B-06 | Reads cutover — needs backend phase A/B reads live |
| 3 | 🟡 PKG-FE-004 | PKG-FE-004 → PKG-BE-D-01, PKG-BE-D-03, PKG-BE-D-04, PKG-BE-D-05 (+3) | Writes — needs backend phase D mutations |
| 4 | 🟡 PKG-FE-001, 🟡 PKG-FE-003, 🔴 PKG-FE-005 | PKG-FE-001 → PKG-BE-B-01, PKG-BE-B-02, PKG-BE-G-01, PKG-BE-G-02 (+1)<br>PKG-FE-003 → PKG-BE-B-03, PKG-BE-B-05, PKG-BE-D-02, PKG-BE-G-05<br>PKG-FE-005 → PKG-BE-E-01 | Complex writes / sagas — needs backend phase E + ADR ratification |

Cutover flow: PKG-FE-002 → PKG-FE-004 → PKG-FE-001 → PKG-FE-003 → PKG-FE-005.

Recommended Story Graph — 1 Frontend Engineer

The staged order map above, run by one frontend engineer. Steps re-sync at each stage because the stage's backend gate — not engineer availability — is the limiter.

| Step | 👤 FE-1 | Backend gate (focus) |
| --- | --- | --- |
| 1 | 🟢 PKG-FE-002 (2–3d) | Reads cutover — needs backend phase A/B reads live |
| 3 | 🟡 PKG-FE-004 (5–8d) | Writes — needs backend phase D mutations |
| 4 | 🟡 PKG-FE-001 (5–8d)<br>🔴 PKG-FE-005 (5–8d)<br>🟡 PKG-FE-003 (4–6d) | Complex writes / sagas — needs backend phase E + ADR ratification |

Elapsed (nominal midpoints): ~27 FE build days — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-packaging.md — the combined Backend + Frontend breakdown this section lives in.