Federated GraphQL Breakdown — Product

Target DGS: plm-product (host)  ·  spark-internal-graphql → Netflix DGS Federation

| Total Stories 69 | T-Shirt Size XXL | Complexity 🔴 5 🟠 4 🟡 27 🟢 33 | Phases B, C, D, E, F, G, H |
| --- | --- | --- | --- |

Target DGS: plm-product (host)   |   Generated: 2026-07-21

🔷 Query · 🔶 Mutation · 🔸 Field Resolver   🔴 Very High · 🟠 High · 🟡 Medium · 🟢 Low   🔴🔬 spike-gated · 📖 B · 🔍 C · ✏️ D · ⚙️ E · 🔗 F · 🧪 G

Backend

What Are We Building?

- We are moving Product — the central entity of the PLM system — off the spark-internal-graphql gateway into the `plm-product` Netflix DGS. - Product is the largest and highest-risk domain (18 queries, 20 mutations, ~50 field resolvers on a 2,629-line resolver) and the host service for the whole product family: BOM, Measurement, Impression, Packaging and others live in the same DGS, so their links from Product resolve internally rather than across the federation gateway.

- Most of the work is mechanical (the long tail of CRUD and simple field resolvers), but a handful of items carry real risk: the TechPack count query (a ~200-line, 14-step aggregation spanning 8 domains' data via 4 physical services, which becomes a federated composite-key entity), the partner drop/undrop orchestration, the cross-domain components and attachmentsWithMetaData field resolvers, and a latent `division` bug. - We recommend the facade-then-federate approach for TechPack (draft ADR-015 Option B; the pattern techpack-migration-options.md labels "Option D (hybrid)"): ship a thin query over a temporary aggregation facade so it works on day 1, then federate each piece to its owning domain, then retire the facade (F-09).

ACL note: the legacy gateway obtains per-resource capability tokens via ACL on nearly every call. Per ADR-019 (complexStories/acl/01-adr-acl-mid-request-update.md), permission-check and own-domain-token call sites stay resolver-local (context-only, unchanged); downstream-token call sites — where a resolver hands its token to a different domain's loader — use Mid-Request ACL Update (SparkSecurityService.updateCurrentUserPermissions(capabilityToken)) before the downstream call.

Migration Scope

| Surface | Count | Notes |
| --- | --- | --- |
| Queries | 18 | incl. TechPack (Very High) and two-stage getProducts |
| Mutations | 20 (+3 deferred) | incl. partner actions + component fan-out |
| Field-resolver stories | ~16 | incl. 2 X-Large (attachmentsWithMetaData, components) |
| External dependencies | 12 EXT + 6 platform | search/attachment/workspace 🔴 |
| Composite-key aggregate | 1 (TechPack ResourcesCount) | 8 sibling subgraphs extend it |
| Federation contributions received | 8 | from sibling domains (Phase F placeholders) |
| Total stories | 67 | green-field build stories (G-11 split into G-11-1/G-11-2 = +1). The 3 Phase-0 spike stubs (S-01–S-03) are tracked as program spikes in the global breakdown and Jira, not as rows here |

Spikes & Complex Cases

This domain's complex, cross-cutting problems are tracked once as program spikes in the global breakdown — see 'Phase 0 — Program Spikes' and 'Spike Detail' (the brief, the decision, intended cross-domain steps, and every affected resolver's external deps + current logic) in Federated+Graphql+Stories+-+BreakDown. Nothing from there is repeated here; the stories below just link to it. Follow a story's SPIKE-0x id to the global Spike Detail for the target flow + the external services each resolver calls (see 'How to read the spikes & related stories' in the global doc).

| Story | Program spike | Bucket |
| --- | --- | --- |
| 🔴🔬 PRODUCT-BE-B-10 — getProductDeptRules(productIds, departmentIds, activeOnly) | SPIKE-07 | Product Rules API Ownership |
| 🔴🔬 PRODUCT-BE-B-11 — getProductBPRules(productIds, businessPartnerIds, activeOnly) | SPIKE-07 | Product Rules API Ownership |
| 🔴🔬 PRODUCT-BE-C-01 — getProducts(...) two-stage hydration | SPIKE-06a | Hydration |
| 🔴🔬 PRODUCT-BE-C-05 — searchProductRules(...) | SPIKE-07 | Product Rules API Ownership |
| 🔴🔬 PRODUCT-BE-D-01 — addProduct | SPIKE-06b | Cross-Domain Association |
| 🔴🔬 PRODUCT-BE-D-02 — addProducts (bulk) | SPIKE-06b | Cross-Domain Association |
| 🔴🔬 PRODUCT-BE-D-04 — updateProduct | SPIKE-06b | Cross-Domain Association |
| 🔴🔬 PRODUCT-BE-E-00 — WriteSaga shared module (Sprint 0, critical path) | SPIKE-01 | Non-Atomic Write Saga |
| 🔴🔬 PRODUCT-BE-E-01 — productBusinessPartnerActions (REMOVE/DROP/UNDROP) | SPIKE-03 | Partner Drop/Undrop + Ownership |
| 🔴🔬 PRODUCT-BE-E-02 — updateComponentStatuses (5-loader fan-out) | SPIKE-01 | Non-Atomic Write Saga |
| 🔴🔬 PRODUCT-BE-E-03 — getProductTechPackCountV1 stub + aggregation facade (facade-then-federate, Phase 1) | SPIKE-02 | TechPack Aggregate |
| 🔴🔬 PRODUCT-BE-E-04 — getProductTechPackBulkCountV1 (bulk wrapper, ordering fix) | SPIKE-02 | TechPack Aggregate |
| 🔴🔬 PRODUCT-BE-G-07 — Product.vendorAttributes + businessPartners + droppedPartners + unDroppablePartners + status | SPIKE-04 | Not-Removable / Undroppable Partners |
| 🔴🔬 PRODUCT-BE-G-11-1 — Product.notRemovablePartnerIds + notRemovableWorkspaceIds | SPIKE-04 | Not-Removable / Undroppable Partners |

Simple, intuitive decisions (drift-op cleanup, dead-method audits, auth-token parity, sort/DTO shape) are resolved inline in the owning story — they are not spikes.

Effort Snapshot by Phase

| Phase | Name | Stories | Effort (est., +20% buffer) |
| --- | --- | --- | --- |
| B | Core Reads | 11 | 13–26d |
| C | Search & Listing | 5 | 14–28d |
| D | Mutations | 18 | 28–55d |
| E | Complex Operations | 5 | 35–60d |
| F | Federation & Stitching | 8 | 10–19d |
| G | Field Resolvers & Tests | 16 | 52–97d |
| H | Entity Resolution | 6 | 14–29d |
| Total | — | 69 | 166–314d (buffered) |

ℹ️  Computed live from be-04-stories.md (phase + complexity per story) — always reconciles with the story tables below and the program overview. Effort = sum of per-story nominal day-ranges (Low 1–2 · Medium 2–4 · High 4–7 · Very High 7–12) × 1.2 buffer, AI-estimated — confirm in refinement. See each story's Depends On column for real sequencing.

Capacity Planning

| Team size | Calendar | Notes |
| --- | --- | --- |
| 1 engineer | ~39–66 sprints | sequential — not recommended for this domain |
| 2 engineers | ~25–42 sprints | B/C/D parallel after B-01 |
| 3–4 engineers | ~18–28 sprints | A done → B + C + D + most of G in parallel; E and the two X-Large fields on dedicated owners |

Recommended Sprint Sequencing

| Sprint | Stories | Focus |
| --- | --- | --- |
| 0 | Program spikes | run in Sprint 0 (see global Phase 0 — Program Spikes) so D/C/E work isn't waiting |
| 1–2 | B-01 (DGS module init + service wiring + first resolver) | schema, types, stubs, Categories resolver, ResourcesCount, service port |
| 3 | B-01–B-11 | all core reads (incl. rules reads) |
| 4 | C-01–C-05 | search/listing + rating + rules search (C-01 needs SPIKE-06a concluded) |
| 5–6 | D-01–D-18 | all simple mutations, parallelizable (D-01/D-02/D-04 need SPIKE-06b concluded; D-03/D-06/D-07/D-11 unblocked) |
| 7–8 | E-03/E-04 | TechPack facade + bulk (focused; facade-then-federate direction already resolved, draft ADR-015) |
| 9 | E-00 (shared WriteSaga module, Sprint-0 critical path) + E-01/E-02 | partner actions (needs SPIKE-03 concluded) + component fan-out |
| 10–12 | G-01–G-10, G-11-1, G-11-2, G-13–G-14 | field resolvers (G-01/G-02 X-Large get their own sprint) |
| 13 | G-15 | utils port (Kotlin). Test coverage/parity/load/cut-over rehearsal tracked outside this Jira pipeline, created manually. |
| post-launch | H-01–H-06, F-09 | TechPack federation (unblocked as siblings migrate) + facade retirement |
| any | F-10–F-12 | gateway composition + platform verify + drift decision |

Recommended Implementation Order

Derived from each story's Depends On edges (plus the module-init scaffold as the implicit first step). A story appears in the earliest step where everything it depends on is already done; stories in the same step are independent of each other and parallelize across engineers. Focus names the phase category each step advances — same convention as the frontend order map.

🔬 spike gates and ⛔ cross-subgraph blocks are entry criteria, not ordering edges — a gated story slides later without reshuffling the map.

| Step | Stories (parallel set) | Entry gates in this step | Focus |
| --- | --- | --- | --- |
| 1 | 🟢 B-01 | — | 🧱 Module init — schema skeleton, service wiring (unblocks everything) |
| 2 | 🟢 B-02, 🟢 B-03, 🟢 B-04, 🟢 B-05, 🟢 B-06, 🟢 B-07, 🟢 B-08, 🟢 B-09, 🟢 B-10, 🟢 B-11, 🟠 C-01, 🟡 C-02, 🟡 C-03, 🟡 C-04, 🟡 C-05, 🟡 D-01, 🟡 D-02, 🟡 D-03, 🟡 D-04, 🟡 D-05, 🟢 D-06, 🟢 D-07, 🟢 D-08, 🟢 D-09, 🟢 D-10, 🟢 D-11, 🟢 D-12, 🟢 D-13, 🟢 D-14, 🟢 D-15, 🟢 D-16, 🟢 D-17, 🟢 D-18, 🟠 E-00, 🔴 E-03, 🟢 F-14, 🔴 G-01, 🔴 G-02, 🟡 G-04, 🟡 G-05, 🟡 G-06, 🟡 G-07, 🟡 G-08, 🟡 G-09, 🟡 G-10, 🟡 G-11-1, 🟡 G-11-2, 🟡 G-13, 🟢 G-14, 🟡 G-15, 🟡 H-06 | B-10 → 🔬 SPIKE-07<br>B-11 → 🔬 SPIKE-07<br>C-01 → 🔬 SPIKE-06a<br>C-05 → 🔬 SPIKE-07<br>D-01 → 🔬 SPIKE-06b<br>D-02 → 🔬 SPIKE-06b<br>D-04 → 🔬 SPIKE-06b<br>E-00 → 🔬 SPIKE-01<br>E-03 → 🔬 SPIKE-02<br>G-07 → 🔬 SPIKE-04<br>G-11-1 → 🔬 SPIKE-04 | Fan-out — 📖 Core Reads · 🔍 Search & Listing · ✏️ Mutations · ⚙️ Complex Operations · 🔗 Federation & Stitching · 🧪 Field Resolvers & Tests · 🧬 Entity Resolution |
| 3 | 🔴 E-01, 🟠 E-02, 🔴 E-04, 🟢 F-04, 🟢 F-06, 🟢 F-08, 🟢 F-10, 🟠 G-03, 🟡 G-17, 🟡 H-01, 🟡 H-02, 🟡 H-03, 🟡 H-04, 🟡 H-05 | E-01 → 🔬 SPIKE-03<br>E-02 → 🔬 SPIKE-01<br>E-04 → 🔬 SPIKE-02<br>H-01 → ⛔ BLOCKED-BY attachment domain (⛔ cross-subgraph — does not ship until plm-attachment is live)<br>H-02 → ⛔ BLOCKED-BY discussion domain (⛔ cross-subgraph)<br>H-03 → ⛔ BLOCKED-BY sample domain (⛔ cross-subgraph)<br>H-04 → ⛔ BLOCKED-BY claim domain (⛔ cross-subgraph)<br>H-05 → ⛔ BLOCKED-BY construction domain (⛔ cross-subgraph) | Fan-out — ⚙️ Complex Operations · 🔗 Federation & Stitching · 🧪 Field Resolvers & Tests · 🧬 Entity Resolution |
| 4 | 🟢 F-09, 🟢 F-11, 🟢 F-12 | — | 🔗 Federation & Stitching |

Critical path: B-01 → E-03 → F-04 → F-09 — 4 sequential stories; everything else hangs off this chain in parallel.

Recommended Story Graph — 1 Backend Engineer

The order map above assumes unlimited parallelism; this packs the same dependency graph onto 1 backend engineer (greedy critical-chain scheduling, nominal day-ranges from complexity — confirm in refinement). Read each column top-to-bottom as one engineer's queue; ⏳ marks a slot that waits on a dependency, 🔬/⛔ are entry gates that slide a slot without reshuffling the lanes.

| Slot | 👤 BE-1 |
| --- | --- |
| 1 | 🟢 B-01 (1–2d) |
| 2 | 🔴 E-03 (7–12d) 🔬 |
| 3 | 🟠 E-00 (4–7d) 🔬 |
| 4 | 🔴 G-01 (7–12d) |
| 5 | 🔴 E-01 (7–12d) 🔬 |
| 6 | 🔴 E-04 (7–12d) 🔬 |
| 7 | 🔴 G-02 (7–12d) |
| 8 | 🟡 H-06 (2–4d) |
| 9 | 🟠 C-01 (4–7d) 🔬 |
| 10 | 🟠 E-02 (4–7d) 🔬 |
| 11 | 🟠 G-03 (4–7d) |
| 12 | 🟢 F-14 (1–2d) |
| 13 | 🟡 H-01 (2–4d) ⛔ |
| 14 | 🟡 H-02 (2–4d) ⛔ |
| 15 | 🟡 H-03 (2–4d) ⛔ |
| 16 | 🟡 H-04 (2–4d) ⛔ |
| 17 | 🟡 H-05 (2–4d) ⛔ |
| 18 | 🟡 C-02 (2–4d) |
| 19 | 🟡 C-03 (2–4d) |
| 20 | 🟡 C-04 (2–4d) |
| 21 | 🟡 C-05 (2–4d) 🔬 |
| 22 | 🟡 D-01 (2–4d) 🔬 |
| 23 | 🟡 D-02 (2–4d) 🔬 |
| 24 | 🟡 D-03 (2–4d) |
| 25 | 🟡 D-04 (2–4d) 🔬 |
| 26 | 🟡 D-05 (2–4d) |
| 27 | 🟢 F-04 (1–2d) |
| 28 | 🟢 F-06 (1–2d) |
| 29 | 🟢 F-08 (1–2d) |
| 30 | 🟢 F-10 (1–2d) |
| 31 | 🟡 G-04 (2–4d) |
| 32 | 🟡 G-05 (2–4d) |
| 33 | 🟡 G-06 (2–4d) |
| 34 | 🟡 G-07 (2–4d) 🔬 |
| 35 | 🟡 G-08 (2–4d) |
| 36 | 🟡 G-09 (2–4d) |
| 37 | 🟡 G-10 (2–4d) |
| 38 | 🟡 G-11-1 (2–4d) 🔬 |
| 39 | 🟡 G-11-2 (2–4d) |
| 40 | 🟡 G-13 (2–4d) |
| 41 | 🟡 G-15 (2–4d) |
| 42 | 🟡 G-17 (2–4d) |
| 43 | 🟢 B-02 (1–2d) |
| 44 | 🟢 B-03 (1–2d) |
| 45 | 🟢 B-04 (1–2d) |
| 46 | 🟢 B-05 (1–2d) |
| 47 | 🟢 B-06 (1–2d) |
| 48 | 🟢 B-07 (1–2d) |
| 49 | 🟢 B-08 (1–2d) |
| 50 | 🟢 B-09 (1–2d) |
| 51 | 🟢 B-10 (1–2d) 🔬 |
| 52 | 🟢 B-11 (1–2d) 🔬 |
| 53 | 🟢 D-06 (1–2d) |
| 54 | 🟢 D-07 (1–2d) |
| 55 | 🟢 D-08 (1–2d) |
| 56 | 🟢 D-09 (1–2d) |
| 57 | 🟢 D-10 (1–2d) |
| 58 | 🟢 D-11 (1–2d) |
| 59 | 🟢 D-12 (1–2d) |
| 60 | 🟢 D-13 (1–2d) |
| 61 | 🟢 D-14 (1–2d) |
| 62 | 🟢 D-15 (1–2d) |
| 63 | 🟢 D-16 (1–2d) |
| 64 | 🟢 D-17 (1–2d) |
| 65 | 🟢 D-18 (1–2d) |
| 66 | 🟢 F-09 (1–2d) |
| 67 | 🟢 F-11 (1–2d) |
| 68 | 🟢 F-12 (1–2d) |
| 69 | 🟢 G-14 (1–2d) |

BE-1: B-01 → E-03 → E-00 → G-01 → E-01 → E-04 → G-02 → H-06 → C-01 → E-02 → G-03 → F-14 → H-01 → H-02 → H-03 → H-04 → H-05 → C-02 → C-03 → C-04 → C-05 → D-01 → D-02 → D-03 → D-04 → D-05 → F-04 → F-06 → F-08 → F-10 → G-04 → G-05 → G-06 → G-07 → G-08 → G-09 → G-10 → G-11-1 → G-11-2 → G-13 → G-15 → G-17 → B-02 → B-03 → B-04 → B-05 → B-06 → B-07 → B-08 → B-09 → B-10 → B-11 → D-06 → D-07 → D-08 → D-09 → D-10 → D-11 → D-12 → D-13 → D-14 → D-15 → D-16 → D-17 → D-18 → F-09 → F-11 → F-12 → G-14

Elapsed (nominal midpoints): ~200 working days.

Jira Stories by Phase

Each row is one Jira story. Complexity drives T-shirt sizing in refinement. 'Depends On' lists blocking story IDs within this domain.

📖 Phase B — Core Reads  (11 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔷 PRODUCT-BE-B-01 getProduct(id) | 🟢 Low [XS] | Query | — | Intent — Looks up a single product by id (the core product read everything else builds on). Today — getByID GET ${v1}?productId={id} → camelCase or null; DataLoader-batched Done when: • returns product; 404→null • batches N ids in 1 call |
| 🔷 PRODUCT-BE-B-02 getProductsByIds(ids) | 🟢 Low [XS] | Query | — | Intent — Looks up several products at once by their ids. Today — getByIdList GET ${v1}?productId={csv}&page=0&size=10000&sort=createdDate,desc; primes getByID Done when: • returns paged products for ids • primes single-id loader |
| 🔷 PRODUCT-BE-B-03 getProductStatus (cacheable) | 🟢 Low [XS] | Query | — | Intent — Returns the list of possible product statuses (dropdown options). Today — getStatus master status list Done when: • returns statuses • cached |
| 🔷 PRODUCT-BE-B-04 getProductVersions(id) | 🟢 Low [XS] | Query | — | Intent — Lists the saved versions of a product. Today — getVersions GET ${v1}/{id}/versions?page=0&size=10000 Done when: • returns versions |
| 🔷 PRODUCT-BE-B-05 getCopyStatus(id) | 🟢 Low [XS] | Query | — | Intent — Tells you whether a product copy is still in progress or done. Today — getCopyStatus GET ${v2}/count/resource-type?copyId={id} Done when: • returns copy status |
| 🔷 PRODUCT-BE-B-06 getProductTemplateById(id) | 🟢 Low [XS] | Query | — | Intent — Looks up a product template by id. Today — getByID → response \¦\¦ {} (empty object on miss — preserve) Done when: • returns product or empty object (not null) |
| 🔷 PRODUCT-BE-B-07 getProductRules | 🟢 Low [XS] | Query | — | Intent — Returns the product business rules. Today — getAllRules GET $… → content Done when: • returns rules content |
| 🔷 PRODUCT-BE-B-08 getProductRulesById(id) | 🟢 Low [XS] | Query | — | Intent — Looks up one business rule by id. Today — getRuleById GET $… Done when: • returns rule |
| 🔷 PRODUCT-BE-B-09 getAllAvailableRules | 🟢 Low [XS] | Query | — | Intent — Lists all the rules that are available to apply. Today — getAvailableRules GET …/spark_rules/v1/rules Done when: • returns available rules |
| 🔴🔬 🔷 PRODUCT-BE-B-10 getProductDeptRules(productIds, departmentIds, activeOnly) 🔴🔬 Spike-gated on SPIKE-07 (Product Rules API Ownership) | 🟢 Low [XS] | Query Calls: ruleLibrary | SPIKE-07 | Intent — Returns the department-level rules for given products. Today — flag fork USE_NEW_RULES_API ? ruleLibrary.searchRuleLibrary : product.searchProductDeptRules GET …/spark_rules/v1/search?productIds=&departmentIds=&activeOnly=. PO… Done when: • default activeOnly=true • flag selects the correct backend • Scope reconfirmed against S-04's decision before implementation starts |
| 🔴🔬 🔷 PRODUCT-BE-B-11 getProductBPRules(productIds, businessPartnerIds, activeOnly) 🔴🔬 Spike-gated on SPIKE-07 (Product Rules API Ownership) | 🟢 Low [XS] | Query Calls: ruleLibrary | SPIKE-07 | Intent — Returns the business-partner-level rules for given products. Today — same as B-10 with businessPartnerIds Done when: • flag fork honored; BP filter applied • Scope reconfirmed against S-04's decision before implementation starts |

ℹ️  PRODUCT-BE-B-01: Note — DGS Module Init (this PR only): Creates product.graphqls (federation v2.3 header, scalars, owned types with @key, external stubs), registers scalars in ScalarConfig.kt, and wires the service and Feign client. Full type list: [be-03-schema.graphql](./be-03-schema.graphql). This scaffold is a prerequisite for every B/C/D/G story — they need the module + schema file to compile their DGS wrapper — so it is assumed globally (shown once in the dependency graph) and not repeated in each story's Depends On. After it lands, the wrappers parallelize.

🔍 Phase C — Search & Listing  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 🔷 PRODUCT-BE-C-01 getProducts(...) two-stage hydration 🔴🔬 Spike-gated on SPIKE-06a (Hydration) | 🟠 High [L] | Query Calls: search | SPIKE-06a | Intent — List products by combining the search index with the canonical record (two-stage hydration). Today — listing products needs data from two places — the search index (which - knows flags like "has boms", "has claims", workspace membership) and the canonical product… Done when: • parity for 4 arg combos (no flags / all flags / resourceType=workspaces / filter array) • truthy defaults preserved • elastic flags merged onto canonical • Workspace-filter placement and elastic/canonical staleness handling match SPIKE-06a's decision | ☐ 4 combos ☐ default truthiness ☐ merge ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔷 PRODUCT-BE-C-02 getProductTemplates(...) | 🟡 Medium [M] | Query Calls: search | — | Intent — Lists product templates, with optional filters on what to include. Today — (search) getFilteredProductsListing({resourceType:'product', includeBoms:false, ...7 includeXxxTemplates flags, types}) → return elastic response (no 2nd hydration) Done when: • all 7 template-include flags forwarded • types:[Int] filter applied | — |
| 🔷 PRODUCT-BE-C-03 getCategories(...) | 🟡 Medium [M] | Query Calls: search | — | Intent — Returns the category tree for products. Today — default productType ?? 100; (search) getProductCategories GET ${elastic}/search/${snake_case(type)}?resourceType=&resourceId=&productType= → ProductsCategories… Done when: • snake_case(type) path exact • wires to Categories union | — |
| 🔷 PRODUCT-BE-C-04 getRatingByTcin(tcin) (external rating) | 🟡 Medium [M] | Query Calls: rating | — | Intent — Gets the customer rating for a product (from an external ratings service). Today — (external) GET ${RATING_ENDPOINT}?reviewType=product&includes=statistics&reviewedId={tcin}&key={API_KEY} (skipJsonParse) → JSON.parse → {averageRating, reviewCount}… Done when: • parses statistics to Rating • any error → null • API key from config/Vault, not source | — |
| 🔴🔬 🔷 PRODUCT-BE-C-05 searchProductRules(...) 🔴🔬 Spike-gated on SPIKE-07 (Product Rules API Ownership) | 🟡 Medium [M] | Query Calls: ruleLibrary | SPIKE-07 | Intent — Searches product rules. Today — flag fork; legacy GET …/spark_rules/v1/search_mapped?... → productRuleResponseTransformer → camelCase Done when: • flag fork honored • legacy response transformed correctly • Scope reconfirmed against S-04's decision before implementation starts | — |

✏️ Phase D — Mutations  (18 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔴🔬 🔶 PRODUCT-BE-D-01 addProduct 🔴🔬 Spike-gated on SPIKE-06b (Cross-Domain Association) | 🟡 Medium [M] | Mutation Calls: workspaceV2, attachment | SPIKE-06b | Intent — Create a product (optionally copy from another + associate a workspace). Today — POST ${v1} + optional copyProductToProduct(copyProduct) + workspace association Done when: • creates product • optional copy runs when copyProduct present • workspace assoc applied via the shared association component (no bespoke fan-out code) • failure after create (link or copy fails) surfaces per the mutation's declared failure policy — default fail-fast, no rollback, documented (ADR-011 §4) |
| 🔴🔬 🔶 PRODUCT-BE-D-02 addProducts (bulk) 🔴🔬 Spike-gated on SPIKE-06b (Cross-Domain Association) | 🟡 Medium [M] | Mutation Calls: attachment | SPIKE-06b | Intent — Create many products at once (plus attachment links). Today — bulk POST ${v1}/bulk + attachment-link side-effects (no rollback — preserve, flag) Done when: • bulk creates • attachment links applied via the shared association component; no-rollback behaviour documented (compensation deferred to the shared WriteSaga module, PRODUCT-BE-E-00, per ADR-011 pin-down 2) • no resolver import remains; the formerly fire-and-forget attachment re-point is awaited and its failure visible (accepted deviations per ADR-011 §4) |
| 🔶 PRODUCT-BE-D-03 bulkUpdateProducts | 🟡 Medium [M] | Mutation | — | Intent — Update many products in one call. Today — PUT ${v1}/mass_update Done when: • mass-updates products |
| 🔴🔬 🔶 PRODUCT-BE-D-04 updateProduct 🔴🔬 Spike-gated on SPIKE-06b (Cross-Domain Association) | 🟡 Medium [M] | Mutation Calls: attachment | SPIKE-06b | Intent — Edit a product (optional copy + template-attachment cleanup). Today — PUT ${v1}/{id} + optional copy + archive removed-template attachments (template branch) Done when: • updates product • optional copy • removed-template attachments archived (template branch) • attachment archiving applied via the shared association component (no bespoke fan-out code) |
| 🔶 PRODUCT-BE-D-05 carryForwardProduct | 🟡 Medium [M] | Mutation | — | Intent — Carries a product forward (creates the next season/version from it). Today — PUT ${v1}/{productId}/carry_forward/{workspaceId} — uses every field on CarryForwardProductInput Done when: • all input fields mapped to the request |
| 🔶 PRODUCT-BE-D-06 addTeamsToProduct 🔀 Collab Canvas | 🟢 Low [XS] | Mutation | — | Intent — Adds teams (and their partners) to a product. Today — POST ${v1}/{productId}/resources/bulk + manage_workspace_teams Done when: • adds teams + new partners + workspace links • partner-add failure exits early with a thrown typed error (today return new Error(...) — standardized per ADR-011 §4 pin-down 4, accepted deviation); teams are not added after a failed partner add (legacy order preserved) |
| 🔶 PRODUCT-BE-D-07 addBusinessPartnersToProductWithType 🔀 Collab Canvas | 🟢 Low [XS] | Mutation | — | Intent — Adds business partners to a product with a given type. Today — POST ${v1}/{productId}/partners-add/bulk; success = response has product_id and no status_code; failure = log + return new Error(...) (returned, not thrown — surfaces… Done when: • adds partners with type • failure throws a typed DgsException instead of return new Error(...) (accepted parity deviation, ADR-011 §4 pin-down 4) |
| 🔶 PRODUCT-BE-D-08 removeProductResources | 🟢 Low [XS] | Mutation | — | Intent — Removes resources (links) from a product. Today — DELETE ${v1}/{productId}/resources/bulk Done when: • removes resources |
| 🔶 PRODUCT-BE-D-09 updateBusinessPartnerStatuses | 🟢 Low [XS] | Mutation | — | Intent — Updates the status of business partners on a product. Today — PUT ${v1}/{productId}/status_update/bulk Done when: • updates partner statuses |
| 🔶 PRODUCT-BE-D-10 updateViewToggle | 🟢 Low [XS] | Mutation | — | Intent — Toggles whether a product is hidden. Today — PUT ${v1} view toggle Done when: • toggles hidden |
| 🔶 PRODUCT-BE-D-11 updateWorkspaceAttributes 🔀 Collab Canvas | 🟢 Low [XS] | Mutation | — | Intent — Updates a product's workspace attributes. Today — PUT ${v1}/{productId} workspace attrs Done when: • updates workspace attrs |
| 🔶 PRODUCT-BE-D-12 updateProductTeamsWorkspaceContext | 🟢 Low [XS] | Mutation | — | Intent — Adds or removes team↔workspace pairings on a product. Today — PUT team-workspace add/remove Done when: • adds/removes team-workspace pairs |
| 🔶 PRODUCT-BE-D-13 linkProduct | 🟢 Low [XS] | Mutation | — | Intent — Links a parent and child product together. Today — PUT link — throws on backend error (only mutation that does) Done when: • links parent/child • backend error → exception (not null) |
| 🔶 PRODUCT-BE-D-14 unlinkProduct | 🟢 Low [XS] | Mutation | — | Intent — Unlinks a parent and child product. Today — PUT unlink Done when: • unlinks parent/child |
| 🔶 PRODUCT-BE-D-15 addProductRule | 🟢 Low [XS] | Mutation | — | Intent — Creates a product rule. Today — POST …/spark_rules/v1 Done when: • creates rule |
| 🔶 PRODUCT-BE-D-16 updateProductRule | 🟢 Low [XS] | Mutation | — | Intent — Updates a product rule. Today — PUT …/spark_rules/v1/{id} Done when: • updates rule |
| 🔶 PRODUCT-BE-D-17 deleteProductRule | 🟢 Low [XS] | Mutation | — | Intent — Deletes a product rule. Today — DELETE …/spark_rules/v1/{id} → Boolean Done when: • deletes; returns Boolean |
| 🔶 PRODUCT-BE-D-18 updateComponentStatus (bulk) | 🟢 Low [XS] | Mutation | — | Intent — Bulk-updates the status of many components at once. Today — bulk PUT ${v1}/component_status_update/bulk Done when: • bulk-updates component statuses |

⚙️ Phase E — Complex Operations  (5 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔴🔬 📄 PRODUCT-BE-E-00 WriteSaga shared module (Sprint 0, critical path) 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Service | SPIKE-01 | Intent — Build the one shared "ordered steps + per-step failure policy" mechanism every multi-step write in the program will use, instead of nine domains each guessing their own. Done when: • WriteSaga executes ordered steps, stops at the first non-retryable failure, and runs declared compensations (in reverse order) for every already-completed step that has one • Every step's response is checked by construction — there is no code path where a step's result is silently ignored (closes ADR-013 pin-down 5) • finish() returns COMMITTED (all steps succeeded), COMPENSATED (a step failed, compensations ran, no net change), or PARTIAL_FAILURE (a step failed, some compensations don't exist or also failed) — always with per-step detail, never a bare generic error (ADR-013 pin-down 6; surfaced via GraphQL error extensions by each consumer) • Parallel fan-out steps isolate per-branch failures and aggregate a per-branch result — a Promise.all-style first-rejection-wins is not possible through this API (ADR-013 pin-down 7) • Compensation inventory completed and recorded before any consumer story starts: for every step kind in the §4-B policy table, confirm the declared inverse actually exists (workspace associate↔dissociate, relationship add↔remove); anything without a confirmed inverse defaults to RECORD, never assumed (ADR-013 pin-down 1 — this is a blocking pre-condition on every consumer story, not optional polish) • Injected mid-sequence failures in unit tests yield COMPENSATED or PARTIAL_FAILURE with correct per-step detail for at least one COMPENSATE, one RETRY, and one RECORD step in the same saga run • Zero consumer-facing API changes are needed if a later step kind's policy is refined (e.g. Option D's backend-composed atomic endpoints replace a saga step with one call) — the saga's public contract is step-name + action + compensation + policy, nothing consumer-specific leaks in • This story ships alone — no domain's E-phase mutation story is modified here; MST-BE-E-01 (updateMeasurement, the smallest real case) is the designated pilot adopter in its own story, followed by BOM-BE-E-01, PKG-BE-E-01, PDTL-BE-E-01, WATCHLIST-BE-E-01, CLAIM-BE-E-01, PRODUCT-BE-E-02, and the later-phase sample mutations, each per their own story's acceptance criteria | ☐ Unit: a 3-step saga where step 2 fails → step 1's compensation runs, step 3 never runs, result is COMPENSATED ☐ Unit: a step with RETRY(n) policy fails n times then still fails → result is PARTIAL_FAILURE with that step's detail ☐ Unit: a step with RECORD policy fails → saga continues past it (not a hard stop), failure recorded in per-step detail ☐ Unit: a step declares COMPENSATE but its own compensation call also fails → surfaced as PARTIAL_FAILURE, not silently swallowed ☐ Unit: a 5-branch parallel fan-out where 1 branch fails → the other 4 branches' results are still returned, aggregated ☐ Integration: compensation inventory checklist (pin-down 1) run and recorded against real backend endpoints before this story closes |
| 🔴🔬 🔶 PRODUCT-BE-E-01 productBusinessPartnerActions (REMOVE/DROP/UNDROP) 🔴🔬 Spike-gated on SPIKE-03 (Partner Drop/Undrop + Ownership) | 🔴 Very High [XL] | Mutation Calls: sampleV2, recentlyViewed, todo, favorite | SPIKE-03, E-00 | Intent — Remove / drop / undrop a business partner across a product — a ~220-line orchestrated write. Today — removing, dropping, or un-dropping a business partner from a product - isn't one write — it's a ~220-line dispatcher that updates the partner's status and then fans… Done when: • all 3 paths reach REST parity (recorded fixtures), incl. the design-partner branch (skipSamples when partnerType == DESIGN_PARTNER) • partial-failure compensation log/strategy implemented per SPIKE-03's decision (draft ADR-012: per-step policy — partner-status compensate · ACL retry-then-fail · activity/profile retry+reconcile) • cleanup fan-out runs per case, with per-target failure isolation (one cleanup failing is visible and doesn't silently swallow the others) • on DROP, ACL revocation completes before the mutation returns success; on UNDROP, ACL restore precedes participant undrops — proven by an automated test, not convention (ADR-012 §4 ordering constraint) • no Relationship-Service traversal and no UserProfileAttributes resolver import remain in the ported flow (replaced by participant enumeration + a user-profile client call). > Note: ADR-012 pin-down 4 (async-refinement scope — recentlyViewed/todo/favorite/user-profile only, never > ACL or partner status) and pin-down 6 (keep the actionType dispatcher shape for phase-1 parity; splitting > is a v2 API question) are scope/architecture statements, not independently testable behavior — no dedicated > AC needed; honored by construction in the service shape above | ☐ REMOVE ☐ DROP ☐ UNDROP ☐ design-partner branch (samples skipped) ☐ partial-failure per step ☐ ACL-before-return ordering invariant ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔴🔬 🔶 PRODUCT-BE-E-02 updateComponentStatuses (5-loader fan-out) 🔴🔬 Spike-gated on SPIKE-01 (Non-Atomic Write Saga) | 🟠 High [L] | Mutation Calls: claim | SPIKE-01, E-00 | Intent — Update a product's component statuses, fanning out to 5 sibling loaders. Today — updating component statuses fans out to 5 places in parallel (bom, - measurement, productDetail, packaging — all internal — plus claim, external). - The bug: a loop… Done when: • per-loader failures don't fail siblings • shadow var fixed • parity | ☐ 5-way fan-out ☐ partial failure isolation ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔴🔬 🔷 PRODUCT-BE-E-03 getProductTechPackCountV1 stub + aggregation facade (facade-then-federate, Phase 1) 🔴🔬 Spike-gated on SPIKE-02 (TechPack Aggregate) | 🔴 Very High [XL] | Query Calls: attachment, search | SPIKE-02 | Intent — Build the TechPack panel's badge counts by aggregating across ~8 domains. Today — the TechPack panel shows badge counts (attachments, discussions, - samples, boms, claims, etc.) for a product. - Getting those counts today means walking the entire… Done when: • Returns a fully populated 11-field ResourcesCount from the facade for a valid (productId, partnerId, workspaceContext, parentProductId) input • @DgsEntityFetcher(name="ResourcesCount") reconstructs the entity from key + context on an _entities query (federation-ready shell) • Recorded-fixture parity vs spark-internal-graphql for ≥ 5 pinned inputs, including: a product with a parent (double-walk), > 100 walked ids (chunked ACL), a 3D attachment, and a critical thread whose parent discussion is outside the walk — 100% field-value match modulo the ADR-015 §4 deviation list (parallelized elastic/ACL calls; counts unchanged) • Facade is observable: per-slice latency + error metrics and a health endpoint exist (they gate the H-01–H-05 re-homings and the F-09 retirement check) • Facade is behavior-frozen: deviations limited to ADR-015 §4 pin-downs; CODEOWNERS guard in place so new feature work lands in the owning domain's F0x story instead | ☐ facade call returns 11 populated fields ☐ entity fetcher via _entities ☐ parity ≥ 5 pinned inputs (incl. parent double-walk, >100 ids, 3D attachment, out-of-walk critical thread) ☐ per-slice metrics emitted ☐ Integration: full query via DGS test client returns expected shape |
| 🔴🔬 🔷 PRODUCT-BE-E-04 getProductTechPackBulkCountV1 (bulk wrapper, ordering fix) 🔴🔬 Spike-gated on SPIKE-02 (TechPack Aggregate) | 🔴 Very High [XL] | Query Calls: attachment, search | SPIKE-02, E-03 | Intent — Return TechPack counts for many products at once, in the caller's order. Today — the bulk version runs all N single-product lookups concurrently and - returns them in whatever order they happen to finish — not the order the caller asked for. - If a… Done when: • bulk(P1..Pn) == [single(P1)..single(Pn)] in input order • empty list → [] | ☐ order preserved ☐ empty ☐ Parity: DGS response matches spark-internal-graphql baseline |

ℹ️  PRODUCT-BE-E-01: Note: ADR-012 pin-down 4 (async-refinement scope — recentlyViewed/todo/favorite/user-profile only, never
> ACL or partner status) and pin-down 6 (keep the actionType dispatcher shape for phase-1 parity; splitting
> is a v2 API question) are scope/architecture statements, not independently testable behavior — no dedicated
> AC needed; honored by construction in the service shape above.

🔗 Phase F — Federation & Stitching  (8 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 PRODUCT-BE-F-04 ResourcesCount.measurementSets (internal, from Measurement) | 🟢 Low [XS] | Field Resolver | E-03 | Intent — Fills in the product's measurement-set count — answered in-process by the co-located Measurement code. Done when: • measurementSets resolves in-process; no gateway hop; parity vs facade |
| 🔸 PRODUCT-BE-F-06 ResourcesCount.productBoms + packagingBoms + boms (internal, from BOM) | 🟢 Low [XS] | Field Resolver | E-03 | Intent — Fills in the product's BOM counts — answered in-process by the co-located BOM code. Done when: • productBoms/packagingBoms/boms resolve in-process; no gateway hop; parity vs facade |
| 🔸 PRODUCT-BE-F-08 ResourcesCount.watchlists (internal, from Watchlist) | 🟢 Low [XS] | Field Resolver | E-03 | Intent — Fills in the product's watchlist count — answered in-process by the co-located Watchlist code. Done when: • watchlists resolves in-process; no gateway hop; parity vs facade |
| 🔸 PRODUCT-BE-F-09 Retire the TechPack aggregation facade | 🟢 Low [XS] | Field Resolver | H-01, H-02, H-03, F-04, H-04, F-06, H-05, F-08 | Intent — Removes the temporary TechPack 'facade' once every count is served by its real owner. Today — remove TechPackAggregatorClient; TechPackDataFetcher returns key+context only; decommission the facade Done when: • all 11 ResourcesCount fields resolve via federation • facade health-check endpoint returns 404 (decommissioned) • no orphaned config (feature flags, Feign client beans, etc. referencing the retired facade) |
| 🔸 PRODUCT-BE-F-10 Hive Gateway supergraph composition | 🟢 Low [XS] | Field Resolver | H-06, F-14 | Intent — Composes all the subgraphs into one federated graph at the gateway. Today — add plm-product subgraph URL; verify composition with VMM/IG/CORONA/Doppler stubs; smoke-test cross-subgraph query Done when: • supergraph composes • cross-subgraph smoke test passes • composition runs as a CI gate on every schema change (not a one-off) and fails on any @key/type-name mismatch between subgraphs (regression guard for federation-review/03 §R1–R5) • zero remaining contract mismatches: VMM_BusinessPartner/VMM_Brand keyed id; every entity keyed id (Claims/Packaging/Watchlist/Dieline synthesize id from humanId — program decision 2026-07-17); ProductDetails/MeasurementPaged names aligned |
| 🔸 PRODUCT-BE-F-11 Platform stub verification (VMM/IG/Doppler/CORONA/APEX) | 🟢 Low [XS] | Field Resolver | F-10 | Intent — Verifies each external platform (VMM, IG, etc.) resolves through its stub. Today — confirm the gateway resolves full platform types from product-emitted @key stubs Done when: • each platform type resolves via its stub key |
| 📄 PRODUCT-BE-F-12 Deferred partner-wrapper decision (drift mutations) | 🟢 Low [XS] | Schema | E-01 | Intent — Decide the fate of three drift partner mutations that have no resolvers. Today — three old mutation names (removeProductBusinessPartner, - dropProductBusinessPartner, unDropProductBusinessPartner) still exist in the schema, but nothing calls them… Done when: • traffic survey complete • decision implemented |
| 📄 PRODUCT-BE-F-14 Cross-subgraph contract alignment (keys, type names, paged wrappers) | 🟢 Low [XS] | Schema | — | Intent — Fixes the naming/key mismatches between product's stubs and the owning schemas so the supergraph can actually compose. Done when: • plm-product schema compiles standalone with every referenced type declared (including TeamPaged, TeamPagedV2, WorkspacesPagedV2, DiscussionElastic) • hive compose over plm-product + spark-claims + platform stubs reports zero key/name conflicts, including zero @shareable field-shape conflicts on TeamPaged (must match claims' declaration exactly) • CORONA_ItemDetails entity form implemented per the 2026-07-17 decision (keyed tcinId; Corona inflates via the gateway) • Blocks released: F-10, CLAIM-BE-H-01, CLAIM-BE-H-02 |

🧪 Phase G — Field Resolvers & Tests  (16 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria | Key Tests |
| --- | --- | --- | --- | --- | --- |
| 🔸 PRODUCT-BE-G-01 Product.attachmentsWithMetaData | 🔴 Very High [XL] | Field Resolver Calls: attachment, relationship | — | Intent — Resolve a product's mixed attachments-with-metadata feed (files + discussions + samples). Today — the attachments panel on a product shows a mixed feed — actual file - attachments, plus discussions and samples that are also surfaced as if they were attachments… Done when: • parity for mixed attachment/discussion/thread/sample • ordering rank preserved (product=0, discussion=1, sample=2; createdAt DESC tiebreak) • product side hydrates both v2 and v3 attachment ids (no v2-ignoring gap) — the workspace-side v2-ignoring behaviour (ADR-018 pin-down 2) does not apply here; confirmed by fixture • thread→parent-discussion lookup guarded — a thread whose parent discussion falls outside the walk is skipped + logged, not a crash (accepted deviation, ADR-018 pin-down 3) • discussion data sourced via a direct discussion-service client + one batched replies call — the cross-resolver import and the per-discussion reply N+1 are both gone (ADR-018 pin-down 4) • attachmentElasticResponseFeatureFlag state surveyed across every environment BEFORE fixtures are recorded — blocking precondition on fixture recording (ADR-018 pin-down 5) • draft-filter TODO ("ACL should be doing this") kept verbatim in the ported code — filter not removed; ACL-enforcement backlog item filed separately (ADR-018 pin-down 7) • createAttachmentPaged's relatedResources precedence bug preserved exactly as today's output — pinned by a fixture using a row with its own non-empty relatedResources (ADR-018 pin-down 9) • independent fetches (token, discussions, threads, samples) run in parallel — accepted performance fix (ADR-018 pin-down 10). > Note: the missing-ACL skip+log behaviour here is intentionally asymmetric with G-02's missing-ACL throw (ADR-014 pin-down 2) — each surface's UI is calibrated to its own behaviour; this asymmetry is by design (ADR-018 pin-down 8) and should not be "fixed" to match | ☐ merge ☐ ordering ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔸 PRODUCT-BE-G-02 Product.components | 🔴 Very High [XL] | Field Resolver Calls: search | — | Intent — List everything attached to a product, tagged by type, with counts. Today — the components tab lists everything attached to a product — measurements, - claims, boms, product-details, packaging — tagged by type, with counts (how many are… Done when: • parity for 50+ components, incl. a product with > 100 components (chunked ACL) and a claim with a missing ACL record (throw path preserved, ADR-014 pin-down 2) • archivedCount/countByComponents match source exactly (incl. name/status fallbacks and type 2 → packagingBom) • ACL batched — exactly one getAccessControlBatch call per resolution (no N+1), asserted by a call-count test • no info.variableValues read; explicit field args confirmed against UI queries (contract test, ADR-014 pin-down 5) • sample→discussion +1 roll-up quirk preserved exactly, not "fixed" to real counts — pinned by a dedicated fixture documenting the quirk as intentional (ADR-014 pin-down 4) • packaging elastic query joins the 4-way Promise.all (5-way parallel) instead of running sequentially after — accepted performance fix, not a behaviour change (ADR-014 pin-down 7). > Note: ADR-014 pin-downs 3 (counts scalar-0 → zeros-object fix) and 8 (WorkspaceV2.products include-flags delegation) are WorkspaceV2-side, not Product-side — they belong to the later-phase WorkspaceV2 twin story (WORKSPACE-BE-G-02/G-04), not here | ☐ merge ☐ counts ☐ batched ACL ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔸 PRODUCT-BE-G-03 Product.attachments + attachmentsV3 + attachmentSummary + ProductTemplate.attachmentsData | 🟠 High [L] | Field Resolver Calls: attachment, search | G-01 | Intent — Resolve the product's attachment views (via a shared enrichment service). Today — four related resolvers sharing AttachmentEnrichmentService (G-01) Done when: • each field returns its shape • shares G-01 service • thin fields inherit all of G-01's fixtures/pin-downs by construction (no separate fixture set) | ☐ each field ☐ draft discussion attachment fixture (draft filter) ☐ workspace-v2-only-attachments fixture ☐ both attachmentsV3 modes (args-present elastic vs args-absent walk/flag) produce parity output ☐ Parity: DGS response matches spark-internal-graphql baseline |
| 🔸 PRODUCT-BE-G-04 ProductsCategories.categories (12-case) + DopplerDepartment fields | 🟡 Medium [M] | Field Resolver Calls: doppler | — | Intent — Resolve the polymorphic categories union (12 branches) and department fields. Today — categories is a polymorphic union — depending on which category type - the caller asked for, a different one of 12 branches builds the response shape. - Two of those… Done when: • each category type built correctly • Doppler fetched once | — |
| 🔸 PRODUCT-BE-G-05 Product.samples + sampleIds + elasticSamplesList | 🟡 Medium [M] | Field Resolver Calls: sampleV2, search | — | Intent — Resolve a product's samples from local context (removing the fragile args hack). Today — today these fields reach into GraphQL's internal info.variableValues to read arguments that were passed to a different, parent query — a fragile, implicit way to pass… Done when: • samples/sampleIds/elastic resolve • no info.variableValues read | — |
| 🔸 PRODUCT-BE-G-06 Product.teams + discussionsV2 + discussionsCount + workspaces | 🟡 Medium [M] | Field Resolver Calls: teamV2, discussion, search, workspaceV2 | — | Intent — Resolve a product's team / discussion / workspace fields. Today — team/discussion/workspace elastic lookups Done when: • each field resolves | — |
| 🔴🔬 🔸 PRODUCT-BE-G-07 Product.vendorAttributes + businessPartners + droppedPartners + unDroppablePartners + status 🔴🔬 Spike-gated on SPIKE-04 (Not-Removable / Undroppable Partners) | 🟡 Medium [M] | Field Resolver Calls: vmm | SPIKE-04 | Intent — Resolve a product's partner fields (with id normalization). Today — business-partner ids sometimes arrive as strings that need to be - parsed to ints before VMM will accept them (vmmUtils's int-parse normalization) — an easy detail to… Done when: • partners resolve via VMM • status merge correct | — |
| 🔸 PRODUCT-BE-G-08 Product.measurementSets + claims + bom + productBom + packagingBom + productDetails + variations + associateProductsAsks | 🟡 Medium [M] | Field Resolver | — | Intent — Resolve the 8 'ask a sibling domain' product fields (bom, measurement, …), each on demand. Today — each of these 8 fields is "go ask a sibling domain (bom, measurement, - etc.) for this product's data" — but only if the caller asked for it (each has an includeXxx… Done when: • each sibling field resolves internally • includeXxx branches honored | — |
| 🔸 PRODUCT-BE-G-09 Product.productWorkspaceAttributes + productWorkspaceInfo | 🟡 Medium [M] | Field Resolver Calls: workspaceV2, search, tag | — | Intent — Resolve a product's per-workspace attributes (incl. lazy designCycle). Today — designCycle is computed lazily today — an inline async () => ... - closure attached to the value, evaluated only if a caller actually reads that sub-field. -… Done when: • both fields resolve • designCycle is a nested fetcher | — |
| 🔸 PRODUCT-BE-G-10 Product.ancestryProducts + rating + reservedDpcis | 🟡 Medium [M] | Field Resolver Calls: relationship, rating, apex | — | Intent — Resolve a product's ancestry, rating and reserved-DPCI fields. Today — rating via RatingClient; reservedDpcis via getReservedDpcisFromApex Done when: • ancestry/rating/dpcis resolve • rating null-on-error | — |
| 🔴🔬 🔸 PRODUCT-BE-G-11-1 Product.notRemovablePartnerIds + notRemovableWorkspaceIds 🔴🔬 Spike-gated on SPIKE-04 (Not-Removable / Undroppable Partners) | 🟡 Medium [M] | Field Resolver Calls: vmm, workspaceV2 | SPIKE-04 | Intent — Compute which partners/workspaces can't be removed (still referenced). Today — to figure out which partners/workspaces can't be removed from a product (e.g. because they're the last remaining owner), today's code calls into 4-5 other field… Done when: • notRemovablePartnerIds/notRemovableWorkspaceIds return the same results as source (same logical union of the underlying sibling data) • No reflective resolver invocation remains — every call is a direct, statically-typed service method call • samples lane's variableValues coupling contract-checked against the UI's samples queries BEFORE cutover — this is a blocking pre-condition, not a nice-to-have (ADR-016 pin-down 2) • the 5 sequential source fetches (discussions/attachments/components/samples/watchlists) parallelize — accepted deviation, union output is order-insensitive (ADR-016 pin-down 3) • the serial ACL chunk loop (getAccessControlBatch) parallelizes — same fix family as ADR-015 pin-down 3 (ADR-016 pin-down 4) • watchlist lane's productWorkspaceInfo[0]-only / first-workspace-only scope preserved exactly as today's semantics (ADR-016 pin-down 8) • the Relationship-Service walk inside unDroppablePartners's owner-enumeration client is a quarantined interim — each lane's future arrival deletes its own share of the walk (ADR-016 pin-down 9) • schema-diff gate proves no lane field (…PartnerIds naming + externals until fed-2/@inaccessible is usable) is exposed to clients (ADR-016 pin-down 10) | — |
| 🔸 PRODUCT-BE-G-11-2 Product.associateProductsAsks + Product.variations | 🟡 Medium [M] | Field Resolver | — | Intent — Resolve two sibling passthroughs (product-asks and variations). Today — two straightforward sibling passthroughs — associateProductsAsks - (the product-ask records tied to this product) and variations (sibling product variation records) —… Done when: • associateProductsAsks resolves the product's ask records • variations resolves the product's variation records | — |
| 🔸 PRODUCT-BE-G-13 IG/tag/tcin/spg + template trivial-field group | 🟡 Medium [M] | Field Resolver Calls: ig, tag, corona | — | Intent — Resolve a group of trivial IG / tag / TCIN / template fields. Today — department/departments/clazz/brand/brands/divisions/productTemplateDepartments, tags, tcins, SPARK_Tcin.itemDetails (CORONA), SPARK_PackagingAttribute.spg (internal… Done when: • each field resolves to the right source | — |
| 🔸 PRODUCT-BE-G-14 Simple user/status fields + trivial pass-throughs (bundle) | 🟢 Low [XS] | Field Resolver Calls: userAttributes | — | Intent — Resolve simple people / status fields and trivial pass-throughs. Today — createdBy/updatedBy/versionCreatedBy (user-profile), ProductComponentStatus.updatedBy, SPARK_ResourcesCount.productThumbnailId (re-fetch product), plus ~60 direct… Done when: • user fields resolve (null id → null) • productThumbnailId re-fetches • scalars mapped | — |
| 📄 PRODUCT-BE-G-15 Port product utils to Kotlin | 🟡 Medium [M] | Service | — | Intent — Port the shared product utility helpers to Kotlin. Today — attachmentUtils, partnerUtils, teamUtils, productUtils, componentStatusUtils, resolvePaging, vmmUtils, accessControlUtils, removePartnerUtils Done when: • utils ported with unit tests • counter logic fixed/verified • ACL batch parallel-chunked | — |
| 🔸 PRODUCT-BE-G-17 Entity references on partner/lineage value types (recommended, PO-gated) | 🟡 Medium [M] | Field Resolver Calls: vmm | G-01 | Intent — Adds partner { … } / product { … } object fields next to the existing ids on the Today — schema adds partner: VMM_BusinessPartner (emit {id} key stub — the gateway Done when: • PO approval recorded (OQ-5) before implementation starts • New object fields resolve; all existing id fields unchanged • product lineage refs batch via DataLoader (no N+1 on ancestryProducts) • Codegen/contract parity suite passes with the additive fields present | — |

ℹ️  PRODUCT-BE-G-01: Note: the missing-ACL skip+log behaviour here is intentionally asymmetric with G-02's missing-ACL throw (ADR-014 pin-down 2) — each surface's UI is calibrated to its own behaviour; this asymmetry is by design (ADR-018 pin-down 8) and should not be "fixed" to match.

ℹ️  PRODUCT-BE-G-02: Note: ADR-014 pin-downs 3 (counts scalar-0 → zeros-object fix) and 8 (WorkspaceV2.products include-flags delegation) are WorkspaceV2-side, not Product-side — they belong to the later-phase WorkspaceV2 twin story (WORKSPACE-BE-G-02/G-04), not here.

🧬 Phase H — Entity Resolution  (6 stories)

| Story | Complexity | Type / Calls | Depends On | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 🔸 PRODUCT-BE-H-01 ResourcesCount.productAttachments + discussionAttachments (federated, from Attachment) | 🟡 Medium [M] | Field Resolver | E-03 | Intent — Contribute attachment counts to the product's TechPack rollup (from Attachment). Done when: • productAttachments/discussionAttachments resolve on the federated ResourcesCount; the E-03 facade stops populating them • Parity vs the facade for the same inputs • Field is live in prod only after plm-attachment is deployed (ship gate honored) |
| 🔸 PRODUCT-BE-H-02 ResourcesCount.discussions (federated, from Discussion) | 🟡 Medium [M] | Field Resolver | E-03 | Intent — Fills in the product's discussion count — answered by the Discussion service once it's live. Done when: • discussions resolves on the federated ResourcesCount; facade stops populating it; parity vs facade • Live in prod only after plm-discussion is deployed |
| 🔸 PRODUCT-BE-H-03 ResourcesCount.sample (federated, from Sample) | 🟡 Medium [M] | Field Resolver | E-03 | Intent — Fills in the product's sample count — answered by the Sample service once it's live. Done when: • sample resolves on the federated ResourcesCount; facade stops populating it; parity vs facade • Live in prod only after plm-sample is deployed |
| 🔸 PRODUCT-BE-H-04 ResourcesCount.claims (federated, from Claim) | 🟡 Medium [M] | Field Resolver | E-03 | Intent — Fills in the product's claims count — answered by the Claims service once it's live. Done when: • claims resolves on the federated ResourcesCount; facade stops populating it; parity vs facade • Live in prod only after spark-claims is deployed |
| 🔸 PRODUCT-BE-H-05 ResourcesCount.constructions (federated, from Construction) | 🟡 Medium [M] | Field Resolver | E-03 | Intent — Fills in the product's construction count — answered by the Construction service once it's live. Done when: • constructions resolves on the federated ResourcesCount; facade stops populating it; parity vs facade • Live in prod only after the construction subgraph is deployed |
| 🔸 PRODUCT-BE-H-06 Product entity fetcher (@DgsEntityFetcher) for cross-subgraph references | 🟡 Medium [M] | Field Resolver | B-01 | Intent — Lets other subgraphs (today: claims) turn a bare Product{id} reference into a full product through the gateway. Today — @DgsEntityFetcher(name = "Product") → `productService Done when: • _entities resolves Product representations with a single batched backend call • Unknown ids yield null entries without failing the whole _entities response • End-to-end: a claims-subgraph query { getClaims { product { description } } } hydrates through the gateway (pairs with CLAIM-BE-G-03) • No ACL plumbing introduced |

Frontend

# Federated GraphQL Breakdown — Product · Frontend

| Client | pdex-ui-react (Apollo Client) |
| --- | --- |
| Backend subgraph | plm-product (host) |
| Total FE Stories | 13 |
| Impact | 🔴 3 High · 🟡 9 Medium · 🟢 1 Low |
| Estimated effort | 68–104 days (single-engineer) |
| Phase-1 surface | 66 operation-to-root-field rows · 20 client files · 48 components |
| Generated | 2026-07-21 |

A frontend story is Done only after every backend story it depends on has been delivered. Full story text (objectives, required changes, AC, testing) lives in fe-08-frontend-stories.md — the hand-authored source of truth; this page is the per-domain planning view.

What Are We Changing?

•  Point the Product GraphQL operations in pdex-ui-react at the federated router (subgraph plm-product (host)) behind the platform feature flag, then remove legacy-gateway assumptions (typenames, cache keys, fragments).

•  Cutover is per-domain and reversible: dual-run first, flag flip after parity, legacy path kept until the exit criterion holds.

Stories

| Story | Title | Type | Impact | Effort | Depends on | Operations |
| --- | --- | --- | --- | --- | --- | --- |
| PRODUCT-FE-001 | Migrate all getProduct documents (single root query, 17 flavors) | Query migration | 🔴 High | 13–19 days | PRODUCT-BE-B-01, PRODUCT-BE-F-10, PRODUCT-BE-G-01, PRODUCT-BE-G-02, PRODUCT-BE-G-03, PRODUCT-BE-G-06, PRODUCT-BE-G-07, PRODUCT-BE-G-08, PRODUCT-BE-G-09, PRODUCT-BE-G-10, PRODUCT-BE-G-13, PRODUCT-BE-G-14, PRODUCT-BE-S-01, PRODUCT-BE-B-04 | getProduct |
| PRODUCT-FE-002 | Migrate getProducts documents (list/search/bulk-create) | Query migration | 🔴 High | 6–9 days | PRODUCT-BE-B-02, PRODUCT-BE-G-13, PRODUCT-BE-S-02 | getProducts |
| PRODUCT-FE-003 | Migrate getProductsByIds documents (bulk-by-id reads) | Query migration | 🟡 Medium | 4–6 days | PRODUCT-BE-B-03 | getProductsByIds |
| PRODUCT-FE-004 | Migrate getProductStatus documents | Query migration | 🟡 Medium | 5–8 days | PRODUCT-BE-B-01, PRODUCT-BE-B-02, PRODUCT-BE-B-03, PRODUCT-BE-F-10, PRODUCT-BE-G-06, PRODUCT-BE-G-07, PRODUCT-BE-G-09, PRODUCT-BE-G-13, PRODUCT-BE-S-01 | getProductStatus |
| PRODUCT-FE-005 | Migrate getProductTemplates documents | Query migration | 🟡 Medium | 6–9 days | PRODUCT-BE-B-03, PRODUCT-BE-C-02, PRODUCT-BE-C-03, PRODUCT-BE-G-03, PRODUCT-BE-G-04, PRODUCT-BE-G-06, PRODUCT-BE-G-07, PRODUCT-BE-G-08, PRODUCT-BE-G-13, PRODUCT-BE-G-14, PRODUCT-BE-H-07, PRODUCT-BE-S-01, PRODUCT-BE-S-02 | getProductTemplates |
| PRODUCT-FE-006 | Migrate getCategories documents | Query migration | 🟢 Low | 2–3 days | PRODUCT-BE-G-03, PRODUCT-BE-G-13 | getCategories |
| PRODUCT-FE-007 | Migrate product rules administration | Query + mutation migration | 🟡 Medium | 4–6 days | PRODUCT-BE-B-07, PRODUCT-BE-B-08, PRODUCT-BE-B-09, PRODUCT-BE-B-10, PRODUCT-BE-B-11, PRODUCT-BE-C-05, PRODUCT-BE-D-15, PRODUCT-BE-D-16, PRODUCT-BE-D-17, PRODUCT-BE-G-07, PRODUCT-BE-G-13, PRODUCT-BE-H-08 | getProductRules, getProductRulesById, getAllAvailableRules, getProductDeptRules, getProductBPRules, searchProductRules, addProductRule, updateProductRule, deleteProductRule |
| PRODUCT-FE-008 | Migrate simple product mutations | Mutation migration | 🟡 Medium | 6–10 days | PRODUCT-BE-D-01, PRODUCT-BE-D-02, PRODUCT-BE-D-03, PRODUCT-BE-D-04, PRODUCT-BE-D-05, PRODUCT-BE-D-10, PRODUCT-BE-D-13, PRODUCT-BE-D-14 | addProduct, addProducts, updateProduct, bulkUpdateProducts, carryForwardProduct, updateViewToggle, linkProduct, unlinkProduct |
| PRODUCT-FE-009 | Migrate team and partner assignment mutations | Mutation migration | 🟡 Medium | 4–6 days | PRODUCT-BE-D-06, PRODUCT-BE-D-07, PRODUCT-BE-D-12, PRODUCT-FE-001 | addTeamsToProduct, addBusinessPartnersToProductWithType, updateProductTeamsWorkspaceContext |
| PRODUCT-FE-010 | Migrate partner drop/undrop orchestration | Mutation migration (complex) | 🔴 High | 8–12 days | PRODUCT-BE-S-03, PRODUCT-BE-D-09 | productBusinessPartnerActions, updateBusinessPartnerStatuses |
| PRODUCT-FE-011 | Migrate TechPack count queries (facade-then-federate) | Query migration (staged) | 🟡 Medium | 4–6 days (step 1) + 4–6 days (step 2) | PRODUCT-BE-E-03, PRODUCT-BE-E-04, PRODUCT-BE-F-06, PRODUCT-BE-F-08, PRODUCT-BE-G-08, PRODUCT-BE-H-01, PRODUCT-BE-H-02, PRODUCT-BE-H-03, PRODUCT-BE-H-04, PRODUCT-BE-H-05 | getProductTechPackCountV1, getProductTechPackBulkCountV1 |
| PRODUCT-FE-012 | Migrate component status mutations and rollup counts | Mutation migration | 🟡 Medium | 3–5 days | PRODUCT-BE-D-18, PRODUCT-BE-E-02, PRODUCT-FE-001 | updateComponentStatus, updateComponentStatuses |
| PRODUCT-FE-013 | Verify fragment type-conditions, __typename logic and cache keys against federated type names | Verification / refactor | 🟡 Medium | 3–5 days | PRODUCT-BE-F-14 | cross-cutting (no single operation) |

Recommended Implementation Order

Staged from each story's dependencies: the backend phase its BE stories sit in (reads → search → writes → sagas) plus in-domain FE→FE chains. Stories in the same step are independent of each other and parallelize. ADR ratifications are entry gates, not ordering edges.

| Step | Stories (parallel set) | Waits for | Focus |
| --- | --- | --- | --- |
| 1 | 🟡 PRODUCT-FE-003 | PRODUCT-FE-003 → PRODUCT-BE-B-03 | Reads cutover — needs backend phase A/B reads live |
| 3 | 🟡 PRODUCT-FE-008 | PRODUCT-FE-008 → PRODUCT-BE-D-01, PRODUCT-BE-D-02, PRODUCT-BE-D-03, PRODUCT-BE-D-04 (+4) | Writes — needs backend phase D mutations |
| 4 | 🟢 PRODUCT-FE-006, 🟡 PRODUCT-FE-007, 🟡 PRODUCT-FE-011, 🟡 PRODUCT-FE-013 | PRODUCT-FE-006 → PRODUCT-BE-G-03, PRODUCT-BE-G-13<br>PRODUCT-FE-007 → PRODUCT-BE-B-07, PRODUCT-BE-B-08, PRODUCT-BE-B-09, PRODUCT-BE-B-10 (+8)<br>PRODUCT-FE-011 → PRODUCT-BE-E-03, PRODUCT-BE-E-04, PRODUCT-BE-F-06, PRODUCT-BE-F-08 (+6)<br>PRODUCT-FE-013 → PRODUCT-BE-F-14 | Complex writes / sagas — needs backend phase E + ADR ratification |
| 5 | 🔴 PRODUCT-FE-001, 🔴 PRODUCT-FE-002, 🟡 PRODUCT-FE-004, 🟡 PRODUCT-FE-005, 🔴 PRODUCT-FE-010 | PRODUCT-FE-001 → PRODUCT-BE-B-01, PRODUCT-BE-F-10, PRODUCT-BE-G-01, PRODUCT-BE-G-02 (+10)<br>PRODUCT-FE-002 → PRODUCT-BE-B-02, PRODUCT-BE-G-13, PRODUCT-BE-S-02<br>PRODUCT-FE-004 → PRODUCT-BE-B-01, PRODUCT-BE-B-02, PRODUCT-BE-B-03, PRODUCT-BE-F-10 (+5)<br>PRODUCT-FE-005 → PRODUCT-BE-B-03, PRODUCT-BE-C-02, PRODUCT-BE-C-03, PRODUCT-BE-G-03 (+9)<br>PRODUCT-FE-010 → PRODUCT-BE-S-03, PRODUCT-BE-D-09 | Externally gated — search/read-hub decision |
| 6 | 🟡 PRODUCT-FE-009, 🟡 PRODUCT-FE-012 | PRODUCT-FE-009 → PRODUCT-BE-D-06, PRODUCT-BE-D-07, PRODUCT-BE-D-12<br>PRODUCT-FE-012 → PRODUCT-BE-D-18, PRODUCT-BE-E-02 | Follow-on cutover — after the stories it depends on |

Cutover flow: PRODUCT-FE-003 → PRODUCT-FE-008 → PRODUCT-FE-006 → PRODUCT-FE-007 → PRODUCT-FE-011 → PRODUCT-FE-013 → PRODUCT-FE-001 → PRODUCT-FE-002 → PRODUCT-FE-004 → PRODUCT-FE-005 → PRODUCT-FE-010 → PRODUCT-FE-009 → PRODUCT-FE-012.

Recommended Story Graph — 1 Frontend Engineer

The staged order map above, run by one frontend engineer. Steps re-sync at each stage because the stage's backend gate — not engineer availability — is the limiter.

| Step | 👤 FE-1 | Backend gate (focus) |
| --- | --- | --- |
| 1 | 🟡 PRODUCT-FE-003 (4–6d) | Reads cutover — needs backend phase A/B reads live |
| 3 | 🟡 PRODUCT-FE-008 (6–10d) | Writes — needs backend phase D mutations |
| 4 | 🟡 PRODUCT-FE-007 (4–6d)<br>🟡 PRODUCT-FE-011 (4–6d)<br>🟡 PRODUCT-FE-013 (3–5d)<br>🟢 PRODUCT-FE-006 (2–3d) | Complex writes / sagas — needs backend phase E + ADR ratification |
| 5 | 🔴 PRODUCT-FE-001 (13–19d)<br>🔴 PRODUCT-FE-010 (8–12d)<br>🔴 PRODUCT-FE-002 (6–9d)<br>🟡 PRODUCT-FE-005 (6–9d)<br>🟡 PRODUCT-FE-004 (5–8d) | Externally gated — search/read-hub decision |
| 6 | 🟡 PRODUCT-FE-009 (4–6d)<br>🟡 PRODUCT-FE-012 (3–5d) | Follow-on cutover — after the stories it depends on |

Elapsed (nominal midpoints): ~86 FE build days — calendar time is set by the backend gates, not FE capacity.

References

•  fe-08-frontend-stories.md — full story text (source of truth).

•  fe-09-story-dependency-matrix.md — FE ↔ BE dependency matrix.

•  fe-10-migration-sequencing.md — program-level waves and external gates.

•  fe-03-merged-inventory.md — every operation × backend root field for this domain.

•  FederatedGqlBreakDown-product.md — the combined Backend + Frontend breakdown this section lives in.