Implementation Plan — 1 Backend + 1 Frontend Engineer

🏷️ Tags: dgs-migration · team-plan — Generated: 2026-07-21 · Derived from the same story parsers as the per-domain breakdowns (grouped-XS merges included), so story counts and day totals reconcile.

Day figures are nominal midpoints of AI-estimated ranges — confirm in refinement. 1 sprint = 10 working days. d0 = program start. Team size and domain sequencing are set in team_config.py — change them there and regenerate.

Team & operating model

•  The backend engineer runs all 8 domains sequentially: Product first (host DGS, shared wiring, largest surface — the foundation the rest build on), then the remaining domains in team_config.BE_QUEUE order.

•  The frontend engineer follows the program waves (fe-10) sequentially: watchlist pilot first (1-sprint production soak is the wave-2 entry gate), then each domain cutover in turn.

•  A domain's FE cutover starts when its backend phases A–E (reads, search, writes) are live; BE phases F–G (federation stitches, field-resolver parity) trail behind the flip and don't block it. (Refinement lever: FE read-stories can start dual-running right after B/C — that pulls each FE start earlier than shown here.)

•  Phase-0 spikes (SPIKE-01…07) are not on these lanes — run them in the first 1–2 sprints alongside PRODUCT-BE scaffold work; E-phase stories are gated on their outcomes.

Backend lane

| # | Domain | Lane | Stories | Est. days (lo–hi) | Day window | FE gate (A–E done) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Product | — | 69 | 200 (138–262) | d0–d200 (spr 1–20) | d108 |
| 2 | Watchlist | — | 13 | 31 (21–41) | d200–d231 (spr 21–24) | d219 |
| 3 | Product Details | — | 12 | 31 (21–41) | d231–d262 (spr 24–27) | d252 |
| 4 | Measurement | — | 30 | 56 (38–75) | d262–d318 (spr 27–32) | d304 |
| 5 | Packaging | — | 23 | 54 (37–72) | d318–d373 (spr 32–38) | d356 |
| 6 | BOM | — | 37 | 91 (62–120) | d373–d464 (spr 38–47) | d420 |
| 7 | Claims | — | 20 | 50 (34–66) | d464–d514 (spr 47–52) | d494 |
| 8 | Impression | — | 7 | 14 (9–18) | d514–d528 (spr 52–53) | d520 |

•  backend drains at d528 — post-launch F-phase stitches and G-phase parity leftovers land after the queue above.

•  Cross-subgraph F-phase stories that wait on later-phase domains (attachment/discussion/sample/search subgraphs) are excluded from these gates — they land post-launch when the owning subgraph exists.

Frontend lane

| Wave | Domain | Lane | FE days | Waits for | Day window |
| --- | --- | --- | --- | --- | --- |
| 1 | Watchlist | — | 8 | BE Watchlist A–E done (d219) | d219–d228 (spr 22–23) |
| 2 | Product Details | — | 10 | BE Product Details A–E done (d252) | d252–d262 (spr 26–27) |
| 2 | Measurement | — | 16 | BE Measurement A–E done (d304) | d304–d319 (spr 31–32) |
| 2 | Packaging | — | 27 | BE Packaging A–E done (d356) | d356–d382 (spr 36–39) |
| 3 | BOM | — | 38 | BE BOM A–E done (d420) | d420–d458 (spr 43–46) |
| 3 | Claims | — | 22 | BE Claims A–E done (d494) | d494–d516 (spr 50–52) |
| 4 | Product | — | 86 | BE Product A–E done (d108) + pilot soak (d238) | d516–d602 (spr 52–61) |
| 4 | Impression | — | 4 | BE Impression A–E done (d520) | d602–d606 (spr 61–61) |

•  The frontend engineer is gate-bound, not capacity-bound — between gates they work parity dashboards, dual-run monitoring and rollback drills, and pre-pull the next domain's fragment/codegen prep.

•  Search-gated stories (MST-FE-002, BOM-FE-003, PRODUCT-FE-002) also wait on the search read-hub decision — external to this plan and may slide independently.

•  Impression rides its partner flips (IMPRESSION-FE-001 with BOM-FE-002, IMPRESSION-FE-002 with PRODUCT-FE-001).

Milestones

| Milestone | ≈ Day | ≈ Sprint |
| --- | --- | --- |
| 🚦 Watchlist pilot live on the router | d228 | 23 |
| 🔗 First cross-subgraph cutover (Claims FE) | d516 | 52 |
| 🏁 Product backend complete (plm-product host) | d200 | 21 |
| 🧱 Backend lane drained (both subgraphs schema-complete) | d528 | 53 |
| ✅ All FE cutovers flipped | d606 | 61 |
| Program complete (excl. post-launch F-phase) | d606 | 61 |

≈ 61 sprints (~30 months) with this 1 BE + 1 FE team — see 00-program-overview.md for the program-level totals. Buffered (+20%) planning figure: ~73 sprints.

How to read this with the other docs

•  Per-domain lane detail: Recommended Story Graph — 1 Backend Engineer and — 1 Frontend Engineer in the Backend / Frontend sections of each FederatedGqlBreakDown-{domain} page.

•  Dependency-only view (no team constraint): Recommended Implementation Order on the same pages.

•  Program waves and external gates: analysis/program/fe-10-migration-sequencing.md.

•  Team size and domain sequencing: team_config.py.

Team plan · generated 2026-07-21 by generate_team_plan.py.